## Slide 1: FY27-Q1, Q2, Q3 & Q4 Plans
Enterprise Tech

## Slide 2: Business Systems – FY26-27/Q1, Q2

## Slide 3: Corporate Systems – FY26-27/Q1

## Slide 4
24th April ‘26
Corporate Systems - FY26-27 Q1 Release Plan (HR Tech)
Initiatives | Programs/Projects | Value Justification/Realization
Compensation Planning & Increment Letter + Bonus Letter Generation FY 26 Phase 1 Workforce Analytics – Employee Snapshot Related Dashboard revamp [Adhoc] Offer Letters Revamp Ph 1 Life ka Plan & Azure SSO Integration | Compensation Planning Templates, Increment & Bonus Letters Templates Implementation Ph 1 Workforce Analytics – Employee Snapshot Related Dashboard revamp [Adhoc] Offer Letters Revamp Ph 1 – Optimizing offer letters (merging of multiple letters) & incorporating wage code changes Life ka Plan & Azure SSO Integration | Standardizes and automates compensation communication, reducing manual effort and ensuring error‑free, timely rollouts. Provides deeper visibility into position structures, vacancies, and utilization through improved visuals and data accuracy, enabling better workforce planning. Reducing release TAT and rework while improving compliance and candidate experience Ensuring single source of truth (SuccessFactors) across systems & 100% data accuracy
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 5
27th May ‘26
Corporate Systems - FY26-27 Q1 Release Plan (HR Tech)
Initiatives | Programs/Projects | Value Justification/Realization
Crew Upgrade Automation Creating Employee Masters (Rule-Based with Validations) – Phase 1 [SkyFam] Weekend Duty Travel Alert on Email for SOD [Adhoc] Offer Letters Revamp Ph 2 Compensation Planning & Increment Letter + Bonus Letter Generation FY 26 Phase 2 | End‑to‑End Crew Upgrade Automation (basis tenure, certification, etc.) Creating Employee Masters (Rule-Based with Validations) – Phase 1 [SkyFam] Weekend Duty Travel Alert on Email for SOD (Carry‑forward + New Project) [Adhoc] Offer Letters Revamp Ph 2 – Optimizing offer letters (merging of multiple letters) & incorporating wage code changes Compensation Planning Templates, Increment & Bonus Letters Templates Implementation Ph 2 | Automates upgrade decisions through rule‑based logic, improving fairness, process speed, and operational efficiency. Creates a validated, rule-based employee master ensuring data integrity and reducing downstream system inconsistencies. Sends automated alerts for planned weekend travel, strengthening compliance, governance, and operational visibility. Reducing release TAT and rework while improving compliance and candidate experience Standardizes and automates compensation communication, reducing manual effort and ensuring error‑free, timely rollouts.
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 6
26th June ‘26
Corporate Systems - FY26-27 Q1 Release Plan (HR Tech)
Initiatives | Programs/Projects | Value Justification/Realization
[Adhoc] Life ka Plan SF Integration Onboarding 2.0 Enhancements Team Touchpoint on PMGM Automation AMS (Attendance Management System) Phase 1 – Linkage to Payroll Enable LWD FNF Input on PeopleStrong BRE – PeopleStrong Expense Module Workforce Analytics – Position Management Related Dashboard Implementation Creating Employee Masters (Rule-Based with Validations) – Phase 2 | [Adhoc] Life ka Plan SF Integration Onboarding 2.0 Enhancements Team Touchpoint on PMGM Automation AMS (Attendance Management System) Phase 1 – Linkage to Payroll Enable LWD FNF Input on PeopleStrong BRE – PeopleStrong Expense Module Workforce Analytics – Position Management Related Dashboard Implementation Creating Employee Masters (Rule-Based with Validations) – Phase 2 | Ensure single source of truth for Life Ka Plan (Insurance) portal for employee master & ensuring seamless automated entry & exit of employees making access active/inactive near real time Digitizes and streamlines onboarding workflows, improving new‑hire experience and reducing turnaround time. Automates scheduled manager–employee conversations, improving documentation quality and PMGM cycle compliance. Ensures accurate payouts by linking attendance directly to payroll, reducing manual reconciliations and errors. Automates full‑and‑final settlement inputs on LWD, reducing manual dependency and speeding up settlement timelines. Implements rule-based checks for expense claims, reducing policy violations and enabling faster reimbursement cycles. Delivers a more intuitive, comprehensive view of employee demographics, movements, and trends, improving stakeholder understanding and analytics adoption. Creates a validated, rule-based employee master ensuring data integrity and reducing downstream system inconsistencies
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 7
30th April ‘26
Corporate Systems - FY26-27 Q1 Release Plan (Fin Tech)
Initiatives | Programs/Projects | Value Justification/Realization | Actual/Revised Go-Live
Provision Module Implementation – Reversal & Adjustments | Provision Module Implementation – Reversal & Adjustments | Improves provisioning accuracy and regulatory compliance through automated, policy‑driven calculations. | 3rd May 2026
Approve Source List (Preferred supplier List) | Approve Source List (Preferred supplier List) | Ensures controlled sourcing from approved suppliers, reducing risk, improving compliance, and strengthening supplier governance. | 24th Apr 2026
Material rate change report – PO Variation | Material rate change report – PO Variation | Provides clear visibility into material price movements, enabling proactive cost control and informed procurement decisions. | 10th Apr 2026
Adhoc - Accelerating Supplier Activation at Parkland | Adhoc - Accelerating Supplier Activation at Parkland | Streamlining vendor onboarding reduces lead time for supplier activation, enabling faster sourcing, contracting, and purchase order execution.​ | 27th Apr 2026
Refund failure report for transaction not hitting XPP | Refund failure report for transaction not hitting XPP | Monitor refund payments, track failures, and provide actionable insights for reconciliation. | 30th Apr 2026
Pax Claim Phase II – Implementation with HSBC | Pax Claim Phase II – Implementation with HSBC | Automating the integration ensures faster processing of Pax Claim payments with reduced manual errors, leading to improved financial accuracy and timely disbursements​. Direct integration with banking partners strengthens data traceability and aligns with financial governance standards​. | 1st July 2026
Pax Claim – Implementation with PayU | Pax Claim – Implementation with PayU | Automating the integration ensures faster processing of Pax Claim payments with reduced manual errors, leading to improved financial accuracy and timely disbursements . Direct integration with banking partners strengthens data traceability and aligns with financial governance standards | On Hold
15 CA/CB - Phase II​ | 15 CA/CB - Phase II​ | Implementing a streamlined process for Form 15CA and 15CB enhances regulatory compliance, reduces tax-related risks, and ensures accurate reporting of foreign remittances. | 30th Apr 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 8
28th May ‘26
Corporate Systems - FY26-27 Q1 Release Plan (Fin Tech)
Initiatives | Programs/Projects | Value Justification/Realization | Actual/Revised Go-Live
Adhoc - User–Role Visibility for CTM | User–Role Visibility for CTM | Access has been provided to the CTM team to review roles assigned to users in SAP. This enables CTM to perform a basic validation to ensure that only minimum required access is assigned. Additionally, this report can be used by business users to conduct access reviews for their respective users, helping them proactively identify and manage user access in SAP. | 05th May 2026
Adhoc - Automated Inactivity Notifications | Automated Inactivity Notifications | An automated notification mechanism has been implemented for users who have not logged in to the system for more than 90 days. As part of this automation, users receive email reminders on the 80th and 85th day prompting them to log in. This initiative helps reduce instances of user lockouts triggered after 90 days by the automated job, ensuring continued compliance with audit requirements. | 05th May 2026
Adhoc - Vendor Master Integration with SuccessFactors Phase II | Vendor Master Integration with SuccessFactors Phase II | A single, consistent source of truth for vendor and service provider data across finance and HR processes. This integration reduces manual data maintenance, prevents data inconsistencies, and strengthens compliance and governance, while enabling faster onboarding, accurate payments, and improved operational efficiency | 03rd Jun 2026
Adhoc - HSBC House Bank Configuration for EBRS - MT940 Part II | HSBC House Bank Configuration FOR EBRS - MT940 Part II | Automates MT940 statement ingestion into EBRS for HSBC house banks, delivering faster cash reconciliation, reduced manual effort, and improved cash visibility across entities. Ensures a robust, audit-ready configuration aligned with bank and internal control requirements — minimizing operational risk and reconciliation delays. | 27th May 2026
Aged provisions Report | Aged provisions Report | Delivers a consolidated, accurate view of aged provisions across entities — enabling faster financial close, improved audit readiness, and better-informed decision-making on provision releases and write-offs. | 21st May 2026
Adhoc - MASS Customer Creation | MASS Customer Creation | Streamlines high-volume customer onboarding with improved data quality, faster processing, and reduced operational overhead. | 09th Jun 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 9
30th June ‘26
Corporate Systems - FY26-27 Q1 Release Plan (Fin Tech)
Initiatives | Programs/Projects | Value Justification/Realization | Actual/Revised Go-Live
Adhoc – F.13 GR/IR automatic clearing | F.13 GR/IR automatic clearing | 17K+ monthly line items automatic clearing functionality enabled reducing manual intervention and adherence to SAP best practices to streamline month end closing activities. | 02nd Jun 2026
Automated Statement Processing (EBS) with CITI Bank | Automated Statement Processing (EBS) with CITI Bank | Implementing EBS logic with MT940 via FF_5 automates matching and posting of bank transactions, reducing manual intervention and reconciliation time. | 25th Jun 2026
Adhoc – Improvements in NFA process for Ariba | Improvements in NFA process for Ariba | Improves business efficiency and user experience through seamless approval workflows, faster processing, and higher success rates for Ariba sourcing projects, while enhancing NFA generation reliability and performance | 12th Jun 2026
Adhoc – Chevron System Upgrade & Migration to Azure | Chevron System Upgrade & Migration to Azure | Improves system reliability and availability through modern Azure infrastructure, reducing unplanned downtime and business interruptions. | 29th Jun 2026
Adhoc – Ariba RFP detailed report + Report for RFPs related to purchase group ANC | Ariba RFP detailed report + Report for RFPs related to purchase group ANC | Reports will provide real-time visibility into the sourcing lifecycle, eliminating manual tracking and enabling faster, informed decision-making. The ANC purchase group-specific view will further strengthen category-level oversight, improve compliance and ensure audit readiness across all sourcing activities. | 26th Jun 2026
Group Consolidation Reporting - Phase I | Group Consolidation Reporting - Phase I | Delivers a single, consolidated view of group financials, improving transparency, accuracy, and leadership decision‑making. | TBD
PAX Claim - JPM Integration | PAX Claim - JPM Integration | Automating the integration ensures faster processing of Pax Claim payments with reduced manual errors, leading to improved financial accuracy and timely disbursements . Direct integration with banking partners strengthens data traceability and aligns with financial governance standards | Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 10: Corporate Systems – FY26-27/Q2

## Slide 11
July ‘26
Initiatives | Programs/Projects | Value Justification/Realization | Go-Live ETA | EIP Integration Required (Yes/No)
Leave Pro-ration on Exit Phase 1 - Tarun | Leave Pro-ration on Exit Phase 1 | Ensures fair and compliant leave settlement, reducing disputes and manual adjustments at exit.. | 25 Jul 2026 | Yes
Offer Letter Revamp Phase 3 | Offer Letter Revamp Phase 3 | Standardizes and modernizes offer communication to improve candidate experience and reduce errors. | 26 Jul 2026 | No
Goal Setting Revamp | Goal Setting Revamp | Drives clearer performance alignment with business priorities, improving accountability and outcomes. | 26 Jul 2026 | No
Employee Attrition & Overview Dashboard Enhancements - Kunal | Employee Attrition & Overview Dashboard Enhancements | Improves workforce retention decisions by providing real-time insights into attrition trends and key drivers. | 26 Jul 2026 | No
AMS Dashboard Enhancements | AMS Dashboard Enhancements | Enhances operational efficiency and service quality through better visibility into application performance and support metrics. | 26 Jul 2026 | No
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Corporate Systems - FY26-27 Q2 Release Plan (HR Tech)

## Slide 12
Aug ‘26
Initiatives | Programs/Projects | Value Justification/Realization | Go-Live ETA | EIP Integration Required (Yes/No)
Gratuity Nomination on myAI – Pallavi Gupta | Gratuity Nomination on myAI | Improves compliance and employee convenience through easy digital nomination and records | 26 Aug 2026 | No
SkyFam – Consultant Auto-passage creation- Amrit | SkyFam – Consultant Auto-passage creation | Automates consultant onboarding records, ensuring faster processing and improved data accuracy | 26 Aug 2026 | No
HR Cost Dashboard Implementation - Kunal | HR Cost Dashboard Implementation | Enables data-driven cost optimization by providing clear visibility into HR spending, workforce costs, and budget efficiency. | 26 Aug 2026 | No
Recruitment Process Enhancements - Alli | Recruitment Process Enhancements – Auto Salary Calculations, Conditional Offer Letter Config, Creation of New Job Req templates | Enhanced recruitment efficiency and accuracy by automating salary calculations, enabling dynamic offer letter generation, and standardizing job requisition templates—reducing manual effort and accelerating hiring turnaround time. | 26 Aug 2026 | No
Creation of new ID Card in SF - Tarun | Creation of new ID Card in SF | Reduce time to ID card creation via seamless integration between SF & Admin systems | 26 Aug 2026 | No
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Corporate Systems - FY26-27 Q2 Release Plan (HR Tech)

## Slide 13
Sep ‘26
Initiatives | Programs/Projects | Value Justification/Realization | Go-Live ETA | EIP Integration Required (Yes/No)
AMS (Attendance, Shift, Rostering) Phase 2 - Alli | AMS (Attendance, Shift, Rostering) Phase 2 | Enhances end-to-end HR service delivery through deeper automation and scalability, driving significant efficiency gains.. | 30 Sep 2026 | Yes
Engineering Upgrade Automation - Tarun | Engineering Upgrade Automation | Reduces manual dependency and turnaround time by automating upgrade workflows, improving reliability and speed. | 30 Sep 2026 | Yes
Worker & Employee Mapping in SF - Vijender | Worker & Employee Mapping in SF | Enables accurate workforce data alignment for better reporting, compliance, and decision-making. | 30 Sep 2026 | No
Labour Code Changes in Payroll - Suraj | Labour Code Changes in Payroll | Ensures payroll compliance with evolving labour laws while minimizing legal and financial risk. | 30 Sep 2026 | No
Leave Pro-ration on Exit Phase 2- Tarun | Leave Pro-ration on Exit Phase 2 | Ensures fair and compliant leave settlement, reducing disputes and manual adjustments at exit. | 30 Sep 2026 | No
Manager Scorecard & Team Insights Dashboard - Kunal | Manager Scorecard & Team Insights Dashboard | Provides leadership with strategic insights and KPIs to enable data-backed decisions and business alignment. | 30 Sep 2026 | No
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Corporate Systems - FY26-27 Q2 Release Plan (HR Tech)

## Slide 14
July ‘26
Corporate Systems - FY26-27 Q2 Release Plan (Fin Tech)
Initiatives | Programs/Projects | Value Justification/Realization | Go-Live ETA | EIP Integration Required (Yes/No)
Approval workflow for customer creation | Approval workflow for both customer creation & modification | Streamlined customer onboarding with automated workflows ensures accuracy and compliance. Multi-level approvals strengthen governance, reduce risks, and enhance audit readiness. | 25 Jul 2026 | No
ENOC System Upgrade & Migration | ENOC System Upgrade & Migration | Modernizes the ENOC platform to boost availability, resilience, and security — reducing unplanned outages, strengthening compliance, and cutting legacy maintenance costs. | 24 Jul 2026 | Yes
HAM Rollout - Phase I | HAM Rollout – PO, GRN & Material Management | The custom HAM solution replaces ServiceNow, eliminating licensing costs while automating asset lifecycle processes and integrating with SAP and HRMS to ensure audit compliance and improved asset visibility. | 10 Jul 2026 | Yes
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 15
Aug ‘26
Corporate Systems - FY26-27 Q2 Release Plan (Fin Tech)
Initiatives | Programs/Projects | Value Justification/Realization | Go-Live ETA | EIP Integration Required (Yes/No)
Trial Balance Report | Trial Balance Report | Trial Balance Report in SAP ensures financial accuracy by validating debit-credit integrity across all GL accounts - eliminating reconciliation errors and accelerating period-end close. | 25 Aug 2026 | No
ReVamp 15 CA/CB | ReVamp 15 CA/CB | Implementing a streamlined process for Form 15CA and 15CB enhances regulatory compliance, reduces tax-related risks, and ensures accurate reporting of foreign remittances. | 25 Aug 2026 | No
Uniform App enablement for Engineering | Uniform App enablement for Engineering | Empowers employees with a single digital platform for end-to-end uniform ordering, size exchanges and entitlement visibility — eliminating manual processes. Real-time notifications ensure seamless tracking from order placement through to collection. | 25 Aug 2026 | Yes
AdHoc - Approval workflow for customer modification | AdHoc - Approval workflow for customer modification | Streamlined customer onboarding with automated workflows ensures accuracy and compliance. Multi-level approvals strengthen governance, reduce risks, and enhance audit readiness. | 25 Aug 2026 | No
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 16
Sep ‘26
Corporate Systems - FY26-27 Q2 Release Plan (Fin Tech)
Initiatives | Programs/Projects | Value Justification/Realization | Go-Live ETA | EIP Integration Required (Yes/No)
Payment workflow implementation (F110) | Payment workflow implementation (F110) | Automated payment workflows with multi-approval reduce errors, prevent fraud, and ensure compliance. Strengthened control and transparency improve financial governance and audit readiness. | 24 Sep 2026 | No
H2H Maker Checker (Domestic) | H2H Maker Checker (Domestic) | Capability fortifies corporate governance by embedding dual authorization into domestic transactions, ensuring compliance, minimizing operational risk, and safeguarding financial integrity. | 24 Sep 2026 | No
LogServ Implementation | LogServ Implementation | legal compliance requirements mandated by the Government of India, system log data must be retained for a minimum period of eight years. | 25 Sep 2026 | No
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 17: Operations Tech – FY27/Q1

## Slide 18
April ‘26
Operations Tech - FY26-27 Q1 Release Plan
Programs/Projects | Programs/Projects | Value Justification/Realization
TMU Dashboard: Planned Go Live: 24th April 2026 Actual Go Live : 23rd April 2026 |  | Automating TMU tracking with clear visibility and timely triggers can help save around 700 pilot man‑days annually, while enabling earlier corrective actions.
DMS development phase 1 Planned Go Live: 24th April 2026 Actual Go Live : 24th April 2026 |  | DMS will enhance internal audit guidelines and overcome dissemination limit of current manual process.
Duplicate qualifications cleanup of CAE CM Planned Go Live: 20th April 2026 Actual Go Live : 23rd April 2026 |  | Eliminating duplicate qualification records creates a single, reliable source of truth, improving trust in compliance status and preventing incorrect marking or rollback issues.
FIXM Activation in CAE FPM Go Live: 24th April 2026 |  | Mandate required by Eurocontrol.
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 19
May ‘26
Operations Tech - FY26-27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization
Crew data health Check Go Live: 20th May 2026 Actual Go Live: 22nd May 2026 |  | To perform a comprehensive health check on crew data to identify data inconsistencies, missing values, and anomalies Ensure alignment across source systems and reporting views
Slot Adherence Dashboard phase 3 Go Live: 24th May 2026 Actual Go Live : 21st May 2026 |  | Phase 3 of the Slot Adherence Dashboard reduces manual effort through automated alerts and delivers 18–20 hours of monthly productivity gains with deeper rotation-level insights.
CAE MM 10.6.10 Upgrade Go Live: 15th May 2026 Actual Go Live : 20th May 2026 |  | Offers a comprehensive view of the entire fleet, reduces manual data entry. ​ Provides additional functionalities and changes in layout of flight pucks, new message format for sending details to CAE FPM. Enhance performance to support large airlines in AMDM Integration for the Crew Domain.
[Adhoc] Schedule comparison tool (SM-MM) - PHASE 2 Go Live: 20th May 2026 Actual Go Live: 20th May 2026 |  | Adding schedule time and subfleet validation improves schedule accuracy, flags mismatches early, reduces manual effort, and strengthens operational efficiency.
Jeppesen Dead Head Optimisation and Assignment in JCR for AIX​ ​Go Live: 26th May 26​ | Jeppesen Pairing and Rostering for AIX | AIX currently executes approximately 1,250 manual deadhead assignments each month, consuming nearly 60 man‑hours and creating operational inefficiencies. Automating and optimizing these assignments through Jeppesen will significantly reduce manual workload, improve accuracy, and deliver measurable cost savings while enhancing overall crew‑planning productivity.​
Jeppesen FD Trainer Lifestyle Bidding Enhancement​ Go Live: 26th May 26​ | Jeppesen Pairing and Rostering Lifestyle Bidding | This will significantly improve operational reliability, compliance, and planner productivity across Crew Planning and Rostering by delivering:​ Improved Trainer Flight Bid Satisfaction​ Fair and transparent distribution of Trainer Flight Bids​ Greater overall operational stability​
[Adhoc] DGCA CAR Change for Para 13.3 Go Live : 26th May 26 | Jeppesen Roster Optimiser | DGCA regulatory requirement to produce legal rosters in Jeppesen.
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 20
June ‘26
Operations Tech - FY26-27 Q1 Release Plan
Initiatives | Programs/Project | Value Justification/Realization
DMS in-house Development Phase 2 Go Live: 1st June 2026 |  | Deployment of Watermark rollback due to Audit constraints
CMTS Go Live : 5th June 2026 |  | Robust training planning module implementation as part of error free operations
RM Ops Phase 2 Go Live : 15th June 2026 |  | Optimization of schedule recovery during IROPS process to improve operational efficiency, reduce disruption cost and customer satisfaction.
ACE CMTS Integration Go Live: 25th June 2026 |  | Since TnQ is being decommissioned, the system needs to be updated accordingly. This change will reduce the manual effort required to add training for crew members and eliminate redundant tasks. It will also help ensure that AI remains compliant with regulatory bodies in the future, paving the way for CBTA.
BA Randomizer Success Factor Integration Go Live: 18th June 2026 |  | It enables seamless, timely onboarding of new crew for BA testing, eliminating manual intervention and reducing errors
Jeppesen Standby Assignment Problem fleet wise​ - FD Go Live: 26th June 2026​ ​ | Jeppesen Pairing and Rostering | With Standby generation now resolved, the next priority is optimizing Standby assignment. Doing so will directly:​ Improve roster stability​ Increase roster efficiency​ Enhance crew productivity​ Efficient Standby allocation is essential for a more reliable and higher‑performing rostering process.​
Jeppesen Carmsys Upgrade from 31.6 to 32.x​ Jeppesen Crew Bid Portal upgrade (for AIX) Go Live: 26th June 2026​ Actual Go Live: 15th June 2026 | Jeppesen Pairing and Rostering System Upgrade | Upgrading Carmsys to 32.x and JCB portal delivers clear operational and analytical benefits:​ Better system performance, stability, and security compliance​ Improved compatibility with latest Jeppesen features and support standards​ Enhanced workflows for more efficient pairing and rostering​ Rave‑based filtering for deeper, targeted insights​ Improved optimizer performance​
Adhoc - IOCC Report 2, 2A and 3A Go Live: 1st June 2026 |  | Enabled a secure, scalable shift from legacy tooling to a modern data platform, mitigating system expiry risk and strengthening reporting reliability.
Adhoc - Integration between Botminds and MyAI Go Live: 25th June 2026 (Technical) |  | Automated filing of approved documents ensures secure, tamper-proof regulatory records with verifiable acknowledgements, strengthening DGCA compliance and audit readiness, while eliminating redundant L1/L2 approvals reduces manual effort, accelerates processing, and lowers operational overhead
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 21: Operations Tech – FY27/Q2

## Slide 22
July ‘26
Operations Tech - FY26-27 Q2 Release Plan
Delivered
On-track
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Initiatives | Programs/Project | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Jeppesen Standby feature enhancement for Cabin Crew Planning | Jeppesen Pairing and Rostering | Improve roster stability,​ roster efficiency & enhance crew productivity​ Efficient Standby allocation is essential for a more reliable and higher‑performing rostering process.​ | 24 Jul 2026​ | No
Jeppesen – Annual Block Time limit for Cabin Crew Planning | Jeppesen Pairing and Rostering | Improve overall annual crew utilization balance Reduce high-hour concentration leading to HOH (High on Hours) and crew unavailability Enable better flying opportunities for under-utilized crew Ensure no compromise on operational coverage Maintain adherence to all regulatory and compliance requirements | 24 Jul 2026 | No
Jeppesen - APC Enhancements for Cabin Crew Planning | Jeppesen Pairing and Rostering | Ensures Compliance: Prevents APC assignments beyond qualification validity, reducing regulatory risk. Optimises Resources: Better trainer–trainee allocation through refined rules and PCI tagging. Enhances Control: Manual PCI tagging enables flexible, informed planning decisions. Reduces Rework: Built-in constraints minimise manual corrections and improve accuracy Strengthens Training: Ensures effective trainer–trainee pairing for better outcomes. Delivers Robust Outcomes: Improves reliability and optimisation of APC assignments in JCR | 24 Jul 2026 | No
Jeppesen - Teaming feature for CC Planning | Jeppesen Pairing and Rostering | Improve roster stability​ and roster efficiency​ During disruptions, it facilitates more efficient crew management, faster recovery, and reduced operational complexity | 24 Jul 2026 | No
ATC comparison tool automation |  | Improves accuracy of ATC call sign data across systems Reduces manual effort through automated comparison Enables quick identification of mismatches Scalable solution to support increasing flight volumes and data complexity | Planned: 15 Jul'26 Actual: 15 Jul'26 | No
DMS Development Phase 3 | Document Control Hub | Simplified UI reduces: User confusion, Incorrect actions and Training dependency Expected drop in:: Support tickets (SRs), Clarification emails to IT team, Manual follow-ups with departments and Effort in consolidating inputs | 25 Jul 2026 | No
CAE MM Message flavor customization for Star Alliance FLIFO system |  | Resolve current message format issues that are causing message delivery failures. Improve reliability of FLIFO message processing for Star Alliance integrations. Reduce operational errors and manual intervention caused by failed message transmissions. | Planned: 20 Jul'26 Actual: 3 Jul'26 | No
Adhoc : Re-engineering of ZFW integration to FPM via EIP |  | MM API had a limitation of 5 calls per app ID per minute, leading to 429 'Too Many requests' error. MM API was replaced with getFlightSchedule CM API. Cost savings: 95000 USD. | Planned: 6 Jul'26 Actual: 6 Jul'26 | Yes

## Slide 23
July ‘26
Operations Tech - FY26-27 Q2 Release Plan
Delivered
On-track
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Initiatives | Programs/Project | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
​Docunet Daily Non-Compliance Report Phase 3 |  | Automate the daily generation of non-compliance reports identifying previous-day rostered crew who have not completed mandatory read-and-sign documents. Create monthly dump od docunet data for flightOps Audit. | Planned: 25 Jul'26 Actual: 1 Jul'26 | No
Adhoc - Schedule comparison tool (SM-MM) – Enhancement |  | Enables early detection of operational discrepancies such as schedule time and aircraft type mismatches, reducing downstream impacts on fleet planning, crew allocation, and operational execution. The enhancement minimizes manual reconciliation effort, supports faster decision‑making, and helps prevent scheduling errors that could lead to delays, increased operational costs, or compliance risks, thereby strengthening overall schedule governance and operational efficiency. | 23 Jul 2026 | No
Adhoc - Integrated FDTL Crew Exceedance Report |  | This will help submit DGCA exceedance reports and analyze crew FDTL exceedance reasons, reducing manhours for report preparation. | Planned: 15 Jul 2026 Actual: 07 Jul 2026 | No
GE Data flow Enhancement |  | Resolve intermittent issues for ODW data share to GE SFTP, increasing the coverage rate from 90% to 100% | Planned: 10 Jul 2026 2026 Actual: 02 Jul 2026 | No

## Slide 24
Aug ‘26
Operations Tech - FY26-27 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Initiatives | Programs/Project | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Jeppesen – Deadhead Automation for Ground / SIM Training | Jeppesen Pairing and Rostering | Reduces manual planning effort through automation, minimizing repetitive scheduling activities. Improves planning accuracy, reducing the likelihood of errors and rework. Ensures timely crew positioning to support seamless flight operations. Enhances overall operational efficiency and resource utilization. Delivers significant productivity gains through reduced manual effort. Estimated Man-Day Savings AI Cabin Crew (AI CC): 4 Man-Days AI Flight Deck (AI FD): 4 Man-Days AIX Cabin Crew (IX CC): 3 Man-Days AIX Flight Deck (IX FD): 3 Man-Days Total Estimated Savings: 14 Man-Days per planning cycle. | 25 Aug 2026 | No
Jeppesen - OOB Trip Restriction for Crew with Negative QTA_FLTS | Jeppesen Pairing and Rostering | Reduces manual validation effort and planning errors through automated optimization. Delivers optimized roster outputs, resulting in better resource utilization and compliance | 25 Aug 2026 | No
Jeppesen - Restriction on Mixing a subset of A320 Sub-fleets with other in JCP runs- AIX | Jeppesen Pairing and Rostering | Reduces the need for multiple optimizer runs, improving overall planning efficiency. Ensures fleet-wise compliance and adherence to BPTD requirements. | 25 Aug 2026 | No
Jeppesen - Restriction on planning of critical airfields in trainer roster based on crew qualifications. | Jeppesen Pairing and Rostering | Reduces the need for multiple optimization runs, improving overall planning efficiency. Aligns trainer rosters with line training requirements to support operational readiness. Saves planner time and minimizes manual intervention through optimized roster generation. Delivers fair and high-quality rosters for both trainers and line crew. Achieves optimized roster outcomes within a single optimization run, enhancing productivity and consistency. | 25 Aug 2026 | No
CAE MM Message flavor customization for Amadeus | CAE MM | Ensures accurate ETA computation by incorporating CFP time and Taxi‑In time, aligning flight data with passenger‑centric needs. Provides more accurate arrival information to Amadeus, improving passenger handling and planning. Enables better management of passenger connections through reliable Estimated Time of Arrival updates. | 20 Aug 2026 | No

## Slide 25
Sep ‘26
Operations Tech - FY26-27 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Initiatives | Programs/Project | Value Justification/Realization | Planned go-live date | EIP Integration Required (Yes/No)
Jeppesen – SLF training optimization and automation for Flight Deck Crew. Go Live: | Jeppesen Pairing and Rostering | Reduces manual intervention in training allocation, minimizing planning effort and human errors Improves optimization of training schedules alongside roster constraints, ensuring better alignment with operational needs Improves crew availability for operations by optimally sequencing training with flying duties Improved utilization of LTC qualified Trainers to increase the availability of line released crew | 25 Sep 2026​ | No
Jeppesen – ALC Enhancements for Cockpit Crew Planning Go Live: 25th Sep 2026​ | Jeppesen Pairing and Rostering | Ensures Compliance: The change pertains to 3 and 4 crew Operations as per latest regulatory requirement. Optimises Resources: Better trainer–trainee allocation through refined rules. Reduces Rework: ALC to be planned using JCR, currently it has been planned manually due to change in policy. Strengthens Training: Ensures effective trainer–trainee pairing for better outcomes. Delivers Robust Outcomes: Improves reliability and optimisation of APC assignments in JCR | 25 Sep 2026​ | No
Jeppesen – STOL Optimization Automation (ATPL & Accelerated Flying Program) Go Live: 25th Sep 2026​ | Jeppesen Pairing and Rostering | Regulatory Compliance Enablement: Supports DGCA mandate by ensuring First Officers meet ATPL qualification requirements in a structured and trackable manner Accelerated Career Progression: Facilitates timely upgrade of First Officers to Captain by aligning training and qualification pathways with regulatory criteria Improved Workforce Readiness: Ensures a qualified pipeline of eligible FOs, strengthening operational continuity and succession planning Reduced Upgrade Delays: Minimizes bottlenecks in captain upgrades through better visibility and compliance tracking of ATPL requirements | 25 Sep 2026 | No
AIFA DMS Go Live: 25th Sep 2026 | Document Management System | Regulatory compliance (DGCA / ICAO) readiness Improved document control and audit traceability Enhanced operational efficiency through workflow automation Cost optimization through reduction in manual processes and paper usage Centralized document repository ensuring a single source of truth | 25 Sep 2026 | No
GE- ELB Fuel Uplift integration Go Live 25th Sep 2026 | GE Fuel Analytics | Reduction of manual effort for cross checking of invoice to understand fuel uplift Improves optimization of fuel savings initiative | 25 Sep 2026 | No
AVSEC lift and Shift Go Live 25th Sep 2026 | AVSEC STEP portal | Mandatory exam portal for AVSEC exams This is a regulatory requirement | 25 Sep 2026 | No
AI/AIX UAE Crew APIS integration from CAE to UAE NAIC System | Integration | Enabled direct Crew APIS submission from CAE to the UAE NAIC system, ensuring compliance with UAE Government regulations and eliminating dependency on the SITA network. The integration improves data reliability, security, and operational continuity while reducing regulatory and transmission risks. | 15 Sep 2026 | Yes

## Slide 26
Sep ‘26
Operations Tech - FY26-27 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
Initiatives | Programs/Project | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Altea- CM reconciliation Tool |  | Establishes a control layer between MM and Altea CM to detect mismatches and enable proactive monitoring Prevents revenue leakage and reduces passenger disruptions through early discrepancy identification Enhances cross-functional coordination, strengthening schedule integrity and overall operational reliability | 20 Sep 2026 | Yes
BA Randomizer Success Factor Integration |  | It enables seamless, timely onboarding of new crew for BA testing, eliminating manual intervention and reducing errors | 18 Sep 2026 | Yes
Logging and alert mechanism to detect any missing NOTAM to the SFTP directory |  | Ensures that any missing NOTAMs are automatically identified, logged, and trigger an alert, enabling timely manual intervention and ingestion to maintain data completeness and operational reliability. | 25 Sep 2026 | Yes
IX Pseudo code configuration in CAE MM and CM |  | Network Planning: Improved schedule accuracy, better aircraft-route pairing, and reduced payload offloads. IOCC: Fewer disruptions, easier aircraft swaps, better visibility, and stronger control of OTP. Commercial: Stronger schedule integrity, better capacity planning, and reduced downgrade risk. Engineering & Maintenance: Clearer maintenance planning and optimized spares and routing. Crew Management: Cleaner qualification mapping and simpler roster planning. | 10 Sep 2026 | No

## Slide 27: Engineering Tech – FY26-27/Q1

## Slide 28
April ‘26
Engineering Tech - FY26-27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization
PPM WO Compliance Report - Phase 2 Dashboard Planned Go Live: April 15, 2026 Actual Go Live: April 02, 2026 | PPM WO Compliance Project | Ensuring strict compliance with scheduled engineering tasks guarantees airworthiness, regulatory adherence, and operational reliability—minimizing safety risks, avoiding costly penalties, and reducing unscheduled maintenance events
IFE Unserviceability Dashboard Go Live: April 29, 2026 Actual Go Live: April 29, 2026 |  | Proactive monitoring of SLAs/warranties. Careful preparation and planning of spares to minimize the number of impacted seats and resulting penalties.
Pred Mx - A320 Aircraft Parking Brake Planned Go Live: April 13, 2026 Actual Go Live: April 15, 2026 |  | Pred Mx - A320 Aircraft Parking Brake improves OTP by reducing delay minutes and delivers technical dispatch reliability, while improving safety and maintenance planning accuracy.
ATC Call Sign Production Rollout Planned Go Live: April 8, 2026 Actual Go Live: April 2, 2026 |  | This initiative replaces the use of commercial flight IDs with dedicated operational call signs, aligned with regulatory guidance and aviation best practices.
Ultramain ELB Go Live - Phase Wise (B787) Planned Go Live: April 21, 2026 Actual Go Live: April 21, 2026 |  | Phase-wise Ultramain ELB go-live for B787 will enable seamless digital logbook adoption, while reducing paper-based delays and compliance risks.
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 29
May ‘26
Engineering Tech - FY26-27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization
AiMeE Mx History Planned Go Live : May 14, 2026 |  | This feature enhances the Aimee Chatbot by adding insights from real maintenance history to complement AMM/TSM guidance. It analyses past fixes, operating conditions, and outcomes to recommend solutions proven effective in actual scenarios.
AHM Alerts Status & Prioritization Planned Go Live : May 27, 2026 Planned Go Live : May 27, 2026 |  | To find unactioned alerts and prioritize them effectively to help improve OTP.
PPM WO Compliance Report – Phase 3 Dashboard Planned Go Live : May 27, 2026 Actual Go Live : May 25, 2026 | PPM WO Compliance Project | The enhanced WO Compliance dashboard will give a single, real‑time view of maintenance performance, deferments, workforce, and material bottlenecks. To improve compliance & reduce ground time.
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 30
June ‘26
Engineering Tech - FY27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization
ELB Crew data automation from MM Planned Go Live : June 20, 2026 ( Descoped) |  | Automating the future flight data with Crew mapping
MPD & AMP Automation to AMOS Planned Go Live : June 23, 2026 ( Pushed to Q2) |  | Eliminate manual errors and repetitive AMP tasks that are currently fed into AMOS
QBank Implementation PPROD & PROD Planned Go Live : June 24, 2026 |  | QBank implementation will drive faster, standardized, and compliant decision-making by centralizing engineering related mandatory testing,
eSign Integration with AMOS & ELB Go Live : June 25, 2026 (Descoped) |  | Enable digital signatures for maintenance tasks and operational documents within AMOS and the Electronic Logbook. Paperless compliance, faster approvals, clear audit trails, and reduced TAT for release.
Collins VHF Coverage Trials Planned Go Live : June 29, 2026 |  | Conducting a VHF Coverage POC with Collins to evaluate alternative communication network capabilities in regions where current SITA AIRCOM coverage is limited (e.g., China, Hong Kong, Vietnam, Thailand, and other parts of India). The initiative aims to improve communication reliability, reduce connectivity gaps, and enhance operational efficiency and flight safety.
AMOS MRO system configuration Planned Go Live : June 26, 2026 |  | Readiness of AMOS MRO system for the end users
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 31: Engineering Tech – FY26-27/Q2

## Slide 32
Jul ‘26
Engineering Tech - FY27 Q2 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Cabin Serviceability |  | Enhance the Cabin Unserviceable Seat Dashboard and related PMO reporting views to improve visibility of cabin seat defects, trends, filters, and internal validation reporting. This will include Galleys, Lavatories, Crew rest areas etc. Improved decision-making through product-wise split of unserviceable seats and cabin issues across all relevant charts Better leadership visibility by adding trend lines for U/S defects and comparable views on the PMO dashboard | 28 July 2026 | NO
ELB (Electronic Logbook) Integration with Airbus Skywise |  | Enable automated transfer of aircraft technical logbook data to Skywise. Providing real-time fleet insights, predictive maintenance capabilities, improved aircraft reliability and reduced operational costs. | 24 July 2026 | NO
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 33
Aug ‘26
Engineering Tech - FY27 Q2 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Automation of Crew Data Retrieval for eTechlog |  | Reduce manual crew data entry effort. Eliminate data discrepancies between systems (Crew Mgmt vs eTechlog) Ensure regulatory compliance (accurate crew attribution per sector). Improve turnaround time during flight ops | 20 Aug 2026 | YES
Cabin Critical Spares – Inventory |  | Provide real-time, fleet-wide visibility of critical cabin spares Ensures compliance with SAFA audits | 03 Aug 2026 | NO
AHM Prognostic Alert Dashboard |  | Provide real-time, fleet-wide visibility of not actioned prognostic alerts Reduction in delays, disruptions and AOGs | 24 Aug 2026 [BRD to be Completed] | NO
AMP – MPD Data Automation |  | MPD and AMP tasks are entered manually into AMOS. This leads to various issues, including delays and errors due to transcription. The process lacks standardization and documentation. | 23 Aug 2026 | NO
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 34
Sep ‘26
Engineering Tech - FY27 Q2 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Cannibalisation / Robbery app |  | Check from the historical data on the number of cannibalizations that have been extracted from AMOS. | TBD [BRD to be agreed] | YES
AiMeE.Invoke v1.0 - Agentic AI Assisted MCC Process |  | Develop an intelligent system that reduces manual work and improves decision-making for invoking MELs. Improved compliance and reduction in delays and MEL evaluation time. | 15 Sep 2026 | YES
Skywise VM EOL Migration |  | Migrate the Skywise Agent VMs to a supported Red Hat Enterprise Linux version to maintain a secure and stable production environment. | 10 Sep 2026 | NO
Inventory Management System - AMOS Integration - Phase 2 |  | Inventory Management Dashboard to provide centralized visibility of engineering materials and spare parts for improved tracking, monitoring, and inventory control. | 16 Sep 2026 | NO
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 35: CRM/CX – FY26-27/Q1

## Slide 36
April ‘26
CRM/CX - FY27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization
Name change Phase-2 – Direct Non Chargeable flow. - 21 April 2026 Refunds AI - Phase-1 – 22 April -2026 Pax Sales - Sales Org. restructure - Agency Module – 22 April 2026 AI - AIX Parent Case Transfer Process – 10 April 2026 Tagging changes – 29 April 2026 | Name change | This project streamlines a highly manual and error‑prone Name Change process by automating it end‑to‑end within Salesforce using Amadeus services. It cuts turnaround time from days to minutes, improving both operational efficiency and customer satisfaction. The automation ensures accurate updates across PNR and ticket, strengthening compliance and reducing denied boarding risks. It also lowers agent workload and helps prevent revenue leakage through consistent handling of direct non chargeable cases. Automating ATC Refunds for W2C and E2C for Disrupted flights Integrated Sales reporting combining both AI and AIX sales team into a single AI group Sales - Only Agency To design and implement a unified Standard Operating Procedure (SOP) and corresponding system capabilities that enable seamless internal case handling and bi‑directional case transfer between AI and AIX support teams. To revamp the tagging in salesforce based on roles & permission set. This revamp will impact all the flows & processes within salesforce
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 37
May ‘26
CRM/CX- FY27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization
MEDA Phase 2 Waiver Flow Enhancements (Phase1) Cargo Voice CSAT Voice of the Customer |  | Phase 2 of the MEDA project will enhance the Salesforce workflow with web-to-case improvements and integrate with the AMOS engineering system to provide real-time visibility of medical equipment inventory. This will enable end-to-end automation for approvals, resource allocation, and fulfillment. While the compensation ‘expenses’ are now tracked and audited as it is managed through the work orders, the ‘waivers’ offered as part of the IRROP policy or exceptions are not recorded / tracked or approved in an auditable or trackable system. This is also a constant ask from the regulators. Cargo Voice CSAT (Customer Satisfaction) project focuses on capturing and analyzing customer feedback from voice interactions to measure satisfaction levels. This initiative helps identify service gaps, improve call center performance, and enhance overall customer experience through actionable insights Develop one consolidated view of the voice of all the customers we receive with drill downs that can generate actionables for improvements in all the customer touch points.
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 38
June ‘26
CRM/CX- FY27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization
Digitizing Crew Ops related Docs for Catering Management- with integration with Paxia E-statement enhancements (Private fare performance, Total Agency Earning, etc.) - PAX Sales International calling for Cargo CC CJM-2 Pax Sales - Sales Org. restructure - Corporate Module + Approval flows + Other Components |  | Digitizing crew operations documents to simplify catering workflows, reduce manual errors, and accelerate decision-making for on-board services 1. Provides detailed insights into private fare utilization and revenue contribution. 2. Consolidates all earnings (commissions, incentives, overrides) into a single, easy-to-read statement. 3. Improves financial transparency and simplifies reconciliation for agencies. International Calling for Cargo Customer Care enables global connectivity by integrating international calling capabilities into the Cargo CC system. This ensures seamless communication with customers and partners worldwide, improving support efficiency and customer experience dependent tagging for agents for streamline the process. This revamp will impact all the flows & processes within salesforce. Integrated Sales reporting combining both AI and AIX sales team into a single AI group Sales – Corporate
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 39: CRM/CX – FY26-27/Q2

## Slide 40
Jul ‘26
CRM/CX- FY27 Q2 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
VIP Management – A/B/C via Slack Automated Email – Refunds |  | We are implementing a centralized Fulfilment Tracking System for Air India to digitally manage and track end‑to‑end VIP Travel Assistance services. The solution will replace manual processes with real‑time tracking, improve GEC assignment, and centralized visibility via Slack, ensuring consistent service delivery, improved efficiency, full auditability, and enhanced premium guest experience. . By automating 13% of refund cases (~46,800 cases annually), Air India can eliminate approximately 6,240 hours of manual effort every year, resulting in operational savings equivalent to ~3 FTEs and direct annual cost savings of ~₹18 Lakhs. | 28/7/2026 15/07/2026 | No No
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 41
Aug ‘26
CRM/CX- FY27 Q2 Release Plan
Initiatives | Programs/ Projects | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Automated Email – Booking Automated Email – Maharaja Club – Retro Claims Automated Email – Maharaja Club – Profile Updates Automated Email – Compliments Automated Email – Refunds Status Enquiry Automated Email – Disruption refund requests |  | By automating the resolution of 30,000 cases annually, this initiative will significantly reduce operational costs, eliminate agent dependency, and enable 24/7 resolution at scale without headcount growth. This directly translates to faster customer resolution times, improved satisfaction scores, and the reallocation of human talent toward higher-value, revenue-generating activities. Target automation of around 2,365 of 4,730 monthly retro claim cases by integrating Salesforce Agentforce , reducing advisor dependency and enabling faster, consistent, audit-ready resolution for eligible missing points claims. Target automation of around 1,114 of 2,228 monthly profile update cases by systemizing request classification, verification checks, profile update execution, and customer communication, improving TAT while ensuring compliant member data updates. Automating responses for compliments reduces manual agent handling across high-volume, process-driven cases. Improved TAT and zero-error routing enhances customer trust and compliance accuracy. Automating 60% of refund status enquiries (21,600 cases annually) will eliminate approximately 1,800 hours of repetitive manual effort every year, resulting in operational savings of ~₹5.1 Lakhs annually. By automating 18% of refund cases (~64,800 cases annually), Air India can eliminate approximately 8,640 hours of manual effort every year, equivalent to ~4 FTEs, resulting in annual operational savings of ~₹25 Lakhs. | 28 July 28 July 28 July 25/8/26 25/8/26 25/8/26 | Yes Yes Yes No No yes
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 42
Sep ‘26
CRM/CX- FY27 Q2 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Planned Go-live date | EIP Integration Required (Yes/No)
Integrated AOD Portal – Baggage Management ( Emails ) |  | This initiative establishes a centralized, Salesforce-led baggage disruption management platform to handle delayed, lost, and damaged baggage cases end-to-end. It integrates with existing systems (ABC Tool, WorldTracer) to automate case creation, communication, and compensation workflows, improving visibility and resolution for ~7,000 cases monthly. |  | 
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped

## Slide 43: PSS Tech– FY26-27/Q2

## Slide 44
Jul‘26
PSS Tech- FY27 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
LOB​ | Initiatives​ | Value Justification/Realization​ | Planned Go-live Date​ | EIP Integration Required (Yes/No)
RM | Dynamic Pricing | 1A product which dynamically changes ticket prices on AI Direct Channels (Web, Mobile & NDC). Price movements in both directions may be achieved for increase or decrease of ATPCO filed fares. 69 O&D routes made live. | 9-Jul-2026 (Live) | No
AOD | Hub And Spoke - Phase 2 | Hub and spoke phase 2 focuses on below :- Error handling - 6 hourly retrigger and batch run functionality. Introduction of new cities for outbound as per AOD. (2 new Spokes – ATQ and AMD) | 24-Jul-2026 | No
RM | Basic Fare project - Phase 2 | Phase 2 builds on the initial go-live scope from Phase 1. It focuses on releasing this fare on 100% DOM routes on AI. | 24-Jul-2026 | No
LSS | DCS-FM Clean Up On LSS | A governance-driven access cleanup was initiated to remove legacy FM access inherited through SITA migration structures (OGUs, Office IDs, and user-level roles). The initiative restricts FM access to authorized and FM-trained users, eliminates cross-organization access inheritance through dedicated AI and AIX structures, standardizes view-only access, and rationalizes administrative privileges based on business need. This enhances access governance, segregation of duties, security, and audit compliance across the FM ecosystem. | 25-Jul-2026 | No

## Slide 45
Aug‘26
PSS Tech- FY27 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
LOB​ | Initiatives​ | Value Justification/Realization​ | Planned Go-live Date​ | EIP Integration Required (Yes/No)
Group projects | IX ET issuance on Sabre GDS | Assisting IX teams for setting up GDS system rules/behaviors. | 7-Aug-2026 | No
E-Comm​ | Buy Now Pay Later – Phase 2 | Project to provide option to customers to block flights/issue tickets before few days of travel only by tweaking the existing Time to Think logic at the back end. Initial solutioning ​provided in June'26. Phase 2 contains knitting the solution together with various stakeholders for testing/implementation. Scoping finalized. | 24-Aug-2026 | No
Customer Experience | Tax filing for Upgrade service | Review, fill, validate and file tax obligations for Upgrade services performed at countries like UK, France, Hongkong, Mauritius etc. for airport upgrade services To ensure revenue accuracy and eliminate tax leakage (occurring currently). Appx. tax leakage of INR 4-5 Crore per year expected to be curtailed/saved via this filing for UK market only. | 24-Aug-2026 | No
RM | Option town integration for Flight Pass | Flight pass solution where the flight pass can be purchased and later redeemed during booking. Under review/testing/CAB approval also. | 24-Aug-2026 | No
Finance/ Distribution | Agent Portal Card Surcharge Collection | This solution is to handle Surcharge for Card payment made in NDC Agent Portal. In addition to Card Surcharge, it provides solution to handle GST Invoice collected for Card Surcharges. Approx. monthly savings of 5L. | 25-Aug-2026 | No

## Slide 46
Sep‘26
PSS Tech- FY27 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Descoped
LOB​ | Initiatives​ | Value Justification/Realization​ | Planned Go-live Date​ | EIP Integration Required (Yes/No)
Alliances | Seat Ancillary project with United Airline(UA) | To set up core system to enable UA to sell AI chargeable seats during Interline journey. ASR OPE under testing. | 24-Sep-2026 | No
Ecommerce | Delayed Boarding Pass | Project to allow customers to opt for check-in later if not willing to purchase chargeable seats. System set up underway. Initial testing to commence. | 24-Sep-2026 | No
GRC | Rajya Sabha Travel Certification | Implementation of API-based integration with airline systems to enable real-time verification of Rajya Sabha MPs’ and authorized members’ travel details, ensuring faster, accurate, and automated claim validation and settlement. DPA and Agreement is currently under review with Air India Legal and DPA teams. | 24-Sep-2026 | No
Finance/ Distribution | Introduction of CP tax code | Enabling/setting up core system to collect penalty fee through introduction of new tax code rather than issuance of EMD, which will save major costs incurred by AI (on GDS channels). | 25-Sep-2026 | No
 | Group Booking CC Surcharge EMDs Issuance | This project is for enabling Credit Card Surcharge collection through Standalone EMD through Group Booking Tool. This will also handle GST Invoicing on CC Surcharge collection through GST module. It will earn additional revenue of 6 to 7 Lakhs per month as CC Surcharge. | 25-Sep-2026 | No
AOD | Hub And Spoke - Phase 3 | Introduction of Inbound flights (INTL to INDIA) only sell flights within 4 hours of connection. | 25-Sep-2026 | No

## Slide 47: Enterprise Platforms – FY26-27/Q1

## Slide 48
April ‘26
Enterprise Intelligent -FY26-27 Q1 Release Plan
LOB | Initiatives | Value Justification/Realization | Go-live Date
FIN Tech | PAX Claim Phase II – Integration with PayU | Automating the integration ensures faster processing of Pax Claim payments with reduced manual errors, leading to improved financial accuracy and timely disbursements . Direct integration with banking partners strengthens data traceability and aligns with financial governance standards | 27 Apr 31 Jul
 | PAX Claim Phase II – Integration with HSBC | Automating the integration ensures faster processing of Pax Claim payments with reduced manual errors, leading to improved financial accuracy and timely disbursements . Direct integration with banking partners strengthens data traceability and aligns with financial governance standards | 27 Apr 22 May
B2E | Boarding Document Display | Integrates catering data from PAXIA to show class‑wise meal types and crew meals in real time | 29 April
 | Crew Error Report (Power Apps) | Automated generation and reporting of crew‑related operational errors | 28 May 25 June
OPS | BotMinds To CAE CM Integration for flightOps | Automating data extraction and updates | 24 Apr
CRM Tech | Refunds AI - Phase-1 | Automating ATC Refunds for W2C and E2C for Disrupted flights | 22 Apr TBF
 | Name Change Amadeus Integration - non Chargable-Direct | This project streamlines a highly manual and error‑prone Name Change process by automating it end‑to‑end within Salesforce using Amadeus services. It cuts turnaround time from days to minutes, improving both operational efficiency and customer satisfaction. The automation ensures accurate updates across PNR and ticket, strengthening compliance and reducing denied boarding risks. | 21 Apr
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release

## Slide 49
April ‘26
Enterprise Intelligent -FY26-27 Q1 Release Plan
ADHOC Projects
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Go-live Date
HR Tech | Life Ka Plan Integration with SuccessFactors | The Life Ka Plan–SuccessFactors integration eliminates manual employee data handling, significantly reducing errors, turnaround time, and operational overhead. By ensuring real‑time, accurate employee master and compensation data, it strengthens benefit eligibility accuracy, compliance, and audit readiness. The solution improves employee experience through timely enrolment and benefit continuity, especially during transfers and role changes. Overall, it enables scalable, governance‑driven HR operations with minimal manual intervention and lower risk to business continuity. | Q2
B2E | Onboarding CAE CM Crew Pairing API to EIP for AI Flight Pro Integration | Delivers a single, real‑time roster view that improves schedule visibility, accuracy, and crew planning while reducing manual effort. Seamless integrations and time‑zone intelligence enhance operational efficiency, compliance, and user confidence at scale. | 11 June

## Slide 50
Enterprise Intelligent -FY26-27 Q1 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Go-live Date
Fin Tech | PAX Claim - JPM Integration | Automating the integration ensures faster processing of Pax Claim payments with reduced manual errors, leading to improved financial accuracy and timely disbursements . Direct integration with banking partners strengthens data traceability and aligns with financial governance standards | 27 May
HR Tech | Crew Upgrade Automation | End‑to‑End Crew Upgrade Automation (basis tenure, certification, etc.). Automates upgrade decisions through rule‑based logic, improving fairness, process speed, and operational efficiency. | 27 May
B2E | Baggage integration with Salesforce | Integrated baggage tracking and case data with Salesforce CRM to enable seamless compensation workflows and centralized case management for customer service teams | 28 May
 | Pilot Check-in (AIFP) | CAE CM Check-in: Capability for Pilots to check into their flight allowing a system check of their licenses and qualifications and informs them of any potential issues Docunet Alerts: Integration with Docunet via APIs resulting in a hard alert preventing check-in. Alerts limited to documents updated and review and sign of mandatory documents | 28 May 26 Jun
May ‘26

## Slide 51
Enterprise Integration -FY26-27 Q1 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Go-live Date
IVCS | IVCS / CVCS – CAE Violation Alerts Integration | As part of the Crew Validation Control System, we require CAE alerts generated in CAE for any violations. These alerts are needed to validate whether they are accurately captured in our systems and to identify any alerts generated by us that are not present in CAE. Justification : The integration of CAE‑generated violation alerts into the Crew Validation Control System provides significant value by strengthening validation accuracy, compliance assurance, and operational reliability. NO IRD, not onboarded created on Jira) 9o trust evidence based operational excellence) | 
FIN Tech | Automated Statement Processing (EBS) with CITI Bank | Implementing EBS logic with MT940 via FF_5 automates matching and posting of bank transactions, reducing manual intervention and reconciliation time. (Not part of Fin roadmap) | 30th June
HR Tech | Leave Pro‑ration on Notice Period Automation | Eliminates manual leave calculations and ensures accurate payouts during notice period, reducing payroll errors. | 26th June
 | Enable LWD FNF Input on People Strong | Automates full‑and‑final settlement inputs on LWD, reducing manual dependency and speeding up settlement timelines. | 26th June
 | AMS (Attendance Management System) Phase 1 – Linkage to Payroll | Ensures accurate payouts by linking attendance directly to payroll, reducing manual reconciliations and errors. | Moved to Q2
June ‘26

## Slide 52
Enterprise Integration -FY26-27 Q1 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Go-live Date
Ops | CMTS to ACE Integration | SinceTnQ is being decommissioned, the system needs to be updated accordingly. This change will reduce the manual effort required to add training for crew members and eliminate redundant tasks. It will also help ensure that AI remains compliant with regulatory bodies in the future, paving the way for CBTA. | 25 Jun TBD
 | BA Randomizer Success Factor Integration | Security and Performance enhancement | Moved to Q2
 | MEL from MM to FPM | Descoped | 25 June
CRM | Digitizing Crew Ops related Docs for Catering Management- with integration with Paxia | Digitizing crew operations documents to simplify catering workflows, reduce manual errors, and accelerate decision-making for on-board services | 05 Jun
June ‘26

## Slide 53
June ‘26
Enterprise Intelligent -FY26-27 Q1 Release Plan
ADHOC Projects
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Go-live Date
HR Tech | Life Ka Plan Integration with SuccessFactors | The Life Ka Plan–SuccessFactors integration eliminates manual employee data handling, significantly reducing errors, turnaround time, and operational overhead. By ensuring real‑time, accurate employee master and compensation data, it strengthens benefit eligibility accuracy, compliance, and audit readiness. The solution improves employee experience through timely enrolment and benefit continuity, especially during transfers and role changes. Overall, it enables scalable, governance‑driven HR operations with minimal manual intervention and lower risk to business continuity. | 2 July
B2E | Onboarding CAE CM Crew Pairing API to EIP for AI Flight Pro Integration | Delivers a single, real‑time roster view that improves schedule visibility, accuracy, and crew planning while reducing manual effort. Seamless integrations and time‑zone intelligence enhance operational efficiency, compliance, and user confidence at scale. | 11 June

## Slide 54
April ‘26
Enterprise Integration Automation - FY27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
HAM - Phase 1 | Hardware asset management system | The custom HAM solution replaces ServiceNow, eliminating licensing costs while automating asset lifecycle processes and integrating with SAP and HRMS to ensure audit compliance and improved asset visibility. | 25 June 2026
May ‘26
June ‘26
No Plan Initiatives
No Plan Initiatives

## Slide 55
April ‘26
ServiceNow - FY26-27 Q1 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
RPA User Auto Creation Requirement For Amadeus FM | Access Management | Automation of access management of Amadeus FM application through RPA | 23-Apr-26
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
ITOM Discovery Replacement | ServiceNow Licence Optimization | Release 1 : Network Resources ServiceNow ITOM Discovery Replacememt with API Integration as part of ITOM Licenses Cost Optimization. | 14-May-26 Business Go-Live 11-May-26
ITOM Discovery Replacement | ServiceNow Licence Optimization | Release 2 : Cloud Resources (Cloud : Azure Integration through API) ServiceNow ITOM Discovery Replacememt with API Integration as part of ITOM Licenses Cost Optimization.(Azure, AWS, GCP) | 28-May-26 Business Go-Live 21-May-26
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
IOCC System Request Categorization (Email to Case) - Adhoc | IOCC Compliance | To raise operational issues or grievances by emailing the Systems team, which in turn automatically generates an incident/ticket for easy tracking and resolution. | Business Go-Live 11-Jun-26
SRE Bot Incidents Integration - Adhoc | Incident Reporting Integration – Agentic Initiative | SRE Bot to create Incidents in ServiceNow for More than 25 Enterprise Applications. UAT Sign-Off Completed. | Business Go-Live 26-Jun-26
May ‘26
June ‘26

## Slide 56: Enterprise Platforms – FY26-27/Q2

## Slide 57
Enterprise Integration -FY26-27 Q2 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Planned Go-live date
HR Tech | Leave Pro‑ration on Notice Period Automation | Leave proration for notice period employees ensures accurate, tenure-based leave balance recalculation through a dedicated SuccessFactors time profile. It reduces manual intervention, prevents leave/payroll discrepancies, and strengthens compliance during employee exit processing. | 27 July
 | Crew Upgrade phase 2 for Pilots | The automated compensation letter integration eliminates manual HR effort by automatically generating and dispatching approved compensation letters, ensuring timely, accurate, and consistent employee communication. It enhances auditability, compliance, and process governance while improving employee experience and enabling scalable, reliable operations. | 13 July
Engg Tech | Crew Data Retrieval( ELB <> CAE) | Automates crew data synchronization between ELB and CAE systems, eliminating manual dependency and reducing data latency/errors. | 12 July
AI Smart | PTS Improvements - Analysis and onboarding for BaggageHub APIs on EIP (AI Smart) | The BaggageHub integration with AISmart will provide real-time visibility of baggage summaries, special baggage categories, and ULD details through a centralized platform. This will improve operational efficiency, enhance decision-making, and streamline baggage handling processes for airport and ground operations teams. | 29 July
Jul ‘26

## Slide 58
Enterprise Integration -FY26-27 Q2 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Planned Go-live date
HR Tech | [Adhoc] Event-Driven Transfer Letter Generation, Approval & Distribution – SuccessFactors Employee Central | The event-driven transfer letter automation removes manual steps for generating, reviewing, and distributing employee transfer letters by triggering letter creation from SuccessFactors employee events. It improves employee experience with timely, consistent communication, | 28 Aug
 | Life Ka Plan Integration with SuccessFactors- Phase 2 | The Life Ka Plan–SuccessFactors integration eliminates manual employee data handling, significantly reducing errors, turnaround time, and operational overhead. By ensuring real‑time, accurate employee master and compensation data, it strengthens benefit eligibility accuracy, compliance, and audit readiness. | 28 Aug
Engg Tech | CAE-MM to AMOS – Delay and Cancellation Flight - 2 | The CAE-MM to AMOS Delay & Cancellation integration enables real-time visibility of flight disruptions, ensuring maintenance planning is always based on the latest operational status. By eliminating manual updates and data gaps, it improves aircraft availability planning, enhances decision-making, and increases operational efficiency while reducing the risk of maintenance scheduling errors. | 28 Aug
 | AMOS to CAE MM integration for Maintenance messages - Maintenance PUKs Closed & Cancellation (AMOS → CAE) | The integration of AMOS with CAE’s Movement Manager enables real‑time flow of maintenance (MX) messages, eliminating manual data transfers and reducing operational delays. By ensuring that critical aircraft maintenance information is instantly available in MM, the solution strengthens flight planning accuracy and enhances IOCC decision‑making. | 28 Aug
B2E | [Adhoc] myAI Profile Picture EIP Onboarding (SF <--> myAI) | Enables direct profile picture updates from myAI into SuccessFactors, ensuring a single, consistent employee identity across systems. | 31 Aug
 | [Adhoc] Service Now myAI security approval | Integrating myAI with ServiceNow will streamline the Security Exception approval process by enabling approvers to review, approve, or reject requests directly within myAI. | 28 Aug
Aug ‘26

## Slide 59
Enterprise Integration -FY26-27 Q2 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Planned Go-live date
CRM Tech | Automated Email :: Resend eTicket W2C | The automation covers detection of e-ticket request intent, extraction and validation of PNR and passenger name, email verification against the PNR, retrieval of the e-ticket document from Amadeus, and dispatch of the document to the customer via email. Failure scenarios are routed to an agent queue for manual resolution. | 28 Aug
 | IRROPS- Disruption Refund Requests Automation | The Disruption Refund Automation solution will significantly reduce manual effort by automating refund eligibility validation, calculation, and processing for disruption-related cases. By enabling straight-through processing for 60-70% of refund requests, the solution will reduce average handling time from 8 minutes to under 1 minute, resulting in improved operational efficiency and lower support costs. | 24 Aug
Security | Cyber Defense – DLP Monitoring for Employees on Notice Period | To improve visibility into potential data exfiltration risks during the notice period and enable the Cyber Defense team to proactively monitor and investigate suspicious data transfer activities. | 31 Aug
Aug ‘26

## Slide 60
Enterprise Integration -FY26-27 Q2 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
LOB | Initiatives | Value Justification/Realization | Planned Go-live date
HR Tech | AMS (Attendance Management System) Phase 2 | Phase II of AMS enables a governed, system-of-record attendance platform that improves data accuracy, compliance, and employee trust across HR, payroll, and analytics. It reduces manual payroll reconciliation effort and operational risk while enabling scalable, audit-ready integrations and leadership-ready insights. | 25 Sep
 | Leave Pro‑ration on Notice Period Automation (HRBP intiated seperation) | To implement leave proration for notice period employees, administrators must create a new time profile in SuccessFactors specifically designed for employees serving notice periods. This profile will automatically re calculate and update leave balances based on the employee's tenure within the current fiscal year, ensuring accurate leave availability when an employee enters their notice period. | 25 Sep
OPS Tech | Automated Schedule Reconciliation between CAE MM and Amadeus Altéa CM | This integration establishes a single source of truth for flight schedule data by automating reconciliation between CAE Movement Manager (MM) and Amadeus Altéa CM, eliminating manual comparisons and reducing operational risk. | 20 Sep
 | BA Randomizer – SuccessFactors Integration | Currently, significant effort is spent validating and updating employee records before they can be used for operational randomisation activities. By automating employee data synchronization from SuccessFactors, the solution will remove manual maintenance effort, reduce data discrepancies, and improve the accuracy of randomisation results. | 18 Sep
 | AI/AIX UAE Crew APIS integration from CAE to UAE NAIC System | The UAE Crew APIS integration modernizes regulatory data exchange by replacing legacy SFTP-based file transfers with a secure, scalable Azure Blob and MQ-based architecture. It improves the reliability and timeliness of passenger and crew data submissions to UAE border authorities, reducing operational disruptions and compliance risks. | 15 Sep
IVCS | AMOS–MM MEL Compliance & Control Monitoring System | This initiative establishes a single, trusted view of MEL workorder compliance by integrating AMOS and MM, ensuring critical maintenance records remain synchronized across operational systems. | 01 Sep
Sep ‘26

## Slide 61
Enterprise Automation-FY26-27 Q2 Release Plan
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Initiatives | Value Justification/Realization | Planned Go-live Date
Zero Trust Evidence Based Operations- Aircraft (DMS Extraction) | Every action and data point supported by underlying evidence in the form of authenticated documents or data from systems with authenticated data | 25 Sep
[Ad Hoc] Aircraft Restriction Process (Excel Change Tracker) | Aircraft restriction process (Excel change tracker). Adding a maker‑checker step before updating the tracker. | 28 Aug
HAM Phase 2 | Requirement yet not finalized. | 
EWS Phase 2 | Requirement yet not finalized. | 
Sep ‘26

## Slide 62
Jul ‘26
ServiceNow - FY26-27 Q2 Release Plan
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
Security Exception-Enabling on SNOW and myAI : Phase 1 &2 | Digital and Technoloy Automation | Phase 1 - CXO Approvals for Security Exceptions on ServiceNow. Phase 2 – Changes in Security Approvals and other form level changes. & CXO Approvals on myAI (Manager/Security/CXO-1/CXO) | 30-JUL-2026
Descoped
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
Hard Alert De-assignment Enhancement | IOCC Automation | Auto De-assignment of Hard Alerts after 3hrs for Flying Duty and after 6 hrs for Training Duty if the IOCC controller doesnot take action through human in the loop action. 16 hrs rolling window for Hard Alerts , Notification changes , Category addition etc. | 23-AUG-2026
SkyFam RPA Automation | RPA Automation | New Admin Screen and Non-Admin Screen changes in RPA Automation flow. | TBD (To be given by HR Tech)
Initiatives | Programs/Projects | Value Justification/Realization | Go-live Date
Security Exception-Enabling on SNOW and myAI : Phase 3 |  | Phase 3 – Security Exceptions SR from myAI + DG | 29-SEP-2026
Aug ‘26
Sep ‘26

## Slide 63: B2E Apps & Channel – FY26-27/Q1

## Slide 64
myAI - FY26-27 Q1 Release Plan
Projects | Value Justification/Realization | Web | Mobile Native | Go Live Date
Digitizing Pilot and Crew Records | Pilot and Crew Document Management flows for pilots to manage their digital license/qualifications with OCR-based data integration for data extraction Admin approval flows based on document type for compliance and accuracy Rule-based Business Engine for updates required in related license/qualification records to ensure regulatory compliance Notifications: Notifications to pilots for expiry, approval flow notifications etc. Admin team notifications for approval management System Integrations: with BotMinds (record management) and Crew Management systems (rostering updates) At launch capability will serve the following with separate flows for each : Licenses: 6 Types including Pilot and Crew License, Instrument Rating and Medical Record Document: 9 Types including Passport, Visa, AEP and Company ID Qualifications: ELP and 2 Medical Related | Y | Y | 29th April
Mobile Device Access for ABC Tool | Allow access to ABC tool from mobile devices to enable on the go management of left behind baggage cases by the security team | Y | N | 29th April
QR based immigration for Crew | Introducing QR code for faster immigration for crew from FTI – TTP Gates , eliminating need for manual processes and long wait time in queues | Y | Y | 29th April
Beneficiary and Nomination Enhancements and bug fixes | Handling for OCR failure scenarios with fallback/manual validation flow Reuse existing documents to eliminate redundant uploads: Employee self docs matching criteria to be selected and reuse of beneficiary docs added Minor changes Building capability to select next FY for beneficiary nomination for Skyfam thus enabling proactive nominations for upcoming FY Beneficiary – auto selection of gender as per beneficiary type, status change as per HR policy Pre-fill spouse as type when beneficiary is spouse Sorting of title list in beneficiary addition Enabling consistent logging for 15 backend services | Y | Y | 29th April
Jan
Jan
Apr ‘26

## Slide 65
myAI - FY26-27 Q1 Release Plan
Initiatives | Value Justification/Realization | Web | Mobile Native | Go Live Date | JIRA
AMS phase 2: Geo fenced attendance | Geo-fencing capabilities in myAI app to provide real-time location based clock-in and clock-out Visibility of attendance status including clock-in/out, absenteeism, late arrivals, early exits, shift swaps, overtime requests, and duty irregularities to managers and rostering team POC/ API review with AMS tool to be conducted | Y | Y | 28th May | MC-112
Leave auto approval | Automatically approving leave request that stays in a “Pending Manager Approval” state for 5 calendar days from the original submission date thus cutting uncertainty and backlog | Y | Y | 28th May | MC-811
Hardware Asset Management | Platform to manage hardware assets provided to employees with the ability to record approvals for audit purposes. | Y | Y | 28th May | MC-499
Auto approval of regularizations | Auto approval of regularization requests ensuring timely attendance/payroll closure Regularization reason updates basis HR requirements | Y | Y | 28th May | MC-148
Uniform issuance for Pilots and other non-crew dept | Digital end-to-end uniform ordering and exchange for all eligible employee departments Entitlement, product and description visibility Self-service ordering with size exchange requests Notification on order collection and completion milestones | Y | Y | 28th May | 
Tech/UI UX debt | Attendance – auto-scroll to date for the day and merging of legends Notification centre- read all message functionality Leave visibility outside FY for non-balance leave types Trips-formatting changes App – introduce quick links in bottom nav Enabling consistent logging for 15 backend services | Y | Y | 28th May | 
Jan
Jan
May ‘26

## Slide 66
myAI - FY26-27 Q1 Release Plan
Initiatives | Value Justification/Realization | Web | Mobile Native | Go Live Date
AMS phase 2: Geo fencing integration | System integration with AMS tool to submit and provide attendance information based on geo-fencing capabilities | Y | Y | 29th June
AMS phase 2: Shift and Rostering | Shift Employees to be provided clear visibility of assigned shifts and planned roster information Employee managers obtain view of team roster and attendance in real time System integration with AMS tool for pulling relevant information in real time Currently available for shift teams from the following depts: AOD, Security, CS, IOCC | Y | Y | 29th June
AMS phase 2: Regularization/ Swap/OT Handling | Employees to submit regularization, OT and shift swap requests based on system defined policy rules reducing manual workflows System integration with AMS tool to provide attendance information | Y | Y | 29th June
AMS phase 2: Approver flow | Unified approval workflow for OT, shift swap and regularization requests for shift employees on myAI, thus eliminating manual process Personalised notifications-location based alerts to employees when a clock-in or clock-out event is missing for the day/shift reducing attendance gaps proactively Notifications to managers for pending leave and regularization approvals | Y | Y | 29th June
AMS phase 2: Payroll sync | System integration with payroll for final attendance status sync with payroll processing, with visible status indicators for employees | Y | Y | 29th June
Tech debt | Enabling consistent logging for 20 backend services | N | N | 29th June
Jan
Jan
Jun ‘26

## Slide 67
CE Plus - FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date | JIRA
Boarding Document display | Integrates catering data from PAXIA to show class‑wise meal types and crew meals in real time | 29th April | TBD (Budget Approvals)
Crew Competency Information | Presents the CE with CAR‑mandated competencies for all crew assigned on the flight in a single location for pre‑flight checks | 29th April | CP-2086
Service Sequence Guide | Provides a visual minute‑by‑minute, flight‑specific service guide that standardizes workflows based on flight type (ULH, LH etc.) and departure time | 29th April | TBD (Budget Approvals)
Jan
Jan
Apr ‘26

## Slide 68
CE Plus - FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date
Meal Order Digitization | Enables Cabin Executives to capture First/Business Class meal selections via real time updated menu digitally on the platform | TBD (Budget Approvals)
Loyalty Platform Enrolment | Allows inflight enrollment of passengers into the Maharaja Club through crew iPads | TBD (Budget Approvals)
My Flight View | Offers a persistent “Guest Summary” widget inside CCVR to quickly access key guest details, reducing navigation time and enabling faster interactions | TBD (Budget Approvals)
Jan
Jan
May ‘26

## Slide 69
CE Plus - FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date
Guest Preferences | Displays historical preferences and favorites of premium class guests and favorites based on past selection on app | TBD (Budget Approvals)
Galley Loading Plan | Provides a flight‑specific galley setup plan including cabin zone served, beverage cart configuration, equipment and service items and dry store items | TBD (Budget Approvals)
Multiple SCCs Onboard Capabilities | Enables iPad‑to‑iPad connectivity between forward and aft SCCs for coordinated reporting, issue resolution, and service recovery | TBD (Budget Approvals)
Jan
Jan
Jun ‘26

## Slide 70
AI Smart - FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date | JIRA
EDTO information for Dispatch | Dispatch team requires the availability of EDTO information including time information and alternate airports for flight planning | 29th April 14-May | E-5986
NOTAM Flight Ops workflow | Flight Ops team manually reviews NOTAMs and categorizes and actions the same recording it over excel sheets. Selection of NOTAMs, automation of categorization and generation of GPS waypoint links for obstacles to be performed via AI Smart | 28th May Moved To May Release | E-6092
AKS Migration | Migration of Control board module to AKS to improve system performance as current platform performance issues have been highlighted by user group | 28th May Moved To May Release | S-972
iCargo Integration | Integration of Cargo load value from i-Cargo application in the fuel compliance module for international stations. | 29th April | S-3647 Descoped due to Prod - API availability
PTS Task Automation – Mobile FM Device (Ad hoc) | Automation of PTS worklist by integrating data from Mobile FM devices via API. 6 out of 30 manual tasks to be automated (Bag/Cargo offload start; Bag/Cargo offload end; Bag/Cargo loading start; Bag/Cargo loading end; GNS bag offload start; GNS bag offload end) | 29th April | E-5456 Descoped due to API availability
Adhoc – PTS Optimization | Performance Optimization on PTS Detail Module for better user experience | 14-May | S-6040
Adhoc – Dispatch Optimization | Performance Optimization on Dispatch Module for better user experience | 14-May | S-6028
Jan
Apr ‘26

## Slide 71
AI Smart - FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date | JIRA
PTS Task Enhancement – PRS Devices | Automation of PTS worklist by integrating data from PRS devices. 12 manual tasks to be automated. (Security Check Start; Security Check End; Crew reported at aircraft; Catering Start; Catering End; Pilots Onboard, etc.) | Descoped due to API unavailability | E-6093
Auto allocation of Dispatchers | Allocation of dispatchers across the flights based on rules defined | Descoped from Business | E-6096
Tail approval - Country and PBCS | Prevent dispatch of unauthorized aircraft by validating tail-wise country approvals and ocean (PBCS) clearances | BRD under review | Link
Notifications | Multiple use cases across modules (e.g. MEL additions, early arrivals, new NOTAM assignment, PTS delays) with the requirements for notifications with acknowledgement capabilities | BRD under development | Link
AKS Migration | Migration of Dispatch module to AKS to improve system performance as current platform performance issues have been highlighted by user group | 29th May | S-1374
AKS Migration | Migration of Control board module to AKS to improve system performance as current platform performance issues have been highlighted by user group | 29th May Moved from Apr Release | S-972
NOTAM Flight Ops workflow | Flight Ops team manually reviews NOTAMs and categorizes and actions the same recording it over excel sheets. Selection of NOTAMs, automation of categorization and generation of GPS waypoint links for obstacles to be performed via AI Smart | 12th Jun Moved from Apr Release | E-6092
Adhoc - NOTAM Manager : Logic change | See all NOTAMs which have any of AIsmart’s predefined stations present in Q-line or A-line. | 29th May | S-6475
Adhoc - SCR/SMA Changes | Logic change for Paris Airport | 29th May | S-6330
AKS Migration | Migration of Engr Control board module to AKS to improve system performance | 29th May | S-6630
Jan
Jan
May ‘26

## Slide 72
AI Smart - FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date | JIRA
Stop Boarding toggle | Functionality to stop the boarding of passengers in case of any unforeseen event utilizing a set of events | 29th June | Link
TRC Support Information | Additional information required in PTS Module including Load and Trim sheet related tasks, gate, live baggage count etc. | 29th June | Link
Live Operations Dashboard | Operations to define a live dashboard with key information for day to day activities | 29th June | Link
Chat & Task Assignment Capabilities | Role based chat and task assignment capabilities for audit and assignment of critical tasks currently being performed ad-hoc and on non Air India systems | 29th June | Link
Jan
Jan
Jun ‘26

## Slide 73
AI Flight Pro- FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date | JIRA
Roster View | Availability of 7-day roster view and 30 day download and email capability on AIFP with redesign for roster card as entry point for Pilot activities | 29th April | Link
Passenger Details | Ability to show PAX Booked vs Pax Boarded on AIFP for Pilots | 29th April | Link
Admin Approval Flow - Enhancement | Enhanced error reporting flow for both crew and operational data with actionable workflows to Admin and DOPs team | 29th April | Link
Crew Data & Compliance Alignment | Automated Seat Position Mapping for Pilots improving seat‑position accuracy by fetching real‑time CM data | 29th April | Link
 | Regulatory Role Mapping for PIC by Virtue & P1/US - Ensures accurate identification of PIC By Virtue and P1/US roles using defined logic based on CM data. |  | Link
 | Shift‑Wise PIC & Co‑Pilot Role Accuracy - Provides accurate PIC and Co‑Pilot role display per shift |  | 
Tech Debt | DB Encryption - This activity will be done to encrypt all the PII Data from the AIFP DB as per Security Requirements | 29th April | Link
Jan
Jan
Apr ‘26

## Slide 74
AI Flight Pro- FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date | JIRA
Pilot Check in | CAE CM Check-in: Capability for Pilots to check into their flight allowing a system check of their licenses and qualifications and informs them of any potential issues | 28th May | 
 | Docunet Alerts: Integration with Docunet via APIs resulting in a hard alert preventing check-in. Alerts limited to documents updated and review and sign of mandatory documents |  | 
 | EFB Alerts: Alert based on iPad battery check > 70% |  | 
Base Training | Ability to submit PSR-based training flight reports via AIFP with submission flow and integration with eGCA | 28th May | 
Approval Flow for Pilots | Allows the PSR to be submitted by one pilot and reviewed by all other pilots on the flight Providing Push and email notifications to Pilots for submission, resubmission flow and missing PSR | 28th May | 
MEL Information | Real-time information on MELs (A-D, NEF, DD) associated with aircraft being operated by the pilots | 28th May | 
Tech Debt | AIFP Upgrade with CM - Introducing the leg‑reference feature as part of the AIFP upgrade in CM Version 19 | 28th May | 
Jan
Jan
May ‘26

## Slide 75
AI Flight Pro- FY27 Q1 Release Plan
Projects | Value Justification/Realization | Go Live Date | JIRA
eGCA Submission | Support submission of Pilot Data to eGCA via CAE CM Obtain an acknowledgement from CM system that PSR is successfully submitted to eGCA post any error related retries or issues with submission Notification to Admin on success/failure of submission | 29th June | 
BA Management | Notifications: Notifications to pilots based on roster to complete BA testing per policy for domestic and international flights | 29th June | 
 | Acknowledgement: Obtain explicit approval of completion of breath analyzer tests | 29th June | 
All Flights information | Provide all flight and crew member information to pilots to support crew swap decisions when required | 29th June | 
Final Fuel Reporting | Allow pilots to report Final fuel with ability to provide fuel information including cargo load, special load, arrival fuel, EZFW etc. | 29th June | 
Jan
Jan
Jun ‘26

## Slide 76: B2E Apps & Channel – FY26-27/Q2

## Slide 77
AI Smart - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go Live Date | JIRA | EIP Integration Required (Yes/No)
Trainee Crew listing | Identification of Trainee Crew required to prevent deviations in crew processing resulting in potential delays, exposing the airline to regulatory action, including Show Cause Notices and financial penalties from BCAS for non‑compliance. | 29-Jul | JIRA | 
SSQ search capabilities | Feature to view and track aircraft movements using tail number, providing complete visibility of the aircraft’s route history across sectors. Supports efficient investigation workflows by establishing a clear and chronological movement flow, including applicability for SRA- Safety risk assessment. | 29-Jul | JIRA | 
PTS - Improvements | Multiple improvements across PTS module to provide TRCs and management with consolidated KPI visibility, critical turnaround data, live baggage tracking, and zonal passenger insights to drive OTP performance and operational efficiency. | 29-Jul | AAM-7030 | Yes
AKS Migration | Migration of OTP dashboard to AKS as part of tech upgrade | 29-Jul | JIRA | 
Jan
Jan
July ’26

## Slide 78
AI Smart - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go Live Date | JIRA | EIP Integration Required (Yes/No)
Cargo load Prediction | Automation of cargo load updates in AI Smart for domestic narrow-body flights by applying predictive analytics based on historical flown data. | 28-Aug | JIRA | 
PTS task automation- PRS device | Automation of PTS worklist by integrating data from PRS devices. 12 manual tasks to be automated. (Security Check Start; Security Check End; Crew reported at aircraft; Catering Start; Catering End; Pilots Onboard, etc.) | 28-Aug | JIRA | 
AKS Migration | Migration of reports module to AKS as part of tech upgrade for reducing infra cost | 28-Aug | JIRA | 
Jan
Jan
Aug ‘26

## Slide 79
AI Smart - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go Live Date | JIRA | EIP Integration Required (Yes/No)
PTS task automation- Mobile FM device | Automation of PTS worklist by integrating data from Mobile FM devices via API. 6 out of 30 manual tasks to be automated (Bag/Cargo offload start; Bag/Cargo offload end; Bag/Cargo loading start; Bag/Cargo loading end; GNS bag offload start; GNS bag offload end) | 29-Sep | JIRA | 
Aircraft License Management & Alerts | Management of country specific licenses and creation alert engine based on flight parameters and licenses providing alerts if flight plan assignment violates parameters Automates validation of aircraft–region authorizations, ensuring regulatory compliance and reducing risk of unauthorized operations resulting in significant financial and reputational impact | 29-Sep | JIRA | 
AKS Migration | Migration of fuel compliance module to AKS as part of tech upgrade | 29-Sep | JIRA | 
Jan
Jan
Sep ‘26

## Slide 80
CE Plus - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go Live Date | JIRA | EIP Integration Required (Yes/No)
Automation for Missing Flight Reports | Achieve higher reporting compliance by proactively identifying and notifying teams (CE, Base and Service Performance) about missing flight reports. Providing visibility of missed/ pending flight reports to CE's in their dashboards | 28-Aug |  | 
Water Management | Achieve better monitoring of onboard water usage by tracking both loaded quantity and wastage for identifying SOP violations, tracking data impacting flight costs | 28-Aug |  | 
CM Function Visibility | Display CM Function code along with the existing parameters of crew type and crew rank to distinguish CM responsible for higher value sections (First/Business) | 28-Aug |  | 
Jan
Jan
Aug

## Slide 81
CE Plus - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go Live Date | JIRA | EIP Integration Required (Yes/No)
Routine Procedures | Achieve easier crew reference to important procedures so as to improve operational consistency across flights. | 28-Sep |  | 
Flight Deck Declaration Toggle | Achieve a simpler and clearer declaration process for flight deck checks through toggles for audit purposese | 28-Sep |  | 
Voice to Text | Achieve faster data entry and reduced typing effort during reporting and filing i=of issues. | 28-Sep |  | 
Grooming Guidelines | Achieve easier access to grooming standards so crew can follow expected norms consistently. | 28-Sep |  | 
Jan
Jan
Sep ‘26

## Slide 82
myAI - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go Live Date | JIRA | EIP Integration Required (Yes/No)
Digitization of Pilots, Cabin Crew and Dispatch team Training records | Digitization of training records through document upload, OCR-based data extraction, validation workflows, and centralized record management Supports Botminds replacement, ensures regulatory compliance, and improves efficiency through centralized digital management of training and qualification records. |  | MC-1654 | 
Admin Access for Pilot/CC/Dispatch Training Docs | Provides administrators with centralized access to view, search and manage training, license and qualification documents for Pilots, Cabin Crew, and Dispatch team with a central audit trail. |  | MC-1654 | 
Pilot/CC Docs – Camera, Photo Album, Multi-photo Upload | Enabling camera integration, photo album access and multi photo for upload functionality in a single submission flow with automatic PDF conversion Removes upload friction for users by enabling in-app camera capture, gallery access, and multi-photo submission — reducing incomplete document submissions and speeding up approval cycles |  | MC-1107 | 
Workplace - Engagement Notifications | Delivers personalized engagement notifications, including persona-specific updates |  | MC-2421 | 
myAI Homepage Redesign- Workplace Widgets | Redesigns the myAI homepage with an intuitive, personalized, and modern interface to improve discoverability of workplace features, content, and services. |  | MC-2024 | 
Passkey Implementation For App Login | Implements passkey-based authentication to enable secure, passwordless login using device biometrics or PIN. |  | MC-2446 | 
Pilot and Crew Docs Licenses Enhancements | Incorporating UAT feedback such as editable field changes, notifications to approver, list view etc |  | MC-2419 | 
Uniform – AOD | Uniform – Enabling uniform booking, entitlement selection, size exchange and reschedule capabilities for AOD dept |  | MC-2329 | 
Jan
Jan
July ‘26

## Slide 83
myAI - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go Live Date | JIRA | EIP Integration Required (Yes/No)
QR based immigration for Crew | Introducing QR code for faster immigration for crew from FTI – TTP Gates , eliminating need for manual processes and long wait time in queues with easy immigration process for 1700+ crew on daily basis |  | MC-204 | 
Personal Visa Approval Flow Change | Automatically approving any Personal Visa NoC letter requests reducing CEO-2 approval overhead Covering both dates and without dates letter requests |  | MC-1634 | 
Leave auto approval | Automatically approving leave request that stays in a “Pending Manager Approval” state for 5 calendar days from the original submission date thus cutting uncertainty and backlog |  | MC-811 | 
Cabin Crew Payable Hours | Real-time payable hours visibility - crew can view their accumulated payable hours for the previous months at any point, without waiting for payroll closure Gives cabin crew real-time, duty-wise visibility of monthly payable hours - reducing payroll disputes and crew queries (20-30 / week requiring data analysis) building trust and transparency in compensation process |  | MC-1806 | 
ACM Notifications to Medical Officer | Automatically notifies the mapped station Medical Officer when an ACM request is approved, providing visibility leading to compliance of BA testing. |  | MC-2433 | 
Extended Maternity LOP Leave | Introduces a new leave type, Extended Maternity LOP Leave, allowing eligible female employees to apply for up to 6 months of leave beyond standard maternity leave entitlements. Change in emailer template, sending more personalised communication to female employees |  | MC-2379 | 
Tech/UX Debt | Blob attachment feature with adobe emails WhatsApp integration(to replace CCNS dependency) Endpoint to insert notifications for InApp |  |  | 
Jan
Jan
Aug ‘26

## Slide 84
myAI - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go- Live Date | JIRA | EIP Integration Required (Yes/No)
Business visa letter template change | Changes to business visa NOC letter to accommodate visa norms and reduce HR queries |  | MC-1635 | 
ACM – Auto Cancel, Auto Approval | ACM – Auto Cancel, Auto Approval basis business logic to ensure compliance with regulatory requirements |  | MC-2435 | 
Meal Preference | Provides personalization by allowing crew to select meal preferences according to dietary needs. Handled via periodic notifications in Adobe |  | MC-2441 | 
Uniform – Pilots | Uniform – Enabling uniform booking, entitlement selection, size exchange and reschedule capabilities for Pilots |  | MC-2436 | 
Workplace – Search Functionality | Enhances search capabilities to search and discover information on people, groups and posts for a unified global search providing filters and improve result relevance. |  | MC-2438 | 
Workplace - Admin Persona Capabilities | Consolidates workplace administration capabilities within myAI, including delegation management, key updates authoring and publishing, and other workplace administration functions, enabling the decommissioning of Workvivo admin tools. |  | MC-2440 | 
Jan
Jan
Sep

## Slide 85
AIFP - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go-live date | JIRA | EIP Integration Required (Yes/No)
MEL Information | Real-time information on MELs (A-D, NEF, DD) associated with aircraft being operated by the pilots | 28-Jul | Link | 
Base Training | Ability to submit PSR-based training flight reports via AIFP with submission flow and integration with eGCA | 28-Jul | Link | 
Jan
Jan
July ’26

## Slide 86
AIFP - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go-live date | JIRA | EIP Integration Required (Yes/No)
Roster Monthly View ( Phase 2) | Enhanced Roster View with design changes for monthly, weekly, and list options | 28-Aug | Link | 
HOTAC | HOTAC integration to display hotel details directly within the roster | 28-Aug | Link | 
Crew Data & Compliance Alignment | Automated Seat Position Mapping for Pilots improving seat‑position accuracy by fetching real‑time CM data | 28-Aug | Link | 
 | Regulatory Role Mapping for PIC by Virtue & P1/US - Ensures accurate identification of PIC By Virtue and P1/US roles using defined logic based on CM data | 28-Aug |  | 
 | Shift‑Wise PIC & Co‑Pilot Role Accuracy - Provides accurate PIC and Co‑Pilot role display per shift | 28-Aug |  | 
 | Showing type of shift at shift level ie – Gen/Line Flying or Training | 28-Aug |  | 
Jan
Jan
Aug ‘26

## Slide 87
AIFP - FY27 Q2 Release Plan
Projects | Value Justification/Realization | Planned Go-live date | JIRA | EIP Integration Required (Yes/No)
Error Report flow for Flight data | Enhanced Error Reporting Flow for Flight and Crew Data allows pilots to submit error reports before departure, ensuring corrections are made prior to arrival and enabling accurate PSR submission ( Service Now Integration) | 28-Sep | Link | 
Approval Flow for Pilots | Allows the PSR to be submitted by one pilot and reviewed by all other pilots on the flight Providing Push and email notifications to Pilots for submission, resubmission flow and missing PSR | 28-Sep | Link | 
Jan
Jan
Sep ‘26

## Slide 88: Data Science and Advanced Analytics -FY26-27 Q1-Q2 Release Plan

## Slide 89: Commercial-Q1

## Slide 90
Commercial - FY26 Q1 Release Plan Status Update
Project/Initiative | Value Justification/Realization
Smart Pricing – Milestone 1 | The current fare-monitoring and filing workflow is manual, complex and time taking —analysts visually identify critical ODs, benchmark in spreadsheets, and pass human-led instructions to a BPO team—creating delays (1–3 days), capacity limits (≈400–600 ODs/day), and a high risk of missing critical ODs. We build a cost-effective solution along with computer user agent automation to augment the filing Phase 1 : Builds the foundation for scalable and Faster fare deployment, Higher pricing control & governance, Reduced revenue leakage.
April 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Smart Pricing – Milestone 2 | The current fare-monitoring and filing workflow is manual, complex and time taking —analysts visually identify critical ODs, benchmark in spreadsheets, and pass human-led instructions to a BPO team—creating delays (1–3 days), capacity limits (≈400–600 ODs/day), and a high risk of missing critical ODs. We build a cost-effective solution along with computer user agent automation to augment the filing Phase 2: Advanced filing options, ML‑driven recommendations, competitive simulation, and SSO access restriction, enabling sustained revenue uplift and analyst scalability.
May 2026

## Slide 91
Commercial - FY26 Q1 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
GHA Onboarding - Phase 1 ( Bach of 4 GHA - Station ) | Address 6 crore revenue discrepancy by automating the Cargo reconciliation process.; 100+ stations, each station agent consuming around 2 to 3 days to check, is being automated and reduced to few hours on the reconciliation process. GHAs included in this phase : AISATS, DNATA, DCSC, SATS
GHA Onboarding - Phase 2 ( Bach of 7 GHA - Station ) | Address 6 crore revenue discrepancy by automating the Cargo reconciliation process.; 100+ stations, each station agent consuming around 2 to 3 days to check, is being automated and reduced to few hours on the reconciliation process. GHAs included in this phase : YVR, YYZ, SFO, VIE, ZRH, BKK,SGN
Family Pool : Modify checks based on the new Family pool check | A total of ~6 Crore INR worth fraud detections were done in the current year and anticipated savings over next 3 years is ~20 Cr+ INR. Details as follows: In this phase we be making necessary changes to Family pool module to enable it to effectively identify family pool based fraudulent attempts in the updated family pool-based workflow.
Voucher Fraud Enhancements | Voucher fraud: 3.3 Crore INR worth revenue impact identification/analysis was done over 3014 Voucher impact and 6768 Tickets. In this phase we are bringing in few business rule changes and UI feature
Fraud Prevention Engine : Actioning directly from Fraud prevention engine | A total of ~6 Crore INR worth fraud detections were done in the current year and anticipated savings over next 3 years is ~20 Cr+ INR. Details as follows: In this phase Enhancement to Fraud prevention engine - where the users will be able to suspend / cancel the account directly from the system
May 2026

## Slide 92
Commercial - FY26 Q1 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Smart Pricing – Milestone 3 | The current fare-monitoring and filing workflow is manual, complex and time taking — analysts visually identify critical ODs, benchmark in spreadsheets, and pass human-led instructions to a BPO team—creating delays (1–3 days), capacity limits (≈400–600 ODs/day), and a high risk of missing critical ODs. We build a cost-effective solution along with computer user agent automation to augment the filing Phase 3: Scaled performance for large OD networks, End to End fare rule coverage across major ATPCO categories. Operational resilience with exception handling
June 2026

## Slide 93: Commercial-Q2

## Slide 94
Commercial RM - FY26 Q2 Release Plan Status Update
Project/Initiative | Value Justification/Realization
Smart Pricing – milestone 1, 2 & 3 + CR productionization | The current fare-monitoring and filing workflow is manual, complex and time taking —analysts visually identify critical ODs, benchmark in spreadsheets, and pass human-led instructions to a BPO team—creating delays (1–3 days), capacity limits (≈400–600 ODs/day), and a high risk of missing critical ODs. We build a cost-effective solution along with computer user agent automation to augment the filing Milestone 1 & 2 : In this stage we be focusing on Production movement of Smart pricing
GHA Onboarding - Phase 1 ( Bach of 4 GHA - Station ) | Address 6 crore revenue discrepancy by automating the Cargo reconciliation process.; 100+ stations, each station agent consuming around 2 to 3 days to check, is being automated and reduced to few hours on the reconciliation process. GHAs included in this phase : AISATS, DNATA, DCSC, SATS
GHA Onboarding - Phase 2 ( Bach of 7 GHA - Station ) | Address 6 crore revenue discrepancy by automating the Cargo reconciliation process.; 100+ stations, each station agent consuming around 2 to 3 days to check, is being automated and reduced to few hours on the reconciliation process. GHAs included in this phase : YVR, YYZ, SFO, VIE, ZRH, BKK,SGN
GHA Onboarding - Phase 3 ( Bach of 10GHA - Station ) | Address 6 crore revenue discrepancy by automating the Cargo reconciliation process.; 100+ stations, each station agent consuming around 2 to 3 days to check, is being automated and reduced to few hours on the reconciliation process. GHAs included in this phase : AMS, CDG, FRA, CPH, DOH, SHJ, RUH, DMM, JED, KUL
AWB- Sales slips based automations- Acceptance documents | In next 3 years, ~3 to 7 crores on the BPO cost optimization. In initial phase (EX INTERNATIONAL), BPO headcount reduction (15% from a head count of 16 to 14), processing speed improvement (4x, from 8-10 days to 2 days) is being achieved using 10K AWB pages/ month . In current phase (EX INDIA, DOMESTIC), automating and scaled up to 60K AWB and 60K acceptance docs.
Jul 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release

## Slide 95
Commercial RM - FY26 Q2 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Smart Pricing – Milestone 4 productionization | The current fare-monitoring and filing workflow is manual, complex and time taking —analysts visually identify critical ODs, benchmark in spreadsheets, and pass human-led instructions to a BPO team—creating delays (1–3 days), capacity limits (≈400–600 ODs/day), and a high risk of missing critical ODs. We build a cost-effective solution along with computer user agent automation to augment the filing Milestone 3 & 4 : In this stage we be rolling out to production all the features which are committed in milestone 3 & 4
GHA Onboarding - Phase 4,5,6 ( Bach of 13GHA - Station ) | Address 6 crore revenue discrepancy by automating the Cargo reconciliation process.; 100+ stations, each station agent consuming around 2 to 3 days to check, is being automated and reduced to few hours on the reconciliation process. GHAs included in this phase : BLR, BLR, CCJ, CJB, CNN, COK, HYD, IXM, MAA, TRV, TRZ, VGA, VTZ
AWB- Sales slips based automations- GHA Website | In next 3 years, few ~10's of crores on the BPO cost optimization. In initial phase (EX INTERNATIONAL), BPO headcount reduction (15% from a head count of 16 to 14), processing speed improvement (4x, from 8-10 days to 2 days) is being achieved using 10K AWB pages/ month . In current phase (EX INDIA, DOMESTIC), automating and scaled up to 60K AWB and 60K acceptance docs.
Next Best Travel Plan prediction | Predicting a user’s next likely travel destination and timing, enabling targeted marketing well in advance for higher engagement and conversions.
Fraud Prevention Engine – Mark voucher “Used” | Additional functionality to fraud prevention engine which enables user to mark a voucher as “Used” if its used and shown as active in the system
Aug 2026

## Slide 96
Commercial Cargo - FY26 Q2 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
GHA Onboarding - Phase 7 ( Bach of 13GHA - Station ) | Address 6 crore revenue discrepancy by automating the Cargo reconciliation process.; 100+ stations, each station agent consuming around 2 to 3 days to check, is being automated and reduced to few hours on the reconciliation process. GHAs included in this phase : TBD
Loyalty Fraud prevention application Enhancement – DOB changes | Changes to Date of birth validation in Fraud prevention engine to enhance validation and reducing false positives while identifying fraudulent attempts.
Sep 2026

## Slide 97: CX-Q1

## Slide 98
CX - FY26 Q1 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Voice of customer (Actionable suggestions) | Analytics platform that aggregates agent and customer interaction on inbound calls and converts them into structured insights presented through Dashboard
Project/Initiative | Value Justification/Realization
Voice of customer (Call Center Emotion Analytics) | Identify emotion of the customer (sentiment at the entry and exit phase) basis the call recordings of interaction between customer and agent.
May 2026
June 2026

## Slide 99: CX-Q2

## Slide 100
CX - FY26 Q2 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Voice of customer (Actionable suggestions) | Analytics platform that aggregates agent and customer interaction on inbound calls and converts them into structured insights presented through Dashboard
July 2026

## Slide 101
CX - FY26 Q2 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Voice of customer (Call Center Emotion Analytics) Emotion detecton | Identify emotion of the customer (sentiment at the entry and exit phase) basis the call recordings of interaction between customer and agent. This being part of larger initiative of post call analytics , is expected to contribute for the AHT optimization, and with 5% optimization on the human effort, ₹4Cr savings/year expected
Loyalty case automation | 20% of case automations, aligning to ~1Cr cost saving per year
NPS feedback enhancement | NPS score improvement: Previous year stats; Similar stats improvement to expect Overall score: NPS last FY: 16 to 30 this FY. CSAT score is specific to touchpoints. Arrival: 3.95 to 4.14 Boarding: 4 to 4.15 Booking : 3.99 and 4.15 Checkin: 4.01 to 4.21 Inflight Exp: 3.66 to 3.97 IN fight meal: 3.61 to 3.79
Aug 2026
Project/Initiative | Value Justification/Realization
NPS Anomaly detections( Phase1) | NPS score improvement: Previous year stats; Similar stats improvement to expect Overall score: NPS last FY: 16 to 30 this FY. CSAT score is specific to touchpoints. Arrival: 3.95 to 4.14 Boarding: 4 to 4.15 Booking : 3.99 and 4.15 Checkin: 4.01 to 4.21 Inflight Exp: 3.66 to 3.97 IN fight meal: 3.61 to 3.79
Sept 2026

## Slide 102: Operations-Q1

## Slide 103
Operations - FY26 Q1 Release Plan Status Update
Project/Initiative | Value Justification/Realization
April 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
FlightOps Compliance OCR for Pilot & CC | OCR service through API provided to MyAI for data extraction from Pilot and Cabin Crew license, qualification and documents. Few enhancements on Medical and CA35 documents expected by Internal Spoc which is in progress.
Flight 787 MEL data discrepancy checks | The MEL issues received from 787 is being compared with the corresponding XML (from vendor)
CVR Analytics-phase1 | Automation of safety analysis on Cockpit Voice Recordings
Project/Initiative | Value Justification/Realization
OTP Skypulse phase 2 | Rebuild the current On-Time Performance (OTP) chatbot- Skypulse. Provide comparison of OTP and related metrics with Historical data of 1.5 years
May 2026
June 2026

## Slide 104: Operations-Q2

## Slide 105
Operations - FY26 Q2 Release Plan Status Update
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
FlightOps Compliance OCR for Pilot & CC Phase3 (Dispatcher docs) | OCR service through API provided to MyAI for data extraction from Pilot and Cabin Crew license, qualification and documents. Few enhancements on Medical and CA35 documents expected by Internal Spoc which is in progress.
CVR Analytics | Automation of safety analysis on Cockpit Voice Recordings
Project/Initiative | Value Justification/Realization
FlightOps Compliance OCR for Pilot & CC Phase2 (Training and qualification docs) | OCR service through API provided to MyAI for data extraction from Pilot and Cabin Crew license, qualification and documents. Few enhancements on Medical and CA35 documents expected by Internal Spoc which is in progress.
OTP Skypulse phase 2 | Rebuild the current On-Time Performance (OTP) chatbot- Skypulse. Provide comparison of OTP and related metrics with Historical data of 1.5 years
Sept 2026
Aug 2026

## Slide 106: Data Engineering-FY26-27 Q1 Release Plan

## Slide 107: Finance-Q1

## Slide 108
Finance - FY26 Q1 Release Plan
Project/Initiative | Value Justification/Realization
Pax Reconciliation Report changes | The report was previously dependent on a file received from an external vendor through an SFTP location. By transitioning the data source to the same dataset available internally on Databricks, we eliminated the vendor dependency, streamlined the data integration process, and improved reliability. This optimization has resulted in a recurring cost saving of approximately ₹20 lakh per month.
2. Pipeline for Early Warning System(EWS) Activity | Developed the data pipeline and dataset for EWS activities, enabling automated fraud detection and monitoring by the Enterprise Automation team. This initiative helps identify potential ticket sale fraud early, reducing revenue leakage and protecting the organization from financial losses.
April 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
BSP Cashflow Dashboard & Automated Report | Automated the weekly Cash BSP reporting process, eliminating the manual consolidation of data from ~75 files. This improved reporting timeliness and accuracy, enabling the Treasury team to make faster and more effective fund allocation and cash management decisions.
2. BIAL AND NAG UDF Tax Report (Nagpur and Bangalore) | Automated the Bangalore and Nagpur Airport Tax reports, enabling accurate and timely tax filings while significantly reducing manual effort. The solution helps prevent overpayments, minimizes compliance risks and penalties, and improves overall financial governance.
3. Enhancements in Revenue Dashboard | Enhanced an existing revenue dashboard to cater to both Accounting/Revenue and FP&A teams, enabling reconciliation, revenue leakage prevention, and ancillary revenue analysis through a single solution. This eliminated the need for a separate report, creating a unified source of truth and saving approximately 60 man-days of development effort.
May 2026

## Slide 109
Finance - FY26 Q1 Release Plan
Jun 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
TDS Report | Developed a TDS Compliance Dashboard that automates TDS validation, reconciliation, exception monitoring, and filing readiness checks. The solution improves compliance accuracy, reduces manual effort, enables early error detection, and supports timely statutory filings while minimizing compliance risks.
2. Refund Re-Issue chain Tracking | Developed an end-to-end Reissue and Refund Analysis Report that provides complete visibility of ticket transactions linked to the original sale ticket. The solution overcomes limitations in the Amadeus ASA tool, improves audit readiness, strengthens revenue controls, and enables efficient identification of discrepancies and potential revenue leakage.
3. BIAL AND NAG UDF Tax Report (Nagpur and Bangalore) | Automated the Bangalore and Nagpur Airport Tax reports, enabling accurate and timely tax filings while significantly reducing manual effort. The solution helps prevent overpayments, minimizes compliance risks and penalties, and improves overall financial governance.
SOD Conflict | Developed an automated SOD booking conflict report to identify anomalies between hotel reservations and travel dates. The solution helps prevent revenue leakage, improves compliance monitoring, and reduces manual effort through proactive exception reporting.
Pay.ai (Native Payments Platform) | Integrated Pay.ai data into existing payment dashboards to ensure uninterrupted reporting and preserve current workflows. Enabled side‑by‑side comparison with XPP, delivering a single, consistent view of payment transactions, refunds, and efficiency metrics to support informed decision‑making.

## Slide 110: Finance-Q2

## Slide 111
Finance - FY26 Q2 Release Plan
Project/Initiative | Value Justification/Realization
LHR APD Tax Report Automation | Automation of APD reporting for LHR, BHX, and LGW flights by consolidating passenger data from DWH and ticketing systems. The solution improves compliance with HMRC regulations, reduces manual effort, enhances reporting accuracy, and mitigates the risk of penalties and revenue leakage.
2. US Tax Collection Report | Automation of generation of tax-specific reports for US tax codes across sales, reissues, and refunds, providing accurate and standardized tax collection reporting. The solution improves reconciliation efficiency, supports audit and compliance requirements, and reduces manual effort while strengthening financial controls.
July 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Q charge Report (Transaction Fee) | Report to identify, calculate, and process transaction fee payouts to agencies for eligible tickets that contain Q-charges in their fare construction
2. Airport Tax - Dashboard India & International | The dashboard will display the total airport taxes collected for each ticket, broken down by sector, along with the applicable taxes at both the sector level and the CPN level and the reconciliation based on DA
3. SAP Log ingestion | SAP LogServ Logs ingestion from Google Cloud Storage to Air India Azure Data Lake Storage. GCS contains around ~2TB yearly files which GCS will retain for 365 days, the ask is to bring those logs to AI Azure platform and to store them for audit purposes if needed.
Aug 2026

## Slide 112
Finance - FY26 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Forward Sales Dashboard Ph-II | Development of Forward Sales Trend Dashboard that compares daily and weekly forward bookings against forecasted and actual flown performance. The solution improves forecast accuracy, supports revenue planning, and enables proactive actions to optimize revenue and demand management.
2. Route Results | Automation of date and flight-level cost allocation for Route Results, enabling accurate route profitability analysis and eliminating manual allocation efforts. The solution improves financial reporting accuracy, supports network optimization decisions, and provides deeper visibility into route performance.
3. PR / PO Report | Development of a procurement analytics report to identify PR/PO splitting and higher-priced PO creations across AMOS and SAP. The solution strengthens procurement controls, improves compliance and audit readiness, and helps prevent unnecessary cost escalations through proactive monitoring
Sep 2026

## Slide 113: Operations-Q1

## Slide 114
Operations - FY26 Q1 Release Plan
Project/Initiative | Value Justification/Realization
E-Filing Automated storage of DCS customer reports and flight information for regulatory requirements. | Cost Reduction Total manhours saved per day = (15 min *700 flights)/24hrs = 175 manhours ~ 63,875 manhours per year Total printing cost saved per day = 700 * 0.6 = INR420 ~ INR 1,53,300 per year
2.Safety Audit Data Management & Analytics | Operational Excellence Build and store audit data sourced via iQSMS and create an analytics layer to display Audit KPI's
3. Movement Manager - Historical Data Integration | Operational Excellence Offload historical CAE MM data from MM database and store historical data on delta lake
April 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
GE ODW Data Integration | Operational Excellence GE ODW Data integration into delta lake to retrieve and store key operational data including FDR .
2. COO Dashboards – Phase I Enhancement | Operational Excellence Offload historical CAE MM data from MM database and store historical data on delta lake
Project/Initiative | Value Justification/Realization
1.Cew Roster Automation | Operational Excellence Near real time automation enablement of crew roster data - planned, published & actual crew roster data from CAE CM for building crew analytics for IOCC and other projects.
2.CEO Dashboards – Enhancements | Operational Excellence Enhance CEO dashboards for including PAX OTP view (OTP & Cancellations )
May 2026
June 2026

## Slide 115: Operations-Q2

## Slide 116
Operations - FY26 Q2 Release Plan
Project/Initiative | Value Justification/Realization
COO Dashboards - Phase II | Operational Excellence Building safety and denied boarding KPI's for COO dashboards
2. Crew Document Analytics – Phase I Crew Document Analytics automate KPI’s across Ops Efficiency , Compliance , Safety , OCR quality for enabling visibility into regulatory compliance, operational readiness. | Operational Excellence Reduces manual tracking, provides near real-time visibility into document processing, identifies approval bottlenecks, improves SLA adherence, and accelerates document renewal workflows.
3.IOCC - Chairman's requirement – Phase I | Operational Excellence
July 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
CEO Dashboards – AMOS Control Center | Operational Excellence
2. ODS Migration | Operational Excellence
3. Uniform Dashboard Enhancements | Operational Excellence - enabling the Uniform feature for engineering dept and would like to extend the Uniform Dashboard for them as a separate link
4.Crew Document Analytics – Phase II | Operational Excellence - Reduces manual tracking, provides near real-time visibility into document processing, identifies approval bottlenecks, improves SLA adherence, and accelerates document renewal workflows.
5.INVISIO – DEN Onboarding | Operational Excellence
6.Corporate Safety – Phase II | Operational Excellence
Project/Initiative | Value Justification/Realization
Zonal Boarding Analytics – Phase II | Operational Excellence AOD required to ensure zonal boarding compliance for every flight and requires ZB analytics to be calculated across airports, zones and aircraft types.
Aug 2026
Sep 2026

## Slide 117: CX-Q1

## Slide 118
CX - FY26 Q1 Release Plan
Project/Initiative | Value Justification/Realization
Transit NPS Survey – Logic Change for Technical Halts | Improve Customer NPS Enhancement of Transit NPS survey logic to exclude or appropriately classify passengers impacted by technical halts, ensuring survey responses accurately reflect the customer experience during transit journeys.
2. Paxia Project Enhancements | Operational Efficiency Implementation of multiple enhancements in the Paxia platform to improve functionality, usability, and operational effectiveness for customer service teams.
April 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Salesforce Data Archival | Cost Reduction Development of a data archival solution for Salesforce to move historical records from production systems while maintaining accessibility and compliance requirement
2. Email to Case – Agent Productivity | Operational Efficiency Enhancement of Email-to-Case functionality in Salesforce to automate case creation and streamline agent workflows for customer email handling.
3. Voice of Customer Dashboard | Improve Customer NPS Development of the first phase of the Voice of Customer Dashboard, consolidating customer feedback and satisfaction metrics into a centralized reporting platform.
4. Compensation Dashboard Enhancement | Improve Customer NPS Enhancement of the Compensation Dashboard to provide improved visibility into customer compensation requests, processing status, and resolution trends.
May 2026

## Slide 119
CX - FY26 Q1 Release Plan
Project/Initiative | Value Justification/Realization
Flight Disruption Dashboard – Flight Level KPIs | Operational Efficiency Development of flight-level disruption KPIs to provide detailed visibility into operational disruptions and their impact on customer journeys.
2. Booking Dashboard Enhancements | Operational Efficiency Enhancements to the Booking Dashboard to improve visibility into booking trends, performance metrics, and operational insights.
3. Misconnection Dashboard Enhancements | Improve Customer NPS Enhancements to the Misconnection Dashboard to improve tracking, analysis, and monitoring of passenger misconnection scenarios across the network.
4. Chat Report Enhancements | Operational Efficiency Enhancements to customer support chat reporting to provide deeper insights into chat performance, customer interactions, and service effectiveness.
5. ATSR Sales Dashboard Enhancements | Operational Efficiency Resolution of data duplication issues in the ATSR Sales Dashboard to ensure accurate sales reporting and performance tracking.
6. F&B Dashboard Enhancements | Improve Customer NPS Enhancements to the Food & Beverage Dashboard to provide improved reporting and visibility into onboard catering performance and customer feedback.
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
June 2026

## Slide 120: CX-Q2

## Slide 121
CX - FY26 Q2 Release Plan
Project/Initiative | Value Justification/Realization
1. Flight Disruption Dashboard – Pax Level KPIs | Operational Efficiency Provides passenger-level visibility into disruption impact, recovery progress, and service delivery KPIs. Enables operations and customer teams to make faster, data-driven decisions during irregular operations.
2. Seat Track Enhancements | Improve Customer NPS Enhances seat tracking and monitoring to improve seat availability and serviceability. Reduces customer dissatisfaction arising from seat allocation and onboard seating issues.
3. Compensation Dashboard | Cost Saving Centralizes compensation requests, approvals, and payout tracking across the organization. Improves transparency, reduces manual effort, and accelerates compensation processing.
July 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
1. Automated Email Response – Web 2 Case Handling - Refund Related Enquiries | Cost Reduction Uses AI to automatically respond to refund-related customer emails without agent intervention. Reduces contact center workload, lowers operational costs, and improves response turnaround time.
2. Automated Email Response – Flight Disruptions | Cost Reduction & Improve Customer NPS Sends timely, personalized AI-generated responses to customers affected by flight disruptions. Improves customer communication, reduces uncertainty, and enhances overall customer satisfaction.
3. OTP and PAX Dashboard- Enhancements | Operational Efficiency Enhances operational dashboards with improved On-Time Performance and passenger analytics. Enables proactive monitoring and quicker identification of operational bottlenecks.
Aug 2026

## Slide 122
CX - FY26 Q2 Release Plan
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
1. Automated Email Response – Web 2 Case Handling - Baggage-related cases | Cost Reduction Automates responses for baggage-related customer enquiries using AI and predefined business rules. Reduces manual handling effort while providing customers with faster updates.
2. Automated Email Response – Web 2 Case Handling - Compensation requests | Cost Reduction Automates responses for compensation-related customer requests based on eligibility and business policies. Minimizes manual intervention, improves consistency, and reduces support costs.
3. Automated Email Response – Web 2 Case Handling - Delay-related customer concerns | Cost Reduction & Improve Customer NPS Delivers immediate AI-driven responses to customers affected by flight delays with relevant information and next steps. Enhances customer experience through faster communication and reduced waiting time.
Sep 2026

## Slide 123: HR-Q1

## Slide 124
HR - FY26 Q1 Release Plan
Project/Initiative | Value Justification/Realization
1. Workforce Analytics – Employee Snapshot | Provides in-depth details about each employees - Employee 360 (tenure, moves, last survey, recognition, learning); Risk flags
April 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
Workforce Analytics – Position Snapshot | Provides details about positions in the organization – open positions, closed positions, time to fill etc
Project/Initiative | Value Justification/Realization
HR Capability – Adoption on reports | Provides a view on adoption of HR reports created - Active users; Views per report; Action-taken rate; Adoption heatmap
2. Organization effectiveness - Employee Cost (AOP Cost + Revenue Cost) | AOP vs Actual HR cost; HR cost per ASK slice; Saving %
May 2026
June 2026

## Slide 125: HR-Q2

## Slide 126
HR - FY26 Q2 Release Plan
Project/Initiative | Value Justification/Realization
HR Helpdesk Enhancement Report | Aims to strengthen HR Helpdesk operations by providing insights into ticket volumes, resolution performance, SLA adherence, reopen and reassignment trends, resolver workload, and overall service efficiency. Supports data-driven decision-making, improve operational governance, and help identify opportunities to enhance employee service experience
2. People Leave Analytics | Provides a comprehensive view of leave utilization, leave balances, leave behavior, and leave liability across the organization. The insights will support workforce planning, policy monitoring, and informed decision-making for HR and business leaders
July 2026
Delivered
Ontrack
Under delay and can be recovered
Delayed and pushed to next release
Project/Initiative | Value Justification/Realization
HR Capability – Adoption on reports | Provides a view on adoption of HR reports created - Active users; Views per report; Action-taken rate; Adoption heatmap
2. Organization effectiveness - Employee Cost (AOP Cost + Revenue Cost) | AOP vs Actual HR cost; HR cost per ASK slice; Saving %
Project/Initiative | Value Justification/Realization
Aug 2026
Sep 2026

## Slide 127: Thank you