## Slide 1
AI/UK Merger –
HR Systems Integration
16 Jul 2024

## Slide 2: Principles of Migration (HRMS)
UK active employee’s past 3 year’s HRMS data will be migrated from UK SuccessFactors (SF) (Source System) to AI SF (Target System).
The migrated data will be validated for any data mapping errors followed by corrections.
Parallel run will be done – 2 mock runs (1st Mock run from 23rd Aug to 30th Aug & 2nd Mock run from 9th Sep to 13th Sep) to ensure correctness of data.
On cutover, AI SF will become the Primary system.
Note: We will be replicating UK SF instance into a Non-Prod new AI SF instance with restricted admin access for meeting business & audit requirements. Post merger Go-Live, UK SF instance will be sunset by Nov 2024.

## Slide 3: Principles of Migration (Payroll)
UK active employee’s past 3 year’s Payroll data (Pay slip, Form 16, Tax slip) will be migrated from UK SAP S4 HANA (Source System) to a new AI PeopleStrong (PS) instance (Target System).
The migrated data will be validated for any data mapping errors followed by corrections.
Parallel payroll processing will be done for Aug & Sep months for UK employees in a new AI PS instance to ensure correctness of data.
On cutover, Primary system will comprise of 2 AI PS instance – one (existing) for processing AI employee’s payroll & other (new) for processing UK employee’s payroll (As per HR decision, AI & UK pay structures will not be harmonized until Mar 2025 & hence a separate PS instance needs to be maintained).
Nov 24 payroll to be processed by AI/UK? (1st 12 days of Nov 24 payroll inputs to be provided by UK/AI Payroll team. Accounting strategy for Nov 24 payroll is needed from Finance.)

## Slide 4
Jul
HRMS – Overall Timeline for UK-AI Merger
Nov
Oct
Sep
70 Aircraft Transfer
12th Nov
Aug
Data Mapping, Migration Preparation
Historical Data Upload
Emp data, Leave balance, Pay info, Candidate & Requisition data migration
Production Migration for UK
Data Mapping &
Migration Preparation
AI Prod Copy to new SF instance
8th July
HR to share harmonized structure
23rd July
5th Aug
23rd Aug
*Past 3 years active UK employee data as aligned with HR
Reconfigurations in AI SF instance
We are here
30th Aug
Historical Data Upload
Emp data, Leave balance, Pay info, Candidate data
9th Sep
Data Validation
13th Sep
Data Validation
Prod
Migration
27th Sep
Activation of UK Employee in AI SF
Historical Data* Migration Mock Run 1
Historical Data* Migration Mock Run 2
13th Aug
Data Migration Complete
Mock-Run 1 Complete
1st Nov
Parallel run for CAE-CM
2nd Sep
Data Migration Complete
Mock-Run 2 Complete
1st Oct
21st Sep

## Slide 5
Jul
Payroll – Overall Timeline for UK-AI Merger
Nov
Dec
Oct
Sep
70 Aircraft Transfer
12th Nov
Aug
Data Mapping, Migration Preparation & Configuration of UK Pay Structures
Production Migration for UK
13th Sep
Data Validation for Aug payroll
(Mock Run 1)
Data Mapping &
Migration Preparation
22nd Aug
Actual Nov Payroll from new AI PS instance
-UK Pay structures, pay heads & master data creation
-SF-PS Integration for test PS instance
-Data cleansing & template creation
Parallel Run
Aug payroll mock run in the new AI PS
Parallel Run
Sep payroll mock run in the new AI PS
13th Oct
Data Validation for Sep payroll
(Mock Run 2)
Historical data migration from SAP S4 HANA to AI PS
We are here
Mock-Run 2 in new AI PS Test Environment
Mock-Run 1 in new AI PS Test Environment
Payroll data for entire Nov to be processed from AI PS?

## Slide 6
Key Activities, Dependencies & Timelines (HRMS)
# | Key Activities | Timeline | Responsibility | Dependency
 | Data Mapping & Migration Preparation |  |  | 
1 | Data Mapping Sign-off | 25th June | Digital & Tech, BU | 
2 | Test Environment Creation – AI As-Is Prod Refresh | 8th July | Digital & Tech | 
3 | Configuration Decision Sign-off | 23rd July | Digital & Tech, BU | HR to share harmonized Org structure & HR policies
4 | Reconfigure AI Test Envt – Org Structure foundation objects, HR events, Time off, Pay Info, Goal templates | 24th July – 23rd Aug | Digital & Tech | Dependent on Config Decision Sign-off
5 | Data Cleansing & Templates creation | 24th July – 23rd Aug | Digital & Tech | 
 | Mock Run in AI Test SF instance |  |  | 
6 | Historical Data Migration Mock Run 1 | 5th Aug – 23rd Aug | Digital & Tech | 
7 | Data Migration Mock Run 1 – Data Validation | 13th Aug – 30th Aug | Digital & Tech | 
8 | Historical Data Migration Mock Run 2 | 31st Aug – 9th Sep | Digital & Tech | 
9 | Data Migration Mock Run 2 – Data Validation | 2nd Sep – 13th Sep | Digital & Tech | 
10 | Testing of Reconfigs & Data Migration- FUT, SIT & UAT | 26th Aug – 13th Sep | Digital & Tech, BU | 
 | Migration in Prod |  |  | 
11 | Migrate all Configs to AI SF Prod | 16th Sep – 20th Sep | Digital & Tech | 
12 | Integrations deployment on AI SF Prod | 23rd Sep – 27th Sep | Digital & Tech | 
13 | Historical data movement to AI SF Prod & Final validation | 20th Sep – 27th Sep | Digital & Tech, BU | 
14 | Hiring of UK employees on permanent roles in AI SF Prod | 12th Nov | Digital & Tech | 

## Slide 7
Key Activities, Dependencies & Timelines (Payroll)
# | Key Activities | Timeline | Responsibility | Dependency
 | Data Mapping & Migration Preparation |  |  | 
1 | Data Mapping Sign-off | 1st July | Digital & Tech, BU | 
2 | Test Environment Creation | 28th July | Digital & Tech | 
3 | Configuration Decision Sign-off | 15th July | Digital & Tech, BU | HR to share UK Pay structures & components
4 | Configure new AI PS instance - UK Pay structures, pay heads & master data creation | 1st Aug – 22nd Aug | Digital & Tech | Dependent on Config Decision Sign-off
5 | Data Cleansing & Templates Creation | 22nd Aug – 31st Aug | Digital & Tech | 
 | Aug Payroll Mock Run in new AI PS instance |  |  | 
6 | Payroll input for Aug month | 3rd Sep | BU | Dependent on UK Payroll & IFS teams to share payroll inputs for Aug month
7 | Emp Master data, Comp data, Investment declaration data upload on new AI PS instance | 6th Sep – 13th Sep | Digital & Tech | Dependent on payroll inputs for Aug month
8 | Payroll validation, final paysheet generation & sign-off | 13th Sep – 20th Sep | Digital & Tech, BU | 
 | Sep Payroll Mock Run in new AI PS instance |  |  | 
9 | Payroll input for Aug month | 3rd Oct | BU | Dependent on UK Payroll & IFS teams to share payroll inputs for Sep month
10 | Emp Master data, Comp data, Investment declaration data upload on new AI PS instance | 6th Oct – 13th Oct | Digital & Tech | Dependent on payroll inputs for Sep month
11 | Payroll validation, final paysheet generation & sign-off | 13th Oct – 20th Oct | Digital & Tech, BU | 
 | Migration to Prod |  |  | 
12 | Historical data movement to new AI PS Prod & Final validation | 1st Nov – 12th Nov | Digital & Tech, BU | 
13 | Nov Payroll Processing for UK employees from new AI PS Prod instance | 12th Nov – 20th Nov | Digital & Tech | 

## Slide 8: HRMS Data Migration Landscape
AI SF Prod
AI SF Test
(New Instance 1)
UK SF Prod
AI SF Test
(New Instance 2)
As-Is AI Copy
-Harmonized Org Structure & Policies Reconfigurations
Past 3 Years Historical UK active employee data
-Past 3 Years Historical UK active employee data
As-Is UK Copy
To be sunset
Future Repository of UK employee data
AI
UK

## Slide 9: Payroll Data Migration Landscape
AI PS Prod
AI PS Prod (New Instance for UK)
UK SAP S4 HANA
Past 3 Years Historical UK active employee payroll data
AI
UK
AI SF Prod
Integration between SF & PS
UK Pay Structure & Components Configurations
Existing
Integration
New
Integration

## Slide 10: Constraints & Dependencies
Area | Constraint/ Dependency | Solution
HRMS (SuccessFactors) | Pending sharing of harmonized Org structure with revised foundation objects from HR (Anuj Khanna, Rahul Gautam) | Expected by 22nd July, in case harmonized Org structure is not available by 22nd July, historical data upload mock run 1 to be done using current Org structure in AI SF Test; incremental reconfigurations to be done later prior to running historical data upload mock run 2 in AI SF Test
HRMS (SuccessFactors) | Pending sharing of harmonized HR policies with revised configurations from HR (Akanksha Jain) | In case harmonized HR policies not received by 29th July, historical data upload mock run 1 to be done assuming no change & incremental reconfigurations to be done later prior to running historical data upload mock run 2 in AI SF Test
Learning (Disprz) | Pending sharing of incremental licenses requirement within Integrated Org post merger for LMS tool Disprz from HR (Tanu Srivastava) | Inputs to be shared by HR team by 14th Aug

## Slide 11: Thank You