## Slide 1: HR Tech SteerCo Update
Digital & Technology
7th July 2026

## Slide 2
Contents
1. SteerCo Recap: Progress & Next Steps
3. New Tools Implementation Progress Update
4. ZTZT Payroll Automation Progress Update
2. Q1 & Q2 FY 27 Roadmap Update
6. Service Requests Update (Apr 26 till date)

## Slide 3: 1. SteerCo Recap: Progress & Next Steps
Digital & Technology

## Slide 4
SteerCo Recap: Progress & Next Steps
S.No | Key Action Item/Discussion Point | Owner | ETA | Status | Comments
1 | Complete end-to-end mapping of domestic payroll flow (including Exit F&F) and all touchpoints along with proposed solution, cost & timeline | Shripad Joshi/Amit Sood/Rasmeeta | 27-May-26 | Completed | End to end mapping of payroll components & flow completed for Domestic payroll; International payroll in progress
2 | Review and close TCS iDL exit commercials with no minimum payment commitment | Amit Sood/Shripad/Procurement Team | 21-Aug-26 | In Progress | 45 days exit period notice provided to TCS iON
3 | SuccessFactors LMS implementation - Expedite vendor onboarding | Amit Sood/Procurement Team | 20-July-26 | In Progress | Budget approval provided, RFP floated – vendor queries addressal in progress – vendor onboarding to be completed by 20th July basis ETA shared by Central Procurement team
4 | Explore attendance management coverage for international locations, starting with US and UK | Amit Sood/Shripad Joshi | TBD | In Progress | Zoho has timesheet capability – team is working with Zoho to estimate the efforts required to onboard international employees on to Zoho app
5 | Send extension note for revised Attendance Management Phase 2 timeline to 30th Sep 26 | Amit Sood | 6-July-26 | Completed | -
6 | Renegotiate ITSM / ServiceNow license commercials and confirm license availability | Vikram Singh/Jatinder | 1-July-26 | Completed | ServiceNow team had proposed a solution to remove dependency on licenses; UAT completed by HR & solution moved to Prod
7 | Prioritize Statutory Forms & letter generation in myAI | Amit Sood | Q2 2026 | In Progress | Owing to multiple operational priorities for business-critical functions, will need to be prioritized in Q2 2026 by myAI
8 | Reprioritize FY 27 Project Plan considering Audit and Board commitments & Employee experience for pilots | Amit Sood/Shripad Joshi | 15-July-26 | In Progress | Review with CHRO & CDTO pending to reprioritize the roadmap deliverables
9 | Automate HR Helpdesk Queries | Amit Sood | Q3 2026 | In Progress | To be prioritized as part of Q3 deliverable for Agentic track for HR
10 | Assigned assets visibility on myAi & current cost estimation | Amit Sood | 30-June-2026 | Completed | HAM (Hardware Asset Management) live on myAI

## Slide 5: 2. Q1 & Q2 FY 27 Roadmap Update
Digital & Technology

## Slide 6
45
TOTAL FY27 INITIATIVES
Portfolio across HRMS, Payroll, Talent, Experience and Analytics
8
Completed
Delivered / live
10
In Progress
Active delivery
26
To Be Started
Queued / future
1
Delayed / At Risk
Leadership watchlist
EXECUTIVE WORKSTREAM LENS
HRMS & Employee Data
8
Talent Acquisition & Experience
9
Performance / Talent / Learning
8
Payroll / Compliance / Finance
7
Analytics & Decision Intelligence
15
DELIVERED INITIATIVES
Conservative estimated / projected value from selected delivered capabilities; figures to be validated with process owners.
1
Comp Planning & Letters Automation
Estimated 60-70% reduction in manual letter effort during increment / bonus cycles; projected to lower template errors and rework by ~30-40%.
2
Crew Upgrade Automation
Projected 50-60% faster upgrade processing
through rule-based eligibility checks; improves
consistency and auditability of crew movements.
3
PMGM Team Touchpoints
Estimated >80% digitization of scheduled
manager-employee touchpoint documentation;
strengthens PMGM cycle compliance and leadership
visibility.
4
PeopleStrong BRE Expense Module
Projected to close key audit guardrails by
embedding rule-based controls; estimated 25-30%
reduction in exception handling / policy
clarifications.
5
Life Ka Plan + Azure / SF Integration
Estimated near real-time access lifecycle with 95%+ data sync reliability target; reduces manual entry / exit
dependency for employee insurance access.
Note:
Impact figures are intentionally conservative estimates / projections and should be baselined with post-go-live run-rate data.
FY27 HR Tech Portfolio
Status Snapshot
Single executive view · 45 initiatives · Categorized across HRMS, Payroll, Talent, Experience and Analytics
JUL 2026 · STEERCO

## Slide 7
FY27 Roadmap Reprioritization
Capacity trade-offs required to protect ZTZT end-to-end payroll automation
DECISION ASK
Why reprioritize now
ZTZT is an 8-month enterprise payroll transformation covering domestic + international payroll automation. It requires concentrated HR, D&T, Finance, vendor and integration bandwidth through Jan/Feb 2027.
184 + 309
Domestic + international payheads
13
External resources / POs
₹3 Cr
CAPEX approval path
100%
Manual touchpoints target
RECOMMENDED DEPRIORITIZATION / DEFERRAL LIST
Project / Scope
Decision
Rationale / value trade-off
Guardrail
Cabin Crew AON Assessment Integration
Defer
Non-payroll experience integration; resources better protected for ZTZT requirement, build and UAT cycles.
Revive post-ZTZT
TATA 1mg Integration for Pilots
Defer
Useful wellness / medical ecosystem integration, but not critical vs payroll automation and compliance accuracy.
Proceed only if mandated
ELT myAI Changes - non-compliance
Freeze all enhancement-only myAI scope; retain only statutory, audit, security or compliance fixes.
Compliance only
New BRE Tool & HOTAC
Defer
Net-new platform/process build will compete with payroll integration and rule-definition capacity.
BAU fixes only
360 Degree Multi-Rater Feedback
Defer
Talent feedback capability can be sequenced after critical payroll stabilization; manual workaround possible.
Reassess in Q4
SteerCo ask:
Approve temporary freeze on above roadmap items until ZTZT foundation, build and UAT bandwidth is secured.
Defer

## Slide 8
Initiative | Key Benefits | Go-Live ETA
Compensation Planning Templates, Increment & Bonus Letters Templates Implementation Ph 1 | Standardizes and automates compensation communication, reducing manual effort and ensuring error‑free, timely rollouts. | 28th Apr 2026
[Adhoc] Offer Letters Revamp Ph 1 – Optimizing offer letters (merging of multiple letters) & incorporating wage code changes​ | Reducing release TAT and rework while improving compliance and candidate experience​ | 28th Apr 2026
Life ka Plan & Azure SSO Integration​ | Ensuring single source of truth (SuccessFactors) across systems & 100% data accuracy​ | 28th Apr 2026
Workforce Analytics – Employee Snapshot Related Dashboard revamp​ | Provides deeper visibility into position structures, vacancies, and utilization through improved visuals and data accuracy, enabling better workforce planning.​ | 28th Apr 2026
FY 27 Q1 Release Plan – Key Initiatives
Completed
In Progress
At Risk
Apr 26
May 26
Initiative | Key Benefits | Go-Live ETA
End‑to‑End Crew Upgrade Automation (basis tenure, certification, etc.)​ | Automates upgrade decisions through rule‑based logic, improving fairness, process speed, and operational efficiency | 28th May 2026
Creating Employee Masters (Rule-Based with Validations) – Phase 1​ | Creates a validated, rule-based employee master ensuring data integrity and reducing downstream system inconsistencies | 28th May 2026
[Adhoc] Offer Letters Revamp Ph 2​ | Reducing release TAT and rework while improving compliance and candidate experience​ | 28th May 2026
Compensation Planning & Increment Letter + Bonus Letter Generation FY 26 Phase 2​ | Standardizes and automates compensation communication, reducing manual effort and ensuring error‑free, timely rollouts.​ | 28th May 2026
[SkyFam] Weekend Duty Travel Alert on Email for SOD​ (Delayed due to AIX Crew DH in progress) | Sends automated alerts for planned weekend travel, strengthening compliance, governance, and operational visibility.​ | 28th May 2026 21st July 2026
Initiative | Key Benefits | Go-Live ETA
Team Touchpoint on PMGM Automation​ | Automates scheduled manager–employee conversations, improving documentation quality and PMGM cycle compliance.​ | 27th June 2026
Workforce Analytics – Position Management Related Dashboard revamp​ | Delivers a more intuitive, comprehensive view of employee demographics, movements, and trends, improving stakeholder understanding and analytics adoption. | 27th June 2026
[Adhoc] Life ka Plan SF Integration | Ensure single source of truth for Life Ka Plan (Insurance) portal for employee master & ensuring seamless automated entry & exit of employees making access active/inactive near real time | 27th June 2026 2nd July 2026
Creating Employee Masters (Rule-Based with Validations) – Phase 2 | Creates a validated, rule-based employee master ensuring data integrity and reducing downstream system inconsistencies | 27th June 2026
PeopleStrong BRE New Module Implementation | Ensures enhanced compliance guardrails in place addressing audit observations | 1st June 2026
Jun 26
On Hold

## Slide 9
Initiative | Key Benefits | Go-Live ETA
Leave Pro-ration on Exit | Ensures fair and compliant leave settlement, reducing disputes and manual adjustments at exit. | 26th July 2026
Offer Letter Revamp Phase 3 – Optimizing offer letters (merging of multiple letters) & incorporating wage code changes​ | ​Standardizes and modernizes offer communication to improve candidate experience and reduce errors. | 26th July 2026
Goal Setting Revamp​ | Drives clearer performance alignment with business priorities, improving accountability & outcomes. | 26th July 2026
Employee Attrition & Overview Dashboard Enhancements | ​Improves workforce retention decisions providing real-time insights - attrition trends & key drivers. | 26th July 2026
AMS Dashboard Enhancements | Improves insights related to attendance & in turn productivity tracking | 26th July 2026
FY 27 Q2 Release Plan – Key Initiatives
Completed
In Progress
At Risk
July 26
Aug 26
Initiative | Key Benefits | Go-Live ETA
Cross Boarding Phase 1 in SF | Streamlines internal mobility by enabling seamless employee movement with minimal manual intervention.​ | 26th Aug 2026
SkyFam – Consultant Auto-passage creation | Automates consultant onboarding records, ensuring faster processing and improved data accuracy. | 26th Aug 2026
HR Cost Dashboard Implementation​ | Enables data-driven cost optimization by providing clear visibility into HR spending, workforce costs, and budget efficiency. | 26th Aug 2026
Initiative | Key Benefits | Go-Live ETA
AMS Phase 2 | Enhances end-to-end HR service delivery through deeper automation and scalability, driving significant efficiency gains. | 26th Sep 2026
Engineering Upgrade Automation​ | Reduces manual dependency and turnaround time by automating upgrade workflows, improving reliability and speed.​ | 26th Sep 2026
Cross Boarding Phase 2​ | Expands internal mobility capabilities with advanced automation, improving employee experience and operational efficiency at scale.​ | 26th Sep 2026
Manager Scorecard & Team Insights Dashboard​ | Provides leadership with strategic insights and KPIs to enable data-backed decisions and business alignment.​ | 26th Sep 2026
Worker & Employee Mapping in SF | Enables accurate workforce data alignment for better reporting, compliance, and decision-making.​ | 26th Sep 2026
Labour Code Changes in Payroll​ | Ensures payroll compliance with evolving labour laws while minimizing legal and financial risk. | 26th Sep 2026
Sep 26
On Hold

## Slide 10: 3. New Tools Implementation Progress Update
Digital & Technology

## Slide 11
Attendance Management Phase 2 Tool Implementation Update
RFP Closure
Functional & Tech DD Analysis Completion
Commercial Discussions & Contract Assignment
Requirement Gathering Workshops Completion
System Configurations & Integrations Start
System Configurations & Integrations Completion
UAT Completion & End User Trainings
CAB Approval, Production Deployment & Go-Live
2nd Mar 2026
1st Apr 2026
11th May 2026
12th May 2026
18th May 2026
14th Aug 2026
30th Aug 2026
30th Sep 2026
Completed
In Progress
At Risk
Key Upcoming Milestones
System configurations & integrations in progress – ETA: 14th Aug 2026
System configuration demo with HR to be scheduled by 10th July 2026
UAT to commence from 16th Aug 2026

## Slide 12
Hiring Experience Tool Implementation Update
Key Upcoming Milestones
RFP floated to vendors for supporting with implementation on 19th June 2026 by Central Procurement team
Queries received from vendors responded to by HR Tech & HR teams by 2nd July 2026
Functional & technical evaluation in progress – ETA: 10th July 2026
Implementation partner contract awarding to be completed by 18th July 2026
Basis leadership alignment, SAP SuccessFactors Smart Recruiters module finalized for Hiring Experience tool including custom BTP automation to ensure seamless transition from current RCM (Recruitment) module
Milestone | Timeline
RFP Initiation | 19-Jun
Pre-bid queries from suppliers | 23-Jun
Response to queries | 25-Jun
Initial response submission | 30-Jun
Technical evaluation | 07-Jul
Commercial Evaluation | 14-Jul
Approval | 17-Jul
Award | 18-Jul
Implementation Partner Onboarding Timelines (shared by Central Procurement Team)
Notes: Notes: We originally started this track because the existing SuccessFactors RCM experience had several usability and process gaps, both for internal admin users and candidates.
The initial approach was to procure a new hiring experience tool through an RFP. The intent was to retain SF RCM as the base system and integrate a new front-end or experience layer to address these gaps. As part of this, multiple vendors were functionally evaluated, and technical due diligence was completed for three vendors.
In parallel, we also evaluated SF Smart Recruiter. This was anyway a mandatory upgrade path from SuccessFactors RCM, although originally expected only after a couple of years. During functional analysis, Smart Recruiter appeared to address the same core issues that the RFP was trying to solve.
Therefore, the current recommendation is to advance the SF Smart Recruiter upgrade instead of introducing a separate tool. This reduces integration complexity, supports single-system usage, and may also provide cost optimization if the current RCM license construct can be replaced or adjusted against Smart Recruiter licensing. This commercial impact still needs to be formally confirmed with SAP.
Functionally, SF Smart Recruiter is now finalized as the preferred path. The immediate next step is for Procurement to initiate discussions with SAP on commercial quotes, licensing, and negotiations, along with identification of an implementation partner.
One impact to highlight is that the overall Go-Live timeline may need to be re-baselined. Earlier timelines were tracking towards July-end, but given the change in approach and dependency on SAP commercials and implementation partner onboarding, the revised Go-Live may move to September-end.

## Slide 13
Other Key Tools Implementation Update
SuccessFactors (SF) LMS New Module Implementation
Commercial Discussions with SF
Addendum Contract Signing with SAP
Requirement Gathering Workshop
System Configurations & Integrations Start
System Configurations & Integrations Completion
Historical Data migration from myAI and UAT Completion & End User Trainings
CAB Approval, Production Deployment & Go-Live
15th May 2026
28th May 2026
29th May 2026
12th June 2026
24th July 2026
15th Sep 2026
15th Oct 2026
30th Sep 2026
30th Oct 2026
1st Nov 2026
Key Upcoming Milestones
SAP SF LMS licenses discussions concluded
Onboarding implementation partner – RFP floated on 19th June by Central Procurement team; awaiting contract awarding by 20th July 2026
Risk: We foresee risk of delivery prior to H2 learning calendar launch (Sep Mid) due to: 1. Implementation partner alignment for SF LMS implementation
2. Delay of 3 weeks due to budget & contract considerations
Aligned Plan: In case of delay, we launch H2 calendar on myAI, migrate nominations received on myAI to SF LMS once launched
Completed
In Progress
At Risk
Milestone | Timeline
RFP Initiation | 19-Jun
Pre-bid queries from suppliers | 23-Jun
Response to queries | 25-Jun
Initial response submission | 30-Jun
Technical evaluation | 07-Jul
Commercial Evaluation | 14-Jul
Approval | 17-Jul
Award | 18-Jul
Implementation Partner Onboarding Timelines (shared by Central Procurement Team)
Notes: Appendix: Key Timeline of Actions
05 Jun 2026 – Requirement for SAP SuccessFactors LMS Implementation Partner shared by D&T Procurement; PR31625 referenced; budget of INR 45 lakhs indicated.
06 Jun 2026 – Finance requested additional governance details on current TCS LMS, business case, gaps, cost-benefit, penalties/claims, and HR sign-off.
09 Jun 2026 – D&T shared detailed responses to Finance queries, including current LMS background, gaps, TCS limitations, and SteerCo alignment.
09 Jun 2026 – HR confirmed that sufficient exploration had been completed and that CHRO and CDTO had approved moving ahead with SAP SuccessFactors LMS.
10 Jun 2026 – HR shared signed-off BRD for SF LMS implementation by Head TLC.
11 Jun 2026 – D&T requested status and timelines for interviewing/evaluating implementation partners.
15 Jun 2026 – D&T again requested partner profiles/interviews, highlighting delay against SteerCo-aligned go-live timelines.
15 Jun 2026 – D&T Procurement requested Central Procurement to seek quotes from partners, subject to closure of queries.
15 Jun 2026 – Finance requested commercial comparison between TCS iDL and SuccessFactors LMS.
15 Jun 2026 – D&T Procurement shared cost comparison, indicating annual savings of approx. INR 8.56 lakhs through migration.
15 Jun 2026 – Finance confirmed alignment and gave go-ahead to move forward.
18 Jun 2026 – D&T requested next steps and evaluation timelines, reiterating the need to begin implementation by 1 July.
19 Jun 2026 – D&T requested ETA for partner profiles, as the plan was already behind schedule.
19 Jun 2026 – Central Procurement shared proposed RFP timeline with award currently planned for 18 July.

## Slide 14: 4. ZTZT Payroll Automation Progress Update
Digital & Technology

## Slide 15
ZTZT – End to end Payroll Automation & Transformation
Overall status: AMBER
Focus: July foundation
ZTZT is moving from design into mobilisation. Immediate priority: close budget approval (planned date of 8th July 2026), complete onboarding, lock requirements and unblock integration dependencies.
SCOPE
184 + 309
Domestic payheads + international payheads
TARGET
100%
Manual touchpoints eliminated by Jan/Feb 2027
RESOURCES
13
External resources contracted / POs initiated
BUDGET
₹3 Cr
CAPEX approval path in progress
Current Progress
Mobilisation
External resource model identified – pending budget approval
Tooling, workspace, repo setup and orientation being mobilised
Requirements & Governance
AI Payroll, HRBP, C&B, CAE and Finance leads engaged
Phase-wise scope and RACI being firmed up
Monthly steering cadence to be established
Execution Readiness
July foundation: requirement sign-off and integration environment setup
AI validation architecture to be finalised
API / vendor dependencies need owner-level closure
Jul
Foundation
Aug-Sep
Critical
Oct-Nov
Scale
Dec-Feb
Tail cleanup
Hypercare
SteerCo Attention / Decisions Needed
1
Budget closure
Confirm ₹3 Cr approval path and expected approval date.
2
Dependency ownership
Assign owners for CAE, AMOS, LifeKaPlan, ADP, bank and HR dependencies.
3
Governance endorsement
Approve monthly SteerCo review plus daily execution cadence during mobilisation.
15

## Slide 16: 5. Service Requests Update (Apr 26 till date)
Digital & Technology

## Slide 17
Service Requests FY26
Apr 1st till date | Same data as source slide, shown as charts instead of tables
149 TOTAL REQUESTS
149
SERVICE
REQUESTS
Effort split
105
43
Low Effort
105
70%
Medium Effort
43
29%
High Effort
1
1%
Low-effort SRs dominate
105 / 149 requests
Category distribution
Ranked horizontal bars highlight repeat-demand hotspots
Top 2 = 71
48% of SRs
Top 4 = 102
68% of SRs
Job Code Creation & Updates
38
Access, Role & Report Provisioning
33
Foundation Object Config. & Mapping
16
Routine Operational Updates
15
Form Processing
11
Moderate Configuration Updates
10
Resignation Workflow Reversal
8
Letter & Template Updates
7
Report Scheduling & Automation
6
Holiday Calendar Maintenance
4
High-Urgency / Priority Requests
1
Executive readout: Access + job-code governance and FO mapping can reduce the largest repeat-request clusters.
Notes: Single-slide graphical representation of Service Requests FY26 categories and effort split. Data used: - Effort split: Low Effort 105, Medium Effort 43, High Effort 1; Total 149. - Category split: Job Code Creation & Updates 38; Access, Role & Report Provisioning 33; Foundation Object Configuration & Mapping 16; Routine Operational Updates 15; Form Processing 11; Moderate Configuration Updates 10; Resignation Workflow Reversal / Correction 8; Letter & Template Updates 7; Report Scheduling & Automation 6; Holiday Calendar Maintenance 4; High-Urgency / Priority Requests 1. [Sources] - Attached deck: HR_Tech_SteerCo_July_7th.pptx, Service Requests FY26 update slide. - Uploaded screenshot of Service Requests FY26 table.

## Slide 18: Thank You

## Slide 19
FY 27 Projects & Plan
Theme | S.No. | Initiative | Release Quarter (TENTATIVE)
Core HR & Employee Data Foundation | 1 | Crew Upgrade Automation for Designation, Comp update Completed | Q1
 | 2 | Leave Pro-ration on notice period In Progress | Q1
 | 3 | Creating Employee Masters (Rule Based with Validations) Completed | Q2
 | 4 | Implementation of JPB (Job Profile Builder) | Q2
 | 5 | AMS Phase 2 + Linkage to Payroll In Progress | Q2
 | 6 | AMS Phase 3 + Linkage to Payroll | Q3
 | 7 | Automate Employee upgrades – Engineering | Q3
 | 8 | International Employee Complete Lifecycle | Q4
Talent Acquisition & Employee Lifecycle | 9 | [Adhoc] Offer Letters Revamp - Optimizing offer letters – Completed | Q1
 | 10 | Onboarding 2.0 Enhancements In Progress | Q2
 | 11 | Cross Boarding Implementation - IJP & Group Transfer In Progress | Q2
 | 12 | New Hiring Experience Tool Implementation | Q3
 | 13 | New Employee Assimilation - Employee Touchpoints Digitization | Q3
Experience, Culture & Future of HR | 14 | Automation of Nudges at Career Milestones | Q3
 | 15 | HR Helpdesk Automation End to end with Agentic AI | Q4
 | 16 | Disciplinary Tool Design & deployment | Q4
 | 17 | HR Analytics Chatbot (RAG) Implementation | Q4

## Slide 20
FY 27 Projects & Plan
Theme | S.No. | Initiative | Release Quarter (TENTATIVE)
Performance, Talent & Growth Systems | 18 | Team Touchpoints implementation on PMGM Completed | Q2
 | 19 | Implementation of EDP (Employee Development Plan) across organization | Q3
 | 20 | Mid Year to final Evaluation revamp | Q3
 | 21 | New LMS module implementation In Progress | Q3
 | 22 | Implementation of Talent integration HUB (TIH) | Q3
 | 23 | Succession Management Enhancements | Q4
 | 24 | Learning Overview Implementation | Q4
Payroll, Compliance & Financial Accuracy | 25 | Comp Planning & Letters Generation Revamp & Automation – Completed | Q1
 | 26 | Enable LWD FNF module on SuccessFactors In Progress | Q2
 | 27 | BRE People Strong Expense Module Completed | Q1
 | 28 | Crew Allowance Automation In Progress | Q2
 | 29 | Wage component Distribution to change as per compliance | Q2
 | 30 | End to End Payroll Automation In Progress | Q4

## Slide 21
FY 27 Projects & Plan
Theme | S.No. | Initiative | Release Quarter
Analytics, Insights & Decision Intelligence | 31 | Position Management Revamp Completed | Q1
 | 32 | Employee Snapshot Dashboard Revamp Completed | Q1
 | 33 | Org. Snapshot Dashboard Implementation In Progress | Q1
 | 34 | Employee Cost (AOP Cost + Revenue Cost) Dashboard Implementation In Progress | Q2
 | 35 | Payroll Quality & Variance Report Implementation | Q2
 | 36 | Servicing Report Implementation | Q2
 | 37 | Compensation & Bonus Dashboard Implementation | Q3
 | 38 | Advantage Club R&R Dashboard Revamp | Q3
 | 39 | Adoption on Reports Dashboard Implementation | Q3
 | 40 | HR Scorecard Dashboard Implementation | Q4
 | 41 | Develop & Deploy HR Predictive & Prescriptive Models | Q4
 | 42 | Manager Scorecard & Team Insights Dashboard Implementation | Q4
 | 43 | Leader Scorecard Dashboard Implementation | Q4
 | 44 | Talent Analytics Map Implementation | Q4
 | 45 | Culture Dashboard Implementation | Q4