## Slide 1: Steering Committee Meeting for HR Tech UK – AI Merger 05-Sep-2024
Digital & Technology

## Slide 2: Todays Agenda
1 | Core HR System – SAP SuccessFactors (SF) Organization Structure; Employee Central; Recruitment & Onboarding; Performance & Goal Management | 
2 | Payroll – PeopleStrong -Merger Principles, Approach & Plan -Upcoming Activities -Payroll Mock Run 1 (Aug Payroll Parallel Run) -RAID | 
3 | Other HR Tech Apps -Learning & Development (TCS iDL, Disprz) -Staff Travel (iFly) -Rewards & Recognition (Advantage Club) | 

## Slide 3: 2. Payroll - PeopleStrong

## Slide 4
Payroll (PeopleStrong) - Merger Principles & Approach
Merger Guiding Principles
UK Crew Salary to be processed by UK Payroll team within UK SAP S4 HANA till merger Go-Live (12th Nov 24).
Separate (New) AI PeopleStrong (PS) instance will be configured with UK pay components – UK pay components & structures to be harmonized post-merger by Apr 2025.
Payroll markers & rates for variable pay components (flying hours, layover count, SIM training hours, etc.) for UK & AI Crew (Cabin & Pilots) will be of AI post-merger.
UK Crew (Cabin & Pilots) will operate on UK ARMS crew management & tracking system till 11th Nov 24 & will be onboarded on to AI CAE post 11th Nov 24 midnight.
Salary for Nov 24 to be processed partially by UK (till 11th Nov EOD) & partially by AI (12th Nov onwards). AI will pay to employee salary in one shot to employees on 30th Nov 24.
There will be 2 Form 16 for UK employees’ post-merger & their settlement will be done by UK Payroll team prior to merger.
UK active employee’s past 5 year’s Payroll data will be migrated from UK SAP S4 HANA (Source) to new AI PeopleStrong (PS) instance (Target) – Salary Slips & Form 16.
-Configuration of UK pay structures in new AI PS instance
-3 parallel payroll mock runs (Aug, Sep, Oct) (In Progress)
-UK IFS & Flight Ops team to provide payroll inputs to AI Payroll team for mock runs
-Flying allowance (variable pay) till 31st Oct salary final calculation to be done by UK payroll for UK Crew
-PS Instance Testing: UAT Completion – 16th Oct 24; Full data migration completion by 18th Oct 24.
-UK IFS & Flight Ops to share flying allowance payroll inputs from 1st to 11th Nov with AI IFS & Flight Ops team
-Harmonized employee master, UK roster & UK leaves Data migration from ARMS to CAE (Go-Live: 11th Nov)
-Flying allowance salary (till 31st Oct) calculation for UK Crew by UK Payroll team (payout on 30th Nov) to be shared with AI Payroll team
-Fixed salary (non-flying) calculation for UK Crew of non-flying salary till 11th Nov by UK Payroll team (post deducting TDS & PF) to be shared with AI Payroll team
-Payout of Flying allowance salary (till 31st Oct) to UK Crew
-Payout of fixed salary component for Nov month to UK Crew (inputs for 1st to 11th Nov from UK & for 12th to 30th Nov from AI)
1st-31st Dec 24
-Fixed salary calculation from 1st to 31st Dec for UK & AI Crew by AI Payroll team
-Flying allowance salary (1st to 30th Nov) calculation for UK & AI Crew to be compiled by AI Payroll team
On 31st Dec 24
-Fixed salary (1st to 31st Dec) payout to UK & AI Crew
-Flying allowance salary (1st to 30th Nov) payout to UK & AI Crew
31st Oct 24
1st Nov 24
Timeline ->
11th Nov 24
30th Nov 24
31st Dec 24
Approach

## Slide 5
Payroll (PeopleStrong) - Program Plan & Current Status
Completed
Yet to Start
Timeline
May 24
June 24
Sep 24
July 24
Aug 24
Oct 24
Nov 24
Progress
PeopleStrong
Discovery Workshops & End State Agreement
(6th May)
Finalize data migration & payroll processing approach
(26th Aug)
Finalize UK-AI Data Mapping & Transformation requirements
(25th June)
HR to share UK Pay structures & components
(27th June)
Contract Signing of PS License contract
(4th Sep)
End (20th Sep)
Start (6th Sep)
Start
(3rd Oct)
End
(16th Oct)
Historical payroll data migration completion
(31st Oct)
Live Payroll Processing 12th Nov onwards ->
Start
(1st Nov)
End
(8th Nov)
HR Tech System
Start
(23rd Sep)
End (1st Oct)
Merger Documents Sign-off from HR
(4th Sep)
12th NOV
Aug Parallel payroll mock run & data validation
Sep Parallel payroll mock run & data validation
Oct Parallel payroll mock run & data validation
Configuration of UK pay structure in AI PS instance
We are here
12th Sep

## Slide 6
Payroll (PeopleStrong) – Upcoming Activities
S.No. | Milestone | Priority | Planned | Actual | Status | Comments
1 | New PS Instance Procurement | High | 30-Aug-24 | 4-Sep-24 | Completed | -
2 | Payroll System (Engine) Setup | High | 6-Sep-24 | 13-Sep-24 | In Progress | Setting up basic functionalities in new PS (Payroll engine) instance
3 | HR to share Aug payroll input & Data | High | 6-Sep-24 | 17-Sep-24 | In Progress | HR (Anuj Khanna, Ajay Aggarwal) to share following: -Employee Master Data (Shared) -Sample CTC Report (Shared) -Salary Register (To be shared) -Tax Computation Sheets (To be shared) -Payroll Inputs for Aug (To be shared)
4 | UK Pay Components & Structure Configurations | High | 12-Sep-24 | 16-Oct-24 | In Progress | Configuring new PS instance with UK pay components & structures as per UK payroll policies
5 | Mock Run 1 – Aug Payroll Processing | High | 23-Sep-24 | 27-Sep-24 | Yet to Start | -
6 | Mock Run 1 – Aug Payroll Sign-off | High | 30-Sep-24 | 1-Oct-24 | Yet to Start | Validation around Gross salary & tax calculations

## Slide 7
Payroll (PeopleStrong) – Mock Run 1 (Aug Payroll)
S.No. | Milestone | Priority | Planned | Actual | Status
1 | Payroll Input to be shared by UK HR for Aug | High | 11-Sep-24 | 11-Sep-24 | In Progress
2 | Input Validation & Clarification | High | 13-Sep-24 | 13-Sep-24 | Yet to Start
3 | Employee Master Data Upload | High | 17-Sep-24 | 17-Sep-24 | Yet to Start
4 | Compensation Data Upload | High | 17-Sep-24 | 17-Sep-24 | Yet to Start
5 | Employee Master & Compensation Data Validation | High | 20-Sep-24 | 20-Sep-24 | Yet to Start
6 | Head Count Validation | High | 20-Sep-24 | 20-Sep-24 | Yet to Start
7 | Aug month payroll parallel processing | High | 27-Sep-24 | 27-Sep-24 | Yet to Start
8 | Aug month payroll validation & sign-off | High | 1-Oct-24 | 1-Oct-24 | Yet to Start

## Slide 8
Payroll (PeopleStrong) – RAID (Risks, Actions, Issues, Decisions)
Type | Description | Impact | Probability of Occurrence | Mitigation Plan | Status | Target Date
Decision | Payroll calculation logic for UK Crew needs to be defined by HR, IFS & Flight Ops & Payroll teams for the 1st to 11th Nov period | Medium | Low | -Decision to be shared by HR by 20th Sep 24 -In case decision is not received, UK & AI respective logics to be followed pre & post-merger Go-Live | In Progress | 20th Sep 24
Risk | Payroll calculations if not vetted correctly may result into wrong payouts to Vistara employees | Medium | Low | -To mitigate, parallel payroll processing mock runs to be done for Aug, Sep months to validate & correct any anomalies prior to merger | In Progress | 16th Oct 24
Risk | Risk of incorrect payouts to harmonized Org employees due to different pay structures for Air India & Vistara employees’ post-merger | Medium | Low | -Ensuring creation of identifier in AI SF to distinguish ex-UK & AI employee post-merger​ -Ensuring PeopleStrong SOP update to do regular audit checks (monthly) prior to processing payroll for the identifier being passed from AI to PS | In Progress | 16th Oct 24
Risk | Issue in reimbursement reconciliation for Vistara employees’ post-merger in case they have already claimed reimbursement in Vistara | Low | Low | -All dues for Vistara employees to be cleared by Vistara payroll team prior to merger Go-Live -Arrears (if any) to be shared by UK team to AI PS team for processing with AI salary payout | In Progress | 30th Oct 24
Risk | Risk of incorrect calculation of taxes since movement of Vistara employees is happening mid-year | Low | Low | -Settlement for Vistara employees will be processed due to closure of PF & issuance of Form 16​ -Gratuity & Leave Encashment to be carried forwarded to AI, to be managed through Tata Group DOJ in PS system​ (to be created in AI SF) -2 Form 16s for Vistara employees to be maintained | In Progress | 30th Oct 24

## Slide 9: 3. Other HR Tech Apps

## Slide 10
Other HR Tech Applications Business Assumptions, Decisions & Open Points
Business Assumptions & Decisions
Learning & Development (TCS iDL & Disprz):
  UK learning history data elements will be migrated by HR Tech team within TCS iDL from UK SuccessFactors (UAT Completion: 31st Oct 24, Full Data Migration: 11th Nov 24)
  No additional licenses are forecasted currently for merged entity for Disprz for FY 24-25; current quota of Disprz licenses are enough & will be re-assigned by AI HR in case of any additional requirements
  Following reconfiguration changes need to be done (ETA: 31st Oct 24):
    Bulk Cool Off Period functionality
    On demand trainings audit trail
    Anonymous survey submission feature
  No data migration to be done from UK e-learning application (currently used by UK engineering team) to AI TCS iDL system – business to keep offline records at their end
Staff Travel (iFly):
  Need to upload a fixed passage quota applicable for remaining FY 24-25 for UK employees’ post-merger basis policy decision taken by AI HR (ETA: 11th Nov 24)
Rewards & Recognition (Advantage Club):
  No historical data related to Rewards & Recognition of Vistara employees needs to be migrated to AI Advantage Club
Upcoming Activities
Learning & Development (TCS iDL):
  Learning history migration mock run to commence from 18th Sep 24
  Following learning history data points to be uploaded from UK SuccessFactors LMS to AI TCS iON as part of mock run:
    Past learning records including completed courses information (Name, SAP ID, Course Name, Course Duration, Completion Status, Learning Hours gained for learning history data).
    Past learning certificates in the form of PDFs.

## Slide 11
Merger Documents Sign-off Status
HR Tech Application | Documents | Sign-off Pending with
SuccessFactors – Employee Central & Onboarding | 1. Employee Central & Onboarding - Key Business Assumptions & Decisions 2. Employee Central & Onboarding - Program Plan 3. Employee Central & Onboarding - Data Mapping | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
SuccessFactors – Performance & Goal Management | 1. Performance & Goal Management - Key Business Assumptions & Decisions 2. Performance & Goal Management - Program Plan 3. Performance & Goal Management - Data Mapping | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
SuccessFactors – Recruitment | 1. Recruitment - Key Business Assumptions & Decisions 2. Recruitment - Program Plan 3. Recruitment - Data Mapping | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
PeopleStrong (Payroll) | 1. PeopleStrong - Pay Components Data Field Mapping 2. PeopleStrong - Business Decisions & Assumptions 3. PeopleStrong - Program Plan | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
Advantage Club (R&R) | 1. Advantage Club - Program Plan 2. Advantage Club - Key Business Assumptions & Decisions | 1. Signed by all stakeholders 2. Signed by all stakeholders
TCS iDL & Disprz (Learning & Development) | 1. Learning & Development - Business Decisions & Assumptions 2. Learning & Development - TCS iDL Program Plan 3. Learning & Development - Disprz Program Plan | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
iFly (SkyFam) | 1. iFly (SkyFam) - Program Plan 2. iFly (SkyFam) - Key Business Assumptions & Decisions | 1. Abhinav Rajmalwar, Akanksha Jain, Vikrant Bhatnagar 2. Abhinav Rajmalwar, Akanksha Jain, Vikrant Bhatnagar

## Slide 12: 3. Appendix

## Slide 13
Payroll (PeopleStrong) Business Assumptions, Decisions & Open Points
Business Assumptions & Decisions
AI & UK pay structures will not be harmonized pre-merger – separate UK pay structures & components to be configured in a separate (new) AI PeopleStrong (PS) instance with UK payroll policies.
Salary for UK employees for Nov 24 to be processed partially by UK (up till 12th Nov) & partially by AI from PeopleStrong (13th Nov onwards).
Payroll markers & rates for variable pay components (flying hours, layover count, SIM training hours, etc.) for UK & AI Crew (Cabin & Pilots) will be of AI post-merger
UK active employee’s past 5 year’s Payroll data will be migrated from UK SAP S4 HANA (Source) to new AI PeopleStrong (PS) instance (Target) – Salary Slips & Form 16.
3 mock runs (parallel payroll processing) to be done for Aug, Sep & Oct months in Test PS environment – UK team to
No historical data migration for BRE considered since all reimbursements to be settled prior to merger by UK payroll team.
There will be 2 Form 16 for UK employees’ post-merger & their settlement will be done by UK Payroll team prior to merger.
PS Instance Testing: UAT Completion – 16th Oct 24; Full data migration completion by 18th Oct 24.
Open Points & Risks
Potential risk for parallel mock run 1 – delay anticipated of ~1 week due to delay in finalization of instance strategy for merged entity & contract closure Mitigation Plan: Additional resources to be deployed by PeopleStrong team to complete configurations within planned timelines for being ready for mock run 1

## Slide 14: Thank You