## Slide 1: Steering Committee Meeting for HR Tech UK – AI Merger 23-Sep-2024
Digital & Technology

## Slide 2: Todays Agenda
1 | Core HR System – SAP SuccessFactors (SF) Organization Structure; Employee Central; Recruitment & Onboarding; Performance & Goal Management | 
2 | Payroll System – PeopleStrong -Merger Principles & Approach (Plan) -Upcoming Activities -Payroll Mock Runs (Mock Runs Validation Criteria & Mock Run 1 Update) -RAID | 
3 | Other HR Tech Apps -Learning & Development (TCS iDL, Disprz) -Staff Travel (iFly) -Rewards & Recognition (Advantage Club) | 

## Slide 3: 1. Merger Project - SF

## Slide 4: Merger Project – Plan on a Page
SuccessFactors
Jun’ 24
Jul’ 24
Aug’ 24
Sep’ 24
Nov’ 24
Dec’ 24
2025
Oct’ 24
Cut Over
1
Build & Test
Extend Config
Mock 1
Data Prep
Project Kick-off workshop
Merger Plan Finalization
Initiate & Design
Asses
Target state
Cut Over 2
Cut Over 1
Mock Loads | Cut Over 1 | Cut Over 2
Mock 2 Employee data load; Leave data; Pay data; HR validation | New harmonized structure Seconded Employees – employment history data load Candidate data load | Non-Seconded Employees – complete data load Seconded Employees – delta data load Inter-company transfer event Goal template; APR forms; Rating – data load Leave balances – data load Pay data – data load
We are here
Harmonized Structure
Mock 2
Data Prep
Cut Over
2
Design

## Slide 5: Overall Status Update
Executive summary | 
Workstream | Merger Project
Reporting Period | 9-Sept to 20-Sept
Overall status | Needs Attention
Mock 1 Sign off Mock 2 Data Extraction Mock 2 Data Mapping SF format
Accomplishments during the reporting period
Mock 2 data load validation from HR Integration Design Document – UK Payroll Technical Validation of Loads
Update on open items from last meeting
Items in progress
Data Load – Mock 2
UAT Execution & Sign Off Cut over 1 plan
Chart: 
| Current Week | Total Weeks
Transition Status | 330 | 315
58%
Implementation completion
Upcoming focus areas

## Slide 6: Mock 1 – Employee Central Update
# | Data Object | Sign-off | Scope | Volume | Status | Validation Process
1 | Basic Import | Anuj Khanna (Sign-off received on 13th Sep 24) | Seconded + Others | 960 | Completed | System pre-load validation Post load download from AI system File comparison between Pre vs Post load SF Portlets validations – select employees SF Reports generation
2 | Formal Education |  | Seconded + Others | 960 | Completed | 
3 | Work Experience |  | Seconded + Others | 960 | Completed | 
4 | Biographical Information |  | Seconded + Others | 960 | Completed | 
5 | Personal Information |  | Seconded + Others | 960 | Completed | 
6 | Contact Information |  | Seconded + Others | 960 | Completed | 
7 | Addresses |  | Seconded + Others | 960 | Completed | 
8 | Emergency Contact |  | Seconded + Others | 960 | Completed | 
9 | National ID Information |  | Seconded + Others | 960 | Completed | 
10 | Employment Details |  | Seconded + Others | 960 | Completed | 
11 | Job Information |  | Seconded + Others | 960 | Completed | 
12 | Position Information |  | Seconded + Others | 960 | Completed | 
13 | Bank information |  | Seconded + Others | 960 | Completed | 
14 | Compensation Information |  | Seconded + Others | 100 | Completed | Dummy values to validate if all components are configured
On Track
Needs Attention
Delayed
Completed
To Start

## Slide 7: Mock 1 – REC & PMGM Update
On Track
Needs Attention
Delayed
Completed
To Start
PMGM Update
REC Update
# | Data Object | Sign-off | Scope | Volume | Status | Validation Process
1 | Candidate Data | Neha Singh, Sunanda Seth, Nidhi Datta (Sign-off received on 4th Sep 24) | NA | 13500 | Completed | System pre-load validation Post load download from AI system File comparison between Pre vs Post load SF Reports generation
# | Data Object | Sign-off | Scope | Volume | Status | Validation Process
1 | APR Forms (PDF) | Madhurima Bhattacharyya (Sign-off received on 4th Sep 24) | Seconded + Others | 100 | Completed | System pre-load validation Post load download from AI system File comparison between Pre vs Post load SF Portlets validations – select employees SF Reports generation
2 | Goal Templates |  |  | 960 |  | 
3 | Performance Ratings |  |  | 960 |  | Dummy data loaded for employees to validate configuration and data load procedures

## Slide 8: Mock 1 – Key Observations
# | Observations | Corrective Action
1 | Foundation objects effective date for historical data was prior to effective start date. Caused errors in Hire date | Effective date corrected at Object level – Config change
2 | Missing associations organization structures for history employee data load | Association validation disabled for history load and enabled post load – data change
3 | Education data multiple duplicate records created | Setting change in SF – Config change
4 | Actual Performance ratings data not received | Dummy data loaded for employees to validate configuration and data load procedures Actual ratings data will be uploaded in Mock 2
5 | Compensation data not received | Dummy values updated against pay components to validate configurations and UK pay component availability in system Actual pay data will be uploaded in Mock 2
6 | Issue due to Delta foundation object creation in production post instance refresh. | Data re-created to enable loads – Data change

## Slide 9: Mock 2 – Employee Central Update
# | Data Object | Sign-off | Scope | Volume | Status | Validation Process
1 | Basic Import | Sign-off Pending Target - 25 Sep 24 | Seconded (1260) + Others (1905) | 3165 | Completed | System pre-load validation Post load download from AI system File comparison between Pre vs Post load SF Portlets validations – select employees
2 | Biographical Information |  | Seconded + Others | 960 | Completed | 
3 | Personal Information |  | Seconded + Others | 960 | Completed | 
4 | Contact Information |  | Seconded + Others | 960 | Completed | 
5 | Addresses |  | Seconded + Others | 960 | Completed | 
6 | Emergency Contact |  | Seconded + Others | 960 | Completed | 
7 | National ID Information |  | Seconded + Others | 960 | Completed | 
8 | Employment Details |  | Seconded + Others | 960 | Completed | 
9 | Job Information |  | Seconded + Others | 960 | Completed | 
10 | Position Information |  | Seconded + Others | 960 | Completed | 
11 | Bank information |  | Seconded + Others | 960 | Completed | 
12 | Compensation Information |  | Seconded + Others | 3165 | Completed | Actual data uploaded. Values and components to be validated.
13 | Leave Data |  | Seconded + Others |  | Not Started | 
On Track
Needs Attention
Delayed
Completed
To Start

## Slide 10: Mock 2 – REC & PMGM Update
On Track
Needs Attention
Delayed
Completed
To Start
PMGM Update
REC Update
# | Data Object | Sign-off | Scope | Volume | Status | Validation Process
1 | Candidate Data |  | NA | Target 100000 Completed 58500 | On Track | 
# | Data Object | Sign-off | Scope | Volume | Status | Validation Process
1 | APR Forms (PDF) |  | Seconded + Others | Yr 23-24 -1820 Yr 22-23 -1539 Yr 21-22 - 1237 | On Track | 
2 | Goal Templates |  |  | In Progress |  | 
3 | Performance Ratings |  |  | Yr 23-24 - 1820 Yr 22-23 - 1539 Yr 21-22 - 1237 Yr 20-21 - 910 Yr 19-20 - 889 |  | 

## Slide 11: Risks – Actions – Issues - Decisions
Category | Type | Description | Impact | Status | Owner | Target Date
Integration Build | Risk | Procure and Provision new payroll instance | H | Completed | Amit (AI) | 05-Sep
Integration Build | Risk | People Strong New payroll Instance configuration In progress. Target to complete and hand for CPI configuration by 3rd Oct 24. | H | Needs Attention | Amit (AI) | 03-Oct
Integration Build | Risk | CPI Build – Three Integration flows for UK pay components will be completed by 18th Oct. Parallel Mock Run on PeopleStrong to be reassessed | H | Needs Attention | Vansh (EY) & Amit (AI) | 18-Oct
Mock 2 | Decision | Half day leave: We will discount the half day leave for UK employees and upload the leave. | H | Completed | Anuj | 
Mock 2 | Decision | Vistara Holiday Calendars & Work Schedule , Time Types are different compared to AI policy Vistara Time policy deployment only for historical data loads will be a challenge Workaround (Custom Portlet for leaves) snapshots to be shared with HR for review & sign-off | H | Needs Attention | Shivender (EY) | 23 Sep
On Track
Needs Attention
Delayed
Completed
To Start

## Slide 12: Mock 2 & UAT Phase: Planned Activities for 20 Sep 2024
# | Milestone | Priority | Plan | Target / Actual | Status | Key accomplishments/ latest status update
1 | Mock 2 Data Loads | High | 20-Sep | 25-Sep | Needs Attention | Data Upload for Leaves Pending
2 | Mock 2 – Data validation | High | 25-Sep |  | On Track | In Progress
3 | UAT Test Execution (End to End) for EC / REC / PMGM | High | 25-Sep |  | On Track | In Progress
4 | RBP Validation | High | 25-Sep |  | On Track | In Progress
5 | Mock 2 and UAT Sign off | High | 25-Sep |  | On Track | Not Started
On Track
Needs Attention
Delayed
Completed
To Start

## Slide 13: Configuration & Cut Over 1: Upcoming Activities for 04 Oct 2024
# | Milestone | Priority | Target date | Status
1 | Migrate all Configurations | High | 01-Oct | Yet to Start
2 | Manual Configuration in Production | High | 03-Oct | Yet to Start
3 | Employee Data - Seconded to AI | High | 04-Oct | Yet to Start
4 | Candidate Data | High | 04-Oct | Yet to Start
On Track
Needs Attention
Delayed
Completed
To Start

## Slide 14: Data Cut Over Plan
Track | Key Activities | Key Dates
Cut Over 1 UK Non - Seconded to AI | Data Cut-off date | 15-Oct-24
 | Data Extraction – Historical Data | 18-Oct-24
 | Data Cleansing / Mapping to SF formats | 25-Oct-24
 | Data Upload in AI Prod | 31-Oct-24
Cut Over 2 UK Seconded to AI Delta for Non - Seconded to AI | Data Cut-off date | 28-Oct-24
 | Data Extraction | 31-Oct-24
 | Data Cleansing / Mapping to SF formats | 07-Nov-24
 | Upload Extract 1 | 10-Nov-24
 | Vistara Instance Black out | 09-Nov-24
 | Delta Data Extraction for Non-Seconded Employees (delta from 15 Oct to 08 Nov) | 09-Nov-24
 | Delta Data Extraction for Seconded to AI Employees (delta from 28 Oct to 08 Nov) | 09-Nov-24
 | Upload Extract 2 (Delta data) | 11-Nov-24
 | UK Employees Transfer Event | 12-Nov-24
 | UK Instance Lock and Release Clone | 14-Nov-24

## Slide 15: 2. Payroll - PeopleStrong

## Slide 16
Payroll Merger Principles & Approach
Merger Guiding Principles
UK Payroll team to process UK employees’ salary in SAP S4 HANA till merger Go-Live. Nov 24 salary processed partially by UK (till 11th Nov 24) & partially by AI (12th Nov 24 onwards); AI to pay one shot salary to UK employees on 30th Nov 24.
UK Crew (Pilots & Cabin) pay components and structures to be harmonized prior to merger Go-Live (12th Nov 24); UK rest of the employee’s pay components & structures to be harmonized post-merger by Mar 2025.
Separate (New) AI PeopleStrong (PS) instance to be configured with UK pay components.
Post-merger, payroll markers & rates for variable pay (flying hours, layover allowance, etc.) for UK & AI Crew will be of AI.
UK Crew to use UK ARMS system till 11th Nov 24, then switch to AI CAE post 11th Nov 24 midnight.
Since merger date is mid-month, following are the guiding principles for 1st-11th Nov payroll calculations for UK Crew:
  For slab-based payroll markers, cumulative logic will apply; for all payroll markers, AI rates & calculation logics to apply for Nov month.
  For guaranteed flying hours, UK Crew to be paid guaranteed flying hours for Nov 24 month in the same month salary payout (Nov 24).
Approach (Plan)
Timeline
May 24
June 24
Sep 24
July 24
Aug 24
Oct 24
Nov 24
Progress
PeopleStrong
Discovery Workshops & End State Agreement
(6th May)
Finalize UK-AI Data Mapping & Transformation requirements
(25th June)
HR to share UK Pay structures & components
(27th June)
Contract Signing of PS License contract
(4th Sep)
End (20th Sep)
Start (6th Sep)
Start
(2nd Oct)
End
(9th Oct)
Historical payroll data migration completion
(31st Oct)
Live Payroll Processing 12th Nov onwards ->
Start
(21st Oct)
End
(28th Oct)
HR Tech System
Start
(23rd Sep)
End (1st Oct)
Merger Documents Sign-off from HR
(4th Sep)
12th NOV
Aug Parallel payroll mock run & data validation
Sep Parallel payroll mock run & data validation
Oct Parallel payroll mock run & data validation
Configuration of UK pay components & structures in AI PS test instance
We are here
23rd Sep
CAE Mock Run Completion
(2nd Oct)
Parallel Run between UK ARMS & AI CAE
(28th Oct to 11th Nov)
-UK Payroll team to share payroll inputs for non-flying & flying components (1st to 11th Nov)
Harmonized employee master, UK roster data upload completion from ARMS to CAE for Live Run
(28th Oct)
-HRIS & BRE configuration completion in new AI PS instance

## Slide 17
Dependencies & Pending Decisions
Dependencies
CAE needs AI employee IDs & email IDs for mock run [Resolved]
UK IFS & Ops to share flying allowance inputs for payroll mock runs & 1st-11th Nov with AI team [Ongoing]
UK IFS & Ops to share details of Forex card allowances with AI team for overlapping period (boarded prior to merger date & landing on or post merger-date scenarios) [Ongoing]

## Slide 18
Payroll (PeopleStrong) – Upcoming Activities
S.No. | Milestone | Priority | Planned Completion | Actual Completion | Status | Comments
1 | New PS Instance Procurement | High | 30-Aug-24 | 4-Sep-24 | Completed | -
2 | HR to share Aug payroll input & Data | High | 9-Sep-24 | 13-Sep-24 | Completed | HR (Anuj Khanna, Ajay Aggarwal) to share following: -Employee Master Data (Shared) -Sample CTC Report (Shared) -Salary Register (Shared) -Tax Computation Sheets (Shared) -Payroll Inputs for Aug (Shared)
3 | Payroll System (Engine) Setup | High | 20-Sep-24 | 20-Sep-24 | Completed | Configuring new AI PS test instance with UK pay components & structures as per UK payroll policies
4 | Mock Run 1 – Aug Payroll Processing* | High | 27-Sep-24 | 27-Sep-24 | In Progress | -
5 | Mock Run 1 – Aug Payroll Sign-off* | High | 1-Oct-24 | 1-Oct-24 | Yet to Start | Validation around Gross salary & tax calculations
6 | HRIS & BRE System Setup | High | 7th Oct 24 | 7th Oct 24 | In Progress | -
7 | Integration with SF Development | High | 10th Oct 24 | 10th Oct 24 | Yet to Start | -
*Mock Run Detailed Plan covered in subsequent slide

## Slide 19
Payroll (PeopleStrong) – Mock Runs (Payroll Parallel Run)
S.No. | Milestone | Priority | Planned Completion | Actual Completion | Status
1 | Payroll Input to be shared by UK HR for Aug | High | 9-Sep-24 | 13-Sep-24 | Completed
2 | Payroll System (Engine) Setup | High | 20-Sep-24 | 20-Sep-24 | Completed
7 | Aug month payroll parallel processing | High | 27-Sep-24 | 27-Sep-24 | In Progress
8 | Aug month payroll validation & sign-off | High | 1-Oct-24 | 1-Oct-24 | Yet to Start
Mock Runs Objective & Validation Criteria
Objective: Ensure accurate payroll transition from SAP S4 HANA to PeopleStrong (PS) for Vistara employees.
Mock Run 1 (Aug) Validation Criteria: Testing – (1) UK employees master data update, (2) Payroll register calculation, (3) UK FBP component on BRE, (4) UK additional allowances which will continue in AI - validation with UK pay register for all UK employees.
Mock Run 2 (Sep) Validation Criteria: Testing – (1) Mock Run 1 observations, (2) Payroll register calculation, (3) UK FBP component on BRE, (4) UK additional allowances, for all UK employees & (5) Tax calculation for a sample set of UK employees (past months investment inputs to be checked manually).
Mock Run 3 (Oct) Validation Criteria: Testing – (1) Mock Run 2 observations, (2) Payroll register calculation, (3) UK FBP component on BRE, (4) UK additional allowances, for all UK employees & (5) Tax calculation for a sample set of UK employees (past months investment inputs to be checked manually).
Mock 1 - Aug Payroll Parallel Run Update

## Slide 20
Payroll (PeopleStrong) – RAID (Risks, Actions, Issues, Decisions)
Type | Description | Impact | Probability of Occurrence | Mitigation Plan | Mitigation Plan Status | Target Date
Risk | Payroll calculations if not vetted correctly may result into wrong payouts to Vistara employees | Medium | Low | -To mitigate, parallel payroll processing mock runs to be done for Aug, Sep months to validate & correct any anomalies prior to merger | In Progress | 16th Oct 24
Risk | Risk of incorrect payouts to harmonized Org employees due to different pay structures for Air India & Vistara employees’ post-merger | Medium | Low | -Ensuring creation of identifier in AI SF to distinguish ex-UK & AI employee post-merger​ -Ensuring PeopleStrong SOP update to do regular audit checks (monthly) prior to processing payroll for the identifier being passed from AI to PS | In Progress | 16th Oct 24
Risk | Issue in reimbursement reconciliation for Vistara employees’ post-merger in case they have already claimed reimbursement in Vistara | Low | Low | -All dues for Vistara employees to be cleared by Vistara payroll team prior to merger Go-Live -Arrears (if any) to be shared by UK team to AI PS team for processing with AI salary payout | In Progress | 30th Oct 24
Risk | Risk of incorrect calculation of taxes since movement of Vistara employees is happening mid-year | Low | Low | -Settlement for Vistara employees will be processed due to closure of PF & issuance of Form 16​ -Gratuity & Leave Encashment to be carried forwarded to AI, to be managed through Tata Group DOJ in PS system​ (to be created in AI SF) -2 Form 16s for Vistara employees to be maintained | In Progress | 30th Oct 24

## Slide 21: 3. Other HR Tech Apps

## Slide 22
Other HR Tech Applications Business Assumptions, Decisions & Open Points
Business Assumptions & Decisions
Learning & Development (TCS iDL & Disprz):
  UK learning history data elements will be migrated by HR Tech team within TCS iDL from UK SuccessFactors (UAT Completion: 31st Oct 24, Full Data Migration: 11th Nov 24)
  No additional licenses are forecasted currently for merged entity for Disprz for FY 24-25; current quota of Disprz licenses are enough & will be re-assigned by AI HR in case of any additional requirements
  Following reconfiguration changes need to be done (ETA: 31st Oct 24):
    Bulk Cool Off Period functionality
    On demand trainings audit trail
    Anonymous survey submission feature
  No data migration to be done from UK e-learning application (currently used by UK engineering team) to AI TCS iDL system – business to keep offline records at their end
Staff Travel (iFly):
  Need to upload a fixed passage quota applicable for remaining FY 24-25 for UK employees’ post-merger basis policy decision taken by AI HR (ETA: 11th Nov 24) along with one time upload of UK employee’s dependent information
  Harmonization of onload priorities for staff travel across all group airlines
Rewards & Recognition (Advantage Club):
  No historical data related to Rewards & Recognition of Vistara employees needs to be migrated to AI Advantage Club
Upcoming Activities
Learning & Development (TCS iDL):
  Learning history migration mock run commenced from 18th Sep 24 – data preparation & upload in progress
  Following learning history data points to be uploaded from UK SuccessFactors LMS to AI TCS iON as part of mock run:
    Past learning records including completed courses information (Name, SAP ID, Course Name, Course Duration, Completion Status, Learning Hours gained for learning history data).
    Past learning certificates in the form of PDFs.

## Slide 23
Merger Documents Sign-off Status
HR Tech Application | Documents | Sign-off Pending with
SuccessFactors – Employee Central & Onboarding | 1. Employee Central & Onboarding - Key Business Assumptions & Decisions 2. Employee Central & Onboarding - Program Plan 3. Employee Central & Onboarding - Data Mapping | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
SuccessFactors – Performance & Goal Management | 1. Performance & Goal Management - Key Business Assumptions & Decisions 2. Performance & Goal Management - Program Plan 3. Performance & Goal Management - Data Mapping | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
SuccessFactors – Recruitment | 1. Recruitment - Key Business Assumptions & Decisions 2. Recruitment - Program Plan 3. Recruitment - Data Mapping | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
PeopleStrong (Payroll) | 1. PeopleStrong - Pay Components Data Field Mapping 2. PeopleStrong - Business Decisions & Assumptions 3. PeopleStrong - Program Plan | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
Advantage Club (R&R) | 1. Advantage Club - Program Plan 2. Advantage Club - Key Business Assumptions & Decisions | 1. Signed by all stakeholders 2. Signed by all stakeholders
TCS iDL & Disprz (Learning & Development) | 1. Learning & Development - Business Decisions & Assumptions 2. Learning & Development - TCS iDL Program Plan 3. Learning & Development - Disprz Program Plan | 1. Signed by all stakeholders 2. Signed by all stakeholders 3. Signed by all stakeholders
iFly (SkyFam) | 1. iFly (SkyFam) - Program Plan 2. iFly (SkyFam) - Key Business Assumptions & Decisions | 1. Abhinav Rajmalwar, Akanksha Jain, Vikrant Bhatnagar 2. Abhinav Rajmalwar, Akanksha Jain, Vikrant Bhatnagar

## Slide 24: Thank You