AI–UK Integration

Track: HR-Tech

Date: 02-Apr-2024

1. Revision History	2

2. Team Matrix	3

3. Overview of Systems for Integration (As Is vs End State)	3

4. System 1. HRMS (SuccessFactors) Integration Strategy	7

1. System Strategy

2. Data Migration Strategy

3. Downstream 3rd Party Integration Strategy

4. Contract Rationalization & Consolidation Strategy

5. System Sunset Strategy

6. Detailed Roadmap Plan

5. System 2. Payroll (PeopleStrong) Integration Strategy	13

1. System Strategy

2. Data Migration Strategy

3. Downstream 3rd Party Integration Strategy

4. Contract Rationalization & Consolidation Strategy

5. System Sunset Strategy

6. Detailed Roadmap Plan

6. System 3. Staff Travel – iFLY Integration Strategy	16

1. System Strategy

2. Data Migration Strategy

3. Downstream 3rd Party Integration Strategy

4. Contract Rationalization & Consolidation Strategy

5. System Sunset Strategy

6. Detailed Roadmap Plan

7. System 4. Learning Management System – TCS iDL, Disprz Integration Strategy	20

1. System Strategy

2. Data Migration Strategy

3. Downstream 3rd Party Integration Strategy

4. Contract Rationalization & Consolidation Strategy

5. System Sunset Strategy

6. Detailed Roadmap Plan

8. System 5. Business Expense Reimbursements – PeopleStrong Integration Strategy	23

1. System Strategy

2. Data Migration Strategy

3. Downstream 3rd Party Integration Strategy

4. Contract Rationalization & Consolidation Strategy

5. System Sunset Strategy

6. Detailed Roadmap Plan

9. System 6. Rewards & Recognition – Advantage Club Integration Strategy	27

1. System Strategy

2. Data Migration Strategy

3. Downstream 3rd Party Integration Strategy

4. Contract Rationalization & Consolidation Strategy

5. System Sunset Strategy

6. Detailed Roadmap Plan

1. Revision History

| Version Number | Date | Department | Changes Made from Previous Version/Remarks |
| --- | --- | --- | --- |
| 2 | 4-Apr-24 | HR Tech | - Added background regarding each HR Tech system in AI & UK respectively – for AI, added brief about system state prior to Tata takeover as well. - Documented list of downstream Tech systems requiring Integration with each HR Tech system in Data Migration strategy for each HR system - Created separate section of ‘Downstream 3rd Party Integration Strategy’ post Data Migration Strategy to capture strategy & milestone plan related to downstream integrations with HR systems |

2. Team Matrix

- Amit Sood (AI – HR Tech)

- Aparna Gupta (AI – HR Tech)

- Kunal Kansra (AI – HR Tech)

- Vikrant Bhatnagar (AI – HR)

- Anuj Khanna (AI – HR)

- Rakesh Dua (UK – IT)

- Sakshi Gera (UK – IT)

- Hemant Patel (UK – HR)

3. Overview of Systems for Integration (As Is vs End State)

- HRMS (SuccessFactors) system:

Before Tata takeover of AI, HRMS tool being used was SAP HR which was implemented in 2013.

Currently, HRMS tool is SuccessFactors (SF) & was implemented in May 2023 for AI employees post takeover. Following modules were implemented – Recruitment, Onboarding, Employee Central, Performance & Goal Management in Phase 1. In Phase 2, Leave module was launched within SF in Oct 24. Compensation, Career Development Planning (CDP), Succession Planning (SP) & Time tracking modules were decided to be onboarded in Phase 3 once Phases 1 & 2 stabilize.

Within UK, HRMS tool is SuccessFactors & was implemented on XX for UK employees. Following modules were implemented – Recruitment, Onboarding, Employee Central, Performance & Goal Management, Compensation, Career Development Planning (CDP) & Succession Planning (SP) over the course of XX years.

| Capability | AI System Availability? (Yes/No) | UK System Availability? (Yes/No) | Target System Capability | Interfaces | Recommended End State System |
| --- | --- | --- | --- | --- | --- |
| Recruitment | Yes | Yes | Recruitment in AI system | 1. Background Verification – AuthBridge, 2. E-Sign - Adobe | -Since this capability is available in both systems & are essential for employee experience, need to have it in Target (end) state system of Integrated Org |
| Onboarding | Yes | Yes | Onboarding in AI system | 1. ID Card Generation | -Since this capability is available in both systems & are essential for employee experience, need to have it in Target (end) state system of Integrated Org |
| Employee Central | Yes | Yes | Employee Central in AI system | 1. Payroll - PeopleStrong 2. Reimbursement – PeopleStrong 3. Staff Travel – iFLY 4. Reward & Recognition – Advantage Club 5. Learning – TCS iDL, Disprz 6. Facial Recognition System 7. S4 HANA 8. CAE (Employee Master & Leave) 9. Move-in Sync 10. Azure AD | -Since this capability is available in both systems & are essential for employee experience, need to have it in Target (end) state system of Integrated Org |
| Performance & Goal Management | Yes | Yes | Performance & Goal Management in AI system | NA | -Since this capability is available in both systems & are essential for employee experience, need to have it in Target (end) state system |
| Compensation, Career Development Planning (CDP), Succession Planning (SP) | No | Yes | -- | NA | -Option 1: Not have Compensation, SP, CDP module in scope of UK-AI integration but implement Compensation, CDP & SP module in AI SF instance (new implementation) in parallel Option 2: Migrate AI employees to UK SF system where Compensation, SP & CDP module already present Option 3: Implement Compensation, CDP & SP module in AI SF instance (new implementation) within scope of integration & migrate UK employee historical data to AI system Recommended: Option 1 Rationale: In interest of integration timelines, we will work on implementation of these as a parallel track & not make it a blocker for integration completion |

- Payroll (PeopleStrong):

Prior to Tata takeover, Payroll system in AI was SAP Payroll which was implemented in 2013.

After Tata takeover, for all new joiners, PeopleStrong was implemented in Apr 2022 for processing payroll. For legacy AI employees, SAP HR Payroll system was being used.

Currently within AI, Payroll tool is PeopleStrong which was implemented for all the employees (Legacy & new joiners) in May 2023 for flying crew & in July 2023 for non-flying crew.

Within UK, Payroll tool is SAP S4 HANA & was implemented on XX for UK employees.

| Capability | AI System Availability? (Yes/No) | UK System Availability? (Yes/No) | Target System Capability | Interfaces | Recommended End State System |
| --- | --- | --- | --- | --- | --- |
| Payroll | Yes | No – Payroll available in SAP | Payroll module within AI instance of PeopleStrong | 1. ARMS/CAE 2. SF | -Option 1: Migrate UK employee data from SAP to AI PeopleStrong (PS) instance & configure Payroll for UK employees in AI PS system Option 2: Migrate AI employee data from AI PS instance to SAP & configure Payroll for AI employees in UK SAP system Recommended: Option 1 Rationale: -As per the management mandate, Payroll needs to be processed via Managed Services Model which is available in PeopleStrong |

- Staff Travel (iFLY) system:

Prior to Tata takeover, Staff Travel process in AI was semi-automated wherein employees could generate RAO through SAP ESS portal.

After Tata takeover, iFLY was implemented in Oct 2023 for Staff Travel needs (Duty Travel, Leisure Travel) of AI employees.

Within UK, Staff Travel tool is an internally developed tool & was implemented on XX for UK employees.

| Capability | AI System Availability? (Yes/No) | UK System Availability? (Yes/No) | Target System Capability | Interfaces | Recommended End State System |
| --- | --- | --- | --- | --- | --- |
| Leisure & Duty Travel Bookings | Yes | No – Internally developed tool used | Travel booking system within AI’s iFLY system | 1. SF 2. Amadeus 3. Payment Gateways | -Option 1: Onboard AI employees on to UK Internal tool for booking Staff Leisure/Duty travel tickets Option 2: Migrate UK employees on to AI iFLY system Recommended: Option 2 Rationale: Since AI’s iFLY system is more robust, mature from a capability point of view (capabilities like Forecast of seat availability, Payment Gateway integration & auto-notifications) & scalable, moving to an Internal tool would not offer the best employee experience within the Integrated Org |

- Learning (TCS iDL & Disprz) system:

Prior to Tata takeover, learning process in AI was manual wherein data used to be maintained in Excel files.

After Tata takeover, TCS iDL & Disprz were implemented in May 2023 for capturing all learning related details.

Within UK, learning tool is SuccessFactors (SF) LMS & was implemented on XX for UK employees.

| Capability | AI System Availability? (Yes/No) | UK System Availability? (Yes/No) | Target System Capability | Interfaces | Recommended End State System |
| --- | --- | --- | --- | --- | --- |
| Learning Management System | Yes | No – LMS available in SF | LMS within AI’s instance of TCS iDL & Disprz | 1. SF | -Option 1: Onboard AI employees on to UK instance of SF - LMS Option 2: Migrate UK employees on to AI TCS iDL & Diprz systems Recommended: Option 2 Rationale: As aligned in workshops done earlier, AI’s TCS iDL & Disprz to be used as end state systems |

- Business Expense Reimbursements (PeopleStrong) system:

Prior to Tata takeover, Business Expense Reimbursement process in AI was manually done.

After Tata takeover, for all new joiners, PeopleStrong was implemented in Apr 2022 for processing Business Expense Reimbursements. For legacy AI employees, manual process was being used.

Currently within AI, Business Expense Reimbursement tool is PeopleStrong which was implemented for all the employees (Legacy & new joiners) in Sep 2023.

Within UK, Business Expense Reimbursement tool is Concur & was implemented on XX for UK employees.

| Capability | AI System Availability? (Yes/No) | UK System Availability? (Yes/No) | Target System Capability | Interfaces | Recommended End State System |
| --- | --- | --- | --- | --- | --- |
| Business Expense Reimbursements Module | Yes | No - Concur | Interim – PeopleStrong (within Integration scope) Final – Concur | 1. SF | -Option 1: Directly move to Concur system for integrated Org Option 2: Migrate to PeopleStrong (As-Is AI system) and subsequently migrate to Concur (New AI implementation) Recommended: Option 2 Rationale: In interest of integration timelines, we will work on implementation of Concur post integration & not make it a blocker for integration completion |

- Rewards & Recognition (Advantage Club – AI Stars) system:

Prior to Tata takeover, limited R&R activities were there in AI which were done manually.

Currently within AI, R&R tool is Advantage Club (AI Stars) which was implemented for all the employees in Sep 2023.

Within UK, R&R tool is not there & process is run manually.

| Capability | AI System Availability? (Yes/No) | UK System Availability? (Yes/No) | Target System Capability | Interfaces | Options & Recommended Strategy |
| --- | --- | --- | --- | --- | --- |
| Rewards & Recognition | Yes | No | AI’s instance of Advantage Club (AI Stars) system | 1. SF | Option 1: Migrate UK employees on to AI’s Advantage Club (AI Stars) system Recommended: Option 1 Rationale: Since UK doesn’t have a tool, we have only option of AI tool for Integrated Org |

4. System 1. HRMS (SuccessFactors) Integration Strategy

System Strategy:

  - We have evaluated following two options for implementing HRMS (SF) system in the Integrated Org:

    - Option 1 (One time activation of UK employees on SF on 28th Oct 12 AM):

      - UK Employees who will move to AI over the next course of 6 months will be on secondment to AI till 27th Oct.

      - Activation of UK employees in AI SF to be done one shot on 28th Oct 12 am.​

      - Historical data of UK employees needs to be migrated well before they are activated on to reconfigured AI systems as employees (Detailed strategy covered in Data Migration Strategy section below)

      - Pros: (1) As per regulatory requirement by DGCA, UK employees cannot be onboarded prior to 27th Oct

(2) Downstream application (Azure AD, CAE, etc.) integration will be seamless & they will complete employee headcount on Go-live date

      - Cons: (1) Data needs to be revalidated for any changes till Go-Live date

      - Open Question/Dependency: Need to review & align with HR on following UK employee experience during secondment stage prior to 28th Oct activation:

        - Determine which policies (travel, BRE, benefits, exit, etc.) will be applicable to UK employees on secondment.

        - Determine where Payroll will be processed for UK employees on secondment.

        - Determine which HR systems (SkyFam, Learning, etc.) will be used for UK employees on secondment.

        - Determine how secondment be converted to AI employees post integration on 28th Oct.

    - Option 2 (Phased wise activation till 28th Oct):

      - UK Employees who will move to AI over the next course of 6 months are activated in a new company code of UK in AI SF instance.

      - Historical data of UK employees is also migrated in a phased manner as & when employees are activated on to AI system.

      - Pros: (1) Data will be latest at the time of phased activation.

      - Cons: (1) Integration with downstream applications (CAE, Azure AD, etc.) will be a challenge since these systems will not have entire headcount on the day of activation of each employee (being done in phased manner)

  - Basis the above options, we are having discussions with the SAP team on the final implementation strategy (Recommended option is Option 1).

  - Detailed System Strategy for SF implementation within the Integrated Org will be finalized with SAP team by 24th Apr 24​.

  - We have begun discussions with HR & expect harmonized Org structure, policies & processes to be shared by HR by 30th Apr 24​.

  - We will do a comparison of current policies & workflows against the Integrated Org structure & policies each for Recruitment, Onboarding, Employee Central, Performance and Goal Management modules to be able to identify where all reconfigurations will be required based on harmonized org policies & processes (Policies Link).

  - We will also list down available integrations with SF in AI system (PS, iFLY, TCS iDL, etc.) & required integrations within the Integrated Org.

  - Once the comparison is done & exact workflows and integrations are identified, AI SF instance will be reconfigured in Test instance by 31st July 24​.

  - We will do thorough testing (FUT, SIT & UAT) of integrated SF instance to validate reconfigurations & workflows basis UK & AI integrated policies by 25th Aug 24.

  - We will do Production movement of reconfigured AI SF & perform sanity tests on Production by 15th Sep 24.

  - We will do full data migration by 22nd Oct 24.

  - User training, train the trainer and new user manual/SOP creation to be done by 31st Oct 24 to ensure adoption to the reconfigured system.

Data Migration Strategy:

  - We have identified following data points specific to HRMS (SF) system which we will need to migrate from UK SF instance to AI SF instance to ensure there is no break in the experience of UK employees migrating to AI:

    - Recruitment & Onboarding:

      - Cutover date for hiring freeze at least 3 months before Go-Live

      - Talent pool needs to be migrated

      - All offer letters and candidate documents (PAN, Adhar, Education details, Previous Employment Letters, etc.)

      - Onboarding data (PF & Gratuity Nomination forms, etc.)

    - Employee Central:

      - Harmonized Org Structure (Reporting Manager, Function, Department, Section, Sub-Section, Role, Designation, Location, Grade, Cost Centre)

      - Basic & Personal (Biographical, Global information) information

      - Education information

      - Contact information

      - Emergency Contact & Dependents information

      - National IDs & Personal Documents information

      - Employment details

      - Job Information (Status, Manager Details, Role, Designation, Emp Category, Emp Class, Probation Status, AEP Expiry Date, ATPL, CPL, FRRO, FRTO, RTR License Details, Line Release Date, Training Completion Date, Contract Details, PIC Endorsement Date, Retirement Date)

      - Job Relationship Information (HRBP Details, Matrix Manager Details)

      - Organization Information (Position Details, Org Structure – Company, Function, Dept, Section & Sub-section, Hub, Location Group, Location, Time Zone, Cost Centre)

      - Previous Job information

      - Awards & Honors, Courses & certification information

      - Language skills & Mobility information

      - Professional Memberships & Community/Volunteer information

      - Leave Details - Opening Balance for PL, SL & CL; Existing leave details for LWP, Maternity & Paternity cases

      - Compensatory Off Information

      - Training Bond Agreement Information

      - Advanced Salary Information

      - Relative Details in Air India

      - Compensation Information & Pay structure (All CTC pay components like Basic, HRA, Variable, Deductions, etc. with details)

      - Bank Information

      - Document Repository

      - Exit clearances information (IT clearance, Assets clearance, Admin clearance, HR clearance, Manager clearance, etc.)

    - Performance & Goal Management:

      - Past Performance Rating history information

      - Talent Profile Overview Information (Overall, Potential, Competency, etc.)

      - Performance & Potential Trend Information (Performance Rating Trend, Potential Rating Trend, etc.)

      - Merits & Demerits history Information (if applicable)

  - We will export all data as per above data elements from UK SF instance.

  - We will cleanse data & rearrange the data as per AI SF upload templates by 16th Aug 24.

  - We will perform two data upload mock runs in test instance of AI SF over a window of 15 days post 16th Aug 24.

  - We will do FUT, SIT testing to ensure that the data is correctly migrated from UK SF to AI SF & any anomalies can be corrected prior to UAT by end users.

  - We will do full UK employees' data migration by 22nd Oct 24 prior to activation on the AI system ​on 28th Oct 24, 12 am.

  - UK employees will be activated on AI SF one-shot at 12 am on 28th Oct 24.

  - Dependencies/Decision Points:

    - We need to discuss & align with HR on decision to migrate only active employee data or even inactive employee data.

    - We need to ascertain what is the time period for which historical data needs to be pulled from UK SF instance for both active & inactive employees.

    - We need to ascertain if there will be any changes in existing HR policies and Structure​ for Integrated Org.

    - We need to ascertain decision on using New/Old emp ID of Vistara employees​.

    - We need to ascertain processes & policies for UK employees during secondment period.

    - We need to ascertain if UK employees’ tenure to be considered or they need to be considered as new employees.

    - We need to ascertain decision on past documents to migrated or not & timeline of past data to be migrated.

  - Assumptions:

    - Revised Integrated Org structure with Functions, Departments, Grades, Designations, Roles etc. & revised policies (if any) will be provided by 30th Apr 24​.

    - Employees to be onboarded to AI on 27th Oct EOD one shot prior to which UK employees to be on secondment​.

  - Additional discussion points with vendor:

    - Module licenses procured by UK SF instance and not by AI, needs to be re-negotiated and revised contract to be finalized.

    - Need to confirm with SAP team if data migration can happen before actual activation in SF.

Downstream 3rd Party Integration Strategy:

  - Since there are multiple integrations existing already in AI SF between SF & other HR tools (SkyFam, Payroll, LMS, etc.), we will do a synchronization between SF & integrated system (3rd party) between 23rd Oct 24 & 30th Oct 24.

  - We will activate 3rd party integrations with following systems between 23rd Oct 24 & 30th Oct 24:

    - Azure AD

    - S4 HANA

    - CAE - CM

    - Corusun

    - Move-In Sync

    - Auto Email ID Creation & Deactivation

    - ID Card Creation

    - Facial Recognition

    - Adobe

- 3rd Party Integration Strategy Plan:

| S.No.​ | Summary​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | Identify 3rd Party integrations with AI SF | Done | AI | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Identify 3rd Party integrations with UK SF | To Do | UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Identify common integration points & potential conflicts to create mitigation plan | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Map out data migration timelines within SF alongside downstream integration points for both AI & UK | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Alignment discussion kick-off between HR Tech team & 3rd party downstream system owners | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Alignment closure on synchronized data migration roadmap plan between HR Tech & 3rd party downstream system owners | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Plan testing activities between HR Tech & 3rd party downstream systems to align with integration steps | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Validate downstream integrations post data migration to ensure seamless operations | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Coordinate deployment activities & timelines between HR Tech & 3rd party downstream systems | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Full UK employees’ data migration from UK SF to AI SF | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | Sanity testing of data flowing into 3rd party integrated systems | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 12​ | Post data migration support to be provided by HR Tech team | To Do | AI + UK | ​ | ​ | ​ | ​ | ​ | ​ | ​ |

Contract Rationalization & Consolidation Strategy:

  - We will revisit UK’s & AI’s SF license contract for scope of renegotiation based on increased volumes of Integrated Org​.

  - We will merge SF AMS partner contract for UK and AI –

    - Option 1 is to continue with current AI SF AMS partner & extend the contract to UK employees

    - Option 2 is to move to another SF AMS partner & negotiate contract for the Integrated Org

    - Recommended Option: Option 2

    - Rationale: Decision is basis the unsatisfactory historical performance record of current AMS partner with AI; hence moving to another partner for integrated Org

  - Decision Points:

    - We will review AI & UK SF contracts to decide if migrating UK SF to AI SF license is more beneficial commercially or vice-versa.

System Sunset Strategy:

  - We will migrate all UK employee's data from UK SF Instance to AI SF Instance by 22nd Oct 24.​

  - Decision Point:

    - We will review scope of historical data to be migrated –

      - Option 1: Migrate entire historical data of UK employees for entire past duration.

      - Option 2: Migrate specific employee historical data for a certain duration in past.

  - We will review the timeline till which UK SF instance needs to be kept active post 28th Oct 24, 12 am & determine the sunset timeline accordingly by 30th Apr 24.

- Detailed Roadmap Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | SAP Team (OEM) Kick Off Discussion​ | Assessment and Planning Track​ | In Progress​ | AI + SAP​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Understand HR processes, policies & requirements of integrated Org​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Overall Integration & Data Migration Strategy Option Finalization with SAP team (OEM) Buy-In​ | Assessment and Planning Track​ | To Do​ | AI + SAP​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Contract review to identify duplicate contracts, overlapping services or scope of renegotiation​ | Contract Rationalization Track​ | To Do​ | AI + SAP​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Merging of SF AMS partner contract for UK and AI​ | Contract Rationalization Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Review data governance policies including correct access control for integrated Org​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Receiving of Harmonized Org Structure & policies from HR​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Identify the scope of data to be migrated (personal, educational, job info, leave data, past rating history, employment history, etc.)​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Finalize data mapping and transformation requirements between the existing data structures and SuccessFactors data models​ | Reconfiguration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Reconfigure AI instance settings, workflows and security based on the harmonized structure and policies for RCM, Onb, WFM modules​ | Reconfiguration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | Develop integrations with other systems, such as Payroll, LMS, to ensure data consistency and synchronization​ | Reconfiguration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 12​ | Data Cleansing & Templates creation for data migration​ | Data Migration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 13​ | FUT & SIT to validate Configuration & data migration​ | Reconfiguration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 14​ | UAT to validate the Configuration & data migration from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 15​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 16​ | Production Movement​ | Production Deployment Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 17​ | Full UK Employee Data Migration​ | Data Migration Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 18​ | Sanity testing for configurations, workflows & full UK employee data migration​ | Production Deployment Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 19​ | User training, train the trainer and new user manual/SOP creation​ | Post Deployment activities Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 20​ | Conduct training sessions to familiarize users with the re-implemented SF system​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 21​ | SF employee activation on the date of Go-Live​​ | Post Deployment activities Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 22​ | Set up monitoring process post deployment & gather feedback from end user​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 23​ | Pushing data to integrated system (3rd party) ​- iFLY, AI Stars, TCS iDL, Disprz, PS​ | Post Deployment activities Track​ | To Do​ | AI + TBD​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 24​ | Archiving data and shutting down the instance​ | Sunset UK Instance Track​ | To Do​ | AI + SAP​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |

5. System 2. Payroll (PeopleStrong) Integration Strategy

- System Strategy:

  - We have evaluated following two options with respect to end state system strategy for Payroll system in the Integrated Org:

    - Option 1 (Payroll for secondment UK employees in PeopleStrong):

      - UK Employees who will move to AI over the next course of 6 months will be on secondment to AI till 27th Oct.

      - Payroll processing for UK employees during secondment to be done via PS​.

      - Pros: (1) Payroll processing through single system for both AI & UK employees prior to 27th Oct EOD.

      - Cons: (1) Payroll processing for UK employees if done through PS could be against the merger guidelines of keeping separate entities prior to 27th Oct EOD.

    - Option 2 (Payroll for secondment UK employees in SF but in PS post 27th Oct EOD):

      - Payroll processing for UK employees on secondment with AI prior to 27th Oct EOD to be done via UK SF instance.

      - Post 27th Oct EOD, UK employees to be onboarded on to AI SF instance.

      - Payroll for UK employees to be done via AI PS instance post AI SF integration on 27th Oct EOD.

      - Pros: (1) Payroll processing via SF for UK employees on secondment prior to 27th Oct EOD will ensure compliance to merger guidelines

      - Cons: (1) Employee experience related to Payroll processes would be different for AI & secondment UK employees prior to 27th Oct EOD

  - Basis the above options, we are having discussions with the PeopleStrong (PS) team on the merits & demerits of the above options (Recommended Option is Option 2).

  - Detailed System Strategy for Payroll implementation in PS within the Integrated Org will be finalized with PS team by 24th Apr 24​.

  - We have begun discussions with HR & expect harmonized compensation structure, payroll policies & processes to be shared by HR by 30th Apr 24​.

  - We will do a comparison of current policies & workflows against the finalized compensation structure & payroll policies to be able to identify where all reconfigurations will be required based on harmonized payroll policies & processes (Policies Link).

  - We will also list down available integrations with PS in AI system (SF, ARMS, CAE) & required integrations within the Integrated Org.

  - Once the comparison is done & exact workflows and integrations are identified, AI PS instance will be reconfigured in Test instance by 31st July 24​.

  - We will do thorough testing (FUT, SIT & UAT) of integrated PS instance to validate reconfigurations & workflows basis UK & AI integrated payroll policies by 25th Aug 24.

  - We will run parallel payroll for UK employees for Aug & Sep 24 in UK SAP system & AI PS system & check for anomalies.

  - We will do Production movement of reconfigured AI PS & perform sanity tests on Production by 15th Sep 24.

  - We will do full data migration (detailed covered in below section) in PS by 22nd Oct 24.

  - User training, train the trainer and new user manual/SOP creation to be done by 31st Oct 24 to ensure adoption to the reconfigured system.

- Data Migration Strategy:

  - We have identified following data points specific to Payroll (PS) system which we will need to migrate from UK SAP instance to AI PS instance to ensure there is no break in the experience of UK employees migrating to AI:

    - Basic & Personal Information

    - Job Information

    - Pay components Information (Basic, HRA, Variable, Other Allowances)

    - Deduction components Information

    - Pay frequencies Information (Flying pay could be at a different frequency compared to Non-flying)

    - CTC structures Information

    - Tax Information

    - Bank details Information

    - Historical Compensation Data (Form 16, Salary Slips, CTC statements)

  - We will export all data as per above data elements from UK SAP instance.

  - We will cleanse data & rearrange the data as per AI PS upload templates by 16th Aug 24 for specific data elements like Form 16, Payslips, tax information, deductions not available in AI SF (other data elements to be pushed from AI SF directly).

  - We will run parallel payroll for UK employees for Aug & Sep 24 in UK SAP system & AI PS system & check for anomalies.

  - We will do FUT, SIT testing to ensure that the data is correctly migrated from UK SF to AI PS & any anomalies can be corrected prior to UAT by end users.

  - We will do full UK employees' data migration by 24th Oct 24 (post SF data migration on 22nd Oct) prior to activation on the AI PS system ​on 28th Oct 24, 12 am.

  - UK employees will be activated on AI PS one-shot at 12 am on 28th Oct 24.

  - In order to ensure the end user adoption is high, strategy is to create User training docs, train the trainer docs & SOPs by 31st Oct 24.

  - Dependency/Decisions:

    - Need to ascertain with HR if there are any changes in payroll components & payroll policies within the Integrated Org

    - Need to ascertain with HR what payroll processing process to be followed for UK employees moving on secondment to AI prior to activation on 28th Oct 12 am.

    - Testing in PeopleStrong is dependent on AI SF data migration testing – strategy is to ensure SF data migration testing is done well before PS testing to allow room for mitigating risks associated with any anomalies found.

  - Assumptions:

    - Revised payroll components & policies will be shared by 30th Apr 24.

- Downstream 3rd Party Integration Strategy:

  - Since there are multiple integrations existing already in AI PS between PS & other HR tools (CAE/ARMS), we will do a synchronization between PS & integrated system (3rd party) between 24th Oct 24 & 30th Oct 24.

  - 3rd Party Integration Milestone Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | Identify 3rd Party integrations with AI PS | Done | AI |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Identify 3rd Party integrations with UK PS | To Do | UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Identify common integration points & potential conflicts to create mitigation plan | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Map out data migration timelines within PS alongside downstream integration points for both AI & UK | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Alignment discussion kick-off between HR Tech team & 3rd party downstream system owners | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Alignment closure on synchronized data migration roadmap plan between HR Tech & 3rd party downstream system owners | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Plan testing activities between HR Tech & 3rd party downstream systems to align with integration steps | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Validate downstream integrations post data migration to ensure seamless operations | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Coordinate deployment activities & timelines between HR Tech & 3rd party downstream systems | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Full UK employees’ data migration from UK SF to AI SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11 | Testing of data flowing correctly into AI PS | To Do | AI + UK |  |  |  |  |  |  |  |  |
| 12​ | Sanity testing of data flowing into 3rd party integrated systems | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 13​ | Post data migration support to be provided by HR Tech team | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |

- Contract Rationalization & Consolidation Strategy:

  - ​We will revisit AI’s PS license contract for renegotiation on commercial terms basis increased volumes.

  - We will procure additional PS licenses for UK employees.

  - Assumption:

    - SAP license & contract of UK employees will be terminated & contracts within PS AI to be extended for UK employees.

  - We will continue with PS team as AMS partner for UK and AI –

    - Option 1 is to continue with current AI PS AMS partner & extend the contract for UK employees.

    - Option 2 is to move to another SF AMS partner & negotiate contract for the Integrated Org

    - Recommended Option: Option 1

    - Rationale: Decision is basis the satisfactory historical performance record of current AMS partner with AI along with Managed Shared Services Model available with current partner; hence moving to another partner for integrated Org would not make sense

- System Sunset Strategy:

  - We will migrate all UK employee's data from UK SAP Instance to AI PS Instance by 30th Sep 24​

  - We will review scope of historical data to be migrated –

    - Option 1: Migrate entire historical data of UK employees for entire past duration.

    - Option 2: Migrate specific employee historical data for a certain duration in past​.

  - We will review the timeline till which UK SAP instance needs to be kept active post 28th Oct 24, 12 am & determine the sunset timeline accordingly by 30th Apr 24.

- Detailed Roadmap Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | PeopleStrong (OEM) Kick Off Discussion​ | Assessment and Planning Track​ | In Progress​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Understand HR processes, policies & requirements of integrated Org​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Overall Integration & Data Migration Strategy Option Finalization with PS team (OEM) Buy-In​ | Assessment and Planning Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Contract review to identify scope of renegotiation​ | Contract Rationalization Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Review data governance policies including correct access control for integrated Org​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Receiving of Harmonized Org Structure & Compensation/Payroll Policies from HR​ | Reconfiguration Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Identify the scope of data to be migrated (history, personal & employment details, pay components, pay frequency, CTC structure, tax information, bank details, etc.)​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Finalize data mapping and transformation requirements between the existing data structures and PS data models​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Reconfigure AI instance settings, workflows, and security based on the harmonized structure and policies for Payroll modules​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | FUT & SIT to validate configured PS changes​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 12​ | UAT to validate the configurations & workflows from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 13​ | FUT & SIT to validate data migration​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 14​ | UAT to validate the data migration from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 15​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 16​ | Configuration movement in Production​ | Production Deployment Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 17​ | SF Data Migration Completion​ | Production Deployment Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 18​ | Full UK Employee Data Migration in PS​ | Data Migration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 19​ | Sanity testing for configurations & workflows​ | Production Deployment Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 20​ | Sanity Testing for full UK employee data migration​ | Data Migration Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 21​ | User training, train the trainer and new user manual/SOP creation​ | Post Deployment activities Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 22​ | Conduct training sessions to familiarize users with the re-implemented PS system​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 23​ | UK Employees to be given PS access on the date of Go-Live​​ | Post Deployment activities Track​ | To Do​ | AI + PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 26​ | Set up monitoring process post deployment & gather feedback from end user​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 27​ | Archiving data and shutting down the instance​ | Sunset UK Instance Track​ | To Do​ | AI + SAP​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |

6. System 3. Staff Travel – iFLY Integration Strategy

- System Strategy:

  - We have evaluated following two options with respect to end state system strategy for iFLY system in the Integrated Org:

    - Option 1 (Staff Travel for secondment UK employees in iFLY)

      - UK Employees who will move to AI over the next course of 6 months will be on secondment to AI till 27th Oct.

      - Any Staff Travel booking for UK employees during secondment to be done through iFLY

      - These employees will be onboarded in iFLY and will follow AI Staff Travel polices

      - Pros: (1) Staff Travel through single system for both AI & UK employees prior to 27th Oct EOD.

      - Cons: (1) Staff travel for UK employees if done through iFLY could be against the merger guidelines of keeping separate entities prior to 27th Oct EOD.

    - Option 2 (Staff travel for secondment UK employees through existing UK Staff Travel system and in iFLY post 27th Oct EOD):

      - Staff travel bookings for UK employees on secondment with AI prior to 27th Oct EOD to be done via UK Staff travel tool

      - Post 27th Oct EOD, UK employees to be onboarded on to iFLY

      - Staff Travel for UK employees to be done via AI iFLY instance post integration on 27th Oct EOD.

      - Pros: (1) Staff travel bookings via UK Staff travel tool for UK employees on secondment prior to 27th Oct EOD will ensure compliance to merger guidelines

      - Cons: (1) Employee experience related to Staff Travel would be different for AI & secondment UK employees prior to 27th Oct EOD

  - Basis the above options, we are having discussions with the iFLY team on the merits & demerits of the above options.

  - Detailed System Strategy for Staff Travel implementation in iFLY within the Integrated Org will be finalized by 24th Apr 24​.

  - We have begun discussions with HR & expect harmonized compensation structure, Staff travel policies & processes to be shared by HR by 30th Apr 24​.

  - We will do a comparison of current policies & workflows against the finalized Staff travel policies to be able to identify where all reconfigurations will be required based on harmonized policies & processes (Policies Link).

  - We will also list down available integrations with iFLY in AI system (SF) & required integrations within the Integrated Org.

  - Once the comparison is done & exact workflows and integrations are identified, AI iFLY instance will be reconfigured in Test instance by 31st July 24​.

  - We will do thorough testing (FUT, SIT & UAT) of integrated iFLY instance to validate reconfigurations & workflows basis UK & AI integrated Staff Travel policies by 25th Aug 24.

  - We will do Production movement of reconfigured AI iFLY & perform sanity tests on Production by 15th Sep 24.

  - We will do full data migration (detailed covered in below section) in iFLY by 22nd Oct 24.

  - User training, train the trainer and new user manual/SOP creation to be done by 31st Oct 24 to ensure adoption to the reconfigured system.

- Data Migration Strategy:

  - We have identified following data points specific to iFLY system which we will need to migrate from UK Travel tool to AI iFLY instance to ensure there is no break in the experience of UK employees migrating to AI:

    - Basic & Personal Information

    - Employment Information

    - Pending Passages from UK (if any) as per Harmonized Policy

    - Reporting Manager Details

  - We will export all data as per above data elements from UK Flight Travel tool instance.

  - We will cleanse data & rearrange the data as per AI iFLY upload templates by 16th Aug 24.

  - We will do FUT, SIT testing to ensure that the data is correctly migrated from UK Staff Travel Tool to AI iFLY & any anomalies can be corrected prior to UAT by end users.

  - We will do full UK employees' data migration by 24th Oct 24 (post SF data migration on 22nd Oct) prior to activation on the AI iFLY system ​on 28th Oct 24, 12 am.

  - UK employees will be activated on AI iFLY one-shot at 12 am on 28th Oct 24.

  - In order to ensure the end user adoption is high, strategy is to create User training docs, train the trainer docs & SOPs by 31st Oct 24.

  - Dependency/Decisions:

    - Need to ascertain with HR if there are any changes in Staff Travel policies within the Integrated Org

    - Need to ascertain with HR what Staff Travel process to be followed for UK employees moving on secondment to AI prior to activation on 28th Oct 12 am.

    - Testing in iFLY is dependent on AI SF data migration testing – strategy is to ensure SF data migration testing is done well before iFLY testing to allow room for mitigating risks associated with any anomalies found.

  - Assumptions:

    - Revised Staff Travel policies will be shared by 30th Apr 24.

- Downstream 3rd Party Integration Strategy:

- Since there are integrations existing already in AI iFLY between iFLY & other HR tools (SF), we will do a synchronization between PS & integrated system (3rd party) between 24th Oct 24 & 30th Oct 24.

- 3rd Party Integration Milestone Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | Identify 3rd Party integrations with AI iFLY | Done | AI |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Identify common integration points & potential conflicts to create mitigation plan | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Map out data migration timelines within iFLY alongside SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Finalization on synchronized data migration roadmap plan between iFLY & SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Plan testing activities between iFLY & SF to align with integration steps | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Validate integrations post data migration to ensure seamless operations | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Coordinate deployment activities & timelines between iFLY & SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Full UK employees’ data migration from UK SF to AI SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Testing of data flowing correctly into AI iFLY | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Sanity testing of data flowing into 3rd party integrated systems | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | Post data migration support to be provided by HR Tech team | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |

- Contract Rationalization & Consolidation Strategy:

  - ​We will revisit AI’s iFLY license contract for renegotiation on commercial terms basis increased volumes.

  - We will procure additional iFLY licenses for UK employees.

  - Assumption:

    - Any license & contract of UK employees internal Staff Travel tool will be terminated & contracts within iFLY AI to be extended for UK employees.

  - We will continue with iFLY team (iBIS) as AMS partner for UK and AI –

    - Option 1 is to continue with current AMS partner & extend the contract for UK employees.

    - Option 2 is to move to another AMS partner & negotiate contract for the Integrated Org

    - Recommended Option: Option 1

    - Rationale: Decision is basis the satisfactory historical performance record of current AMS partner with AI; hence moving to another partner for integrated Org would not make sense

- System Sunset Strategy:

  - We will migrate all UK employee's data from UK Staff Travel tool Instance to AI iFLY Instance by 30th Sep 24​

  - We will review scope of historical data to be migrated –

    - Option 1: Migrate entire historical data of UK employees for entire past duration.

    - Option 2: Migrate specific employee historical data for a certain duration in past​.

  - We will review the timeline till which UK Internal Tool instance needs to be kept active post 28th Oct 24, 12 am & determine the sunset timeline accordingly by 30th Apr 24.

- Detailed Roadmap Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | iFLY (OEM) Kick Off Discussion​ | Assessment and Planning Track​ | In Progress​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Understand HR processes, policies & requirements of integrated Org​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Contract review to identify scope of renegotiation​ | Contract Rationalization Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Gap Analysis between UK instance & AI existing iFLY instances and harmonized Org's requirement​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Overall Integration & Data Migration Strategy Option Finalization with iFLY team (OEM) Buy-In​ | Assessment and Planning Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Review data governance policies including correct access control for integrated Org​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Receiving of Harmonized Org Structure & Policies from HR​ | Reconfiguration Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Identify the scope of data to be migrated (pending passages as per policy, personal details, employment details, manager details, etc.)​​ | Reconfiguration Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Finalize data mapping and transformation requirements between the existing data structures and iFLY data models​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Reconfigure AI instance settings, workflows, and security based on the harmonized structure and policies for iFLY modules​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | FUT & SIT to validate configured iFLY changes​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 12​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 13​ | UAT to validate the configurations & workflows from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 14​ | FUT & SIT to validate data migration​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 15​ | UAT to validate the data migration from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 16​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 17​ | Configuration movement in Production​ | Production Deployment Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 18​ | SF Data Migration Completion​ | Production Deployment Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 19​ | Full UK Employee Data Migration in iFLY Tool​ | Data Migration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 20​ | Sanity testing for configurations & workflows​ | Production Deployment Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 21​ | Sanity Testing for full UK employee data migration​ | Data Migration Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 22​ | User training, train the trainer and new user manual/SOP creation​ | Post Deployment activities Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 23​ | Conduct training sessions to familiarize users with the re-implemented iFLY system​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 24​ | UK Employees to be given iFLY access on the date of Go-Live​​ | Post Deployment activities Track​ | To Do​ | AI + IBS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 25 | Set up monitoring process post deployment & gather feedback from end user​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 28 | Archiving Data & shutting down the UK tool | Sunset UK Instance Track | To Do | AI + UK |  |  |  |  |  |  |  |

7. System 4. Learning Management System – TCS iDL, Disprz Integration Strategy

- System Strategy:

  - We have evaluated following two options with respect to end state system strategy for TCS iDL & Disprz system in the Integrated Org:

    - Option 1 (LMS for secondment UK employees in TCS iDL & Disprz)

      - UK Employees who will move to AI over the next course of 6 months will be on secondment to AI till 27th Oct.

      - Any trainings for UK employees during secondment to be done through TCS iDL & Disprz

      - These employees will be onboarded in TCS iDL & Disprz and will follow AI LMS polices

      - Pros: (1) LMS through single system for both AI & UK employees prior to 27th Oct EOD.

      - Cons: (1) LMS for UK employees if done through TCS iDL & Disprz could be against the merger guidelines of keeping separate entities prior to 27th Oct EOD.

    - Option 2 (LMS for secondment UK employees through existing UK SF LMS and in TCS iDL & Disprz post 27th Oct EOD):

      - LMS for UK employees on secondment with AI prior to 27th Oct EOD to be done via UK SF LMS tool.

      - Post 27th Oct EOD, UK employees to be onboarded on to TCS iDL & Disprz

      - LMS for UK employees to be done via AI TCS iDL & Disprz instance post integration on 27th Oct EOD.

      - Pros: (1) LMS via UK SF for UK employees on secondment prior to 27th Oct EOD will ensure compliance to merger guidelines

      - Cons: (1) Employee experience related to LMS would be different for AI & secondment UK employees prior to 27th Oct EOD

  - Basis the above options, we are having discussions with the TCS iDL & Disprz team on the merits & demerits of the above options.

  - Detailed System Strategy for LMS implementation in TCS iDL & Disprz within the Integrated Org will be finalized by 24th Apr 24​.

  - We have begun discussions with HR & expect harmonized compensation structure, LMS policies & processes to be shared by HR by 30th Apr 24​.

  - We will do a comparison of current policies & workflows against the finalized LMS policies to be able to identify where all reconfigurations will be required based on harmonized policies & processes (Policies Link).

  - We will also list down available integrations with TCS iDL & Disprz in AI system (SF) & required integrations within the Integrated Org.

  - Once the comparison is done & exact workflows and integrations are identified, AI TCS iDL & Disprz instance will be reconfigured in Test instance by 31st July 24​.

  - We will do thorough testing (FUT, SIT & UAT) of integrated TCS iDL & Disprz instance to validate reconfigurations & workflows basis UK & AI integrated LMS policies by 25th Aug 24.

  - We will do Production movement of reconfigured AI TCS iDL & Disprz & perform sanity tests on Production by 15th Sep 24.

  - We will do full data migration (detailed covered in below section) in TCS iDL & Disprz by 22nd Oct 24.

  - User training, train the trainer and new user manual/SOP creation to be done by 31st Oct 24 to ensure adoption to the reconfigured system.

- Data Migration Strategy:

  - We have identified following data points specific to TCS iDL & Disprz system which we will need to migrate from UK Travel tool to AI TCS iDL & Disprz instance to ensure there is no break in the experience of UK employees migrating to AI:

    - Basic & Personal Information

    - Job Information

    - Learning History Information (Courses, Trainings)

    - Course Material Information

    - Competencies Gained Information

  - We will export all data as per above data elements from UK SF LMS instance.

  - We will cleanse data & rearrange the data as per AI TCS iDL & Disprz upload templates by 16th Aug 24.

  - We will do FUT, SIT testing to ensure that the data is correctly migrated from UK SF to AI TCS iDL & Disprz & any anomalies can be corrected prior to UAT by end users.

  - We will do full UK employees' data migration by 24th Oct 24 (post SF data migration on 22nd Oct) prior to activation on the AI TCS iDL & Disprz system ​on 28th Oct 24, 12 am.

  - UK employees will be activated on AI TCS iDL & Disprz one-shot at 12 am on 28th Oct 24.

  - In order to ensure the end user adoption is high, strategy is to create User training docs, train the trainer docs & SOPs by 31st Oct 24.

  - Dependency/Decisions:

    - Need to ascertain with HR if there are any changes in LMS policies within the Integrated Org

    - Need to ascertain with HR what LMS process to be followed for UK employees moving on secondment to AI prior to activation on 28th Oct 12 am.

    - Testing in TCS iDL & Disprz is dependent on AI SF data migration testing – strategy is to ensure SF data migration testing is done well before PS testing to allow room for mitigating risks associated with any anomalies found.

  - Assumptions:

    - Revised LMS policies will be shared by 30th Apr 24.

- Downstream 3rd Party Integration Strategy:

  - Since there are integrations existing already in AI between TCS iDL & Disprz & other HR tools (SF), we will do a synchronization between TCS iDL & Disprz & integrated system (3rd party) between 24th Oct 24 & 30th Oct 24.

  - 3rd Party Integration Milestone Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | Identify 3rd Party integrations with AI TCL iDL & Disprz | Done | AI |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Identify common integration points & potential conflicts to create mitigation plan | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Map out data migration timelines within TCL iDL & Disprz alongside SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Finalization on synchronized data migration roadmap plan between TCL iDL & Disprz & SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Plan testing activities between TCL iDL & Disprz & SF to align with integration steps | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Validate integrations post data migration to ensure seamless operations | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Coordinate deployment activities & timelines between TCL iDL & Disprz & SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Full UK employees’ data migration from UK SF to AI SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Testing of data flowing correctly into AI TCL iDL & Disprz | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Sanity testing of data flowing into 3rd party integrated systems | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | Post data migration support to be provided by HR Tech team | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |

- Contract Rationalization & Consolidation Strategy:

  - ​We will revisit AI’s TCS iDL & Disprz license contract for renegotiation on commercial terms basis increased volumes.

  - We will procure additional TCS iDL & Disprz licenses for UK employees.

  - Assumption:

    - SF license & contract of UK employees will be terminated & contracts within TCS iDL & Disprz AI to be extended for UK employees.

  - We will continue with PS team as AMS partner for UK and AI –

    - Option 1 is to continue with current AMS partner & extend the contract for UK employees.

    - Option 2 is to move to another AMS partner & negotiate contract for the Integrated Org

    - Recommended Option: Option 1

    - Rationale: Decision is basis the satisfactory historical performance record of current AMS partner with AI; hence moving to another partner for integrated Org would not make sense

- System Sunset Strategy:

  - We will migrate all UK employee's data from UK SF Instance to AI TCS iDL & Disprz Instance by 30th Sep 24​

  - We will review scope of historical data to be migrated –

    - Option 1: Migrate entire historical data of UK employees for entire past duration.

    - Option 2: Migrate specific employee historical data for a certain duration in past​.

  - We will review the timeline till which UK SF instance needs to be kept active post 28th Oct 24, 12 am & determine the sunset timeline accordingly by 30th Apr 24.

- Detailed Roadmap Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | TCS iDL & Disprz (OEM) Kick Off Discussion​ | Assessment and Planning Track​ | In Progress​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Understand HR processes, policies & requirements of integrated Org​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Contract review to identify scope of renegotiation​ | Contract Rationalization Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Gap Analysis between UK SF & AI existing TCL iDL & Disprz instances and harmonized Org's requirement​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Overall Integration & Data Migration Strategy Option Finalization with TCS iDL & Disprz team (OEM) Buy-In​ | Assessment and Planning Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Review data governance policies including correct access control for integrated Org​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Receiving of Harmonized Org Structure & Policies from HR​ | Reconfiguration Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Identify the scope of data to be migrated (learning history, personal details, employment details (designations, functions), course material, competencies gained, etc.)​​ | Reconfiguration Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Finalize data mapping and transformation requirements between the existing data structures and TCS iDL & Disprz data models​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Reconfigure AI instance settings, workflows, and security based on the harmonized structure and policies for TCS iDL & Disprz modules​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | FUT & SIT to validate configured TCS iDL & Disprz changes​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 12​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 13​ | UAT to validate the configurations & workflows from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 14​ | FUT & SIT to validate data migration​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 15​ | UAT to validate the data migration from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 16​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 17​ | Configuration movement in Production​ | Production Deployment Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 18​ | SF Data Migration Completion​ | Production Deployment Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 19​ | Full UK Employee Data Migration in TCS iDL & Disprz Tool​ | Data Migration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 20​ | Sanity testing for configurations & workflows​ | Production Deployment Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 21​ | Sanity Testing for full UK employee data migration​ | Data Migration Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 22​ | User training, train the trainer and new user manual/SOP creation​ | Post Deployment activities Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 23​ | Conduct training sessions to familiarize users with the re-implemented TCS iDL & Disprz system​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 24​ | UK Employees to be given TCS iDL & Disprz access on the date of Go-Live​​ | Post Deployment activities Track​ | To Do​ | AI + TCS iDL & Disprz​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 25​ | Set up monitoring process post deployment & gather feedback from end user​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 26 | Archiving data and shutting down the UK tool​ | Sunset UK Instance Track | To Do | AI + UK |  |  |  |  |  |  |  |

8. System 5. Business Expense Reimbursements – PeopleStrong Integration Strategy

- System Strategy:

  - We have evaluated following two options with respect to end state system strategy for BRE system in the Integrated Org:

    - Option 1 (Directly moving to Concur for BRE)

      - UK Employees who will move to AI over the next course of 6 months will be on secondment to AI till 27th Oct.

      - Any Reimbursements for UK & AI employees during secondment to be processed through Concur

      - AI employees will be onboarded in Concur and will follow revised polices

      - Pros: (1) Reimbursements through single system for both AI & UK employees prior to 27th Oct EOD.

      - Cons: (1) Reimbursements for AI & UK employees if done through Concur could be against the merger guidelines of keeping separate entities prior to 27th Oct EOD.

    - Option 2 (Moving to PeopleStrong during Integration & then new implementation of Concur):

      - Reimbursements for UK employees on secondment with AI prior to 27th Oct EOD to be done via Concur

      - Post 27th Oct EOD, UK employees to be onboarded on to PeopleStrong

      - Reimbursements for UK employees to be done via AI PS instance post integration on 27th Oct EOD.

      - Post Integration, new implementation of Concur to be done for Integrated UK-AI Org.

      - Pros: (1) Reimbursements via UK Concur for UK employees on secondment prior to 27th Oct EOD will ensure compliance to merger guidelines

      - Cons: (1) Employee experience related to Reimbursements would be different for AI & secondment UK employees prior to 27th Oct EOD

  - Basis the above options, we are having discussions with the Concur & PS team on the merits & demerits of the above options.

  - Detailed System Strategy for Staff Travel implementation in Concur & PS within the Integrated Org will be finalized by 24th Apr 24​.

  - We have begun discussions with HR & expect harmonized policies & processes to be shared by HR by 30th Apr 24​.

  - We will do a comparison of current policies & workflows against the finalized policies to be able to identify where all reconfigurations will be required based on harmonized policies & processes (Policies Link).

  - We will also list down available integrations with Concur & PS in AI system (SF) & required integrations within the Integrated Org.

  - Once the comparison is done & exact workflows and integrations are identified, AI Concur & PS instance will be reconfigured in Test instance by 31st July 24​.

  - We will do thorough testing (FUT, SIT & UAT) of integrated Concur & PS instance to validate reconfigurations & workflows basis UK & AI integrated Staff Travel policies by 25th Aug 24.

  - We will do Production movement of reconfigured AI Concur & PS & perform sanity tests on Production by 15th Sep 24.

  - We will do full data migration (detailed covered in below section) in Concur & PS by 22nd Oct 24.

  - User training, train the trainer and new user manual/SOP creation to be done by 31st Oct 24 to ensure adoption to the reconfigured system.

- Data Migration Strategy:

  - We have identified following data points specific to Concur & PS system which we will need to migrate from UK Travel tool to AI Concur & PS instance to ensure there is no break in the experience of UK employees migrating to AI:

    - Basic & Personal Information

    - Job Information

    - Pay components Information (Basic, HRA, Variable, Other Allowances)

    - Deduction components Information

    - Pay frequencies Information (Flying pay could be at a different frequency compared to Non-flying)

    - CTC structures Information

    - Tax Information

    - Bank details Information

    - Historical Compensation Data (Form 16, Salary Slips, CTC statements)

  - We will export all data as per above data elements from UK Concur instance.

  - We will cleanse data & rearrange the data as per AI PS upload templates by 16th Aug 24.

  - We will do FUT, SIT testing to ensure that the data is correctly migrated from UK Concur to AI PS & any anomalies can be corrected prior to UAT by end users.

  - We will do full UK employees' data migration by 24th Oct 24 (post SF data migration on 22nd Oct) prior to activation on the AI PS system ​on 28th Oct 24, 12 am.

  - UK employees will be activated on AI PS one-shot at 12 am on 28th Oct 24.

  - In order to ensure the end user adoption is high, strategy is to create User training docs, train the trainer docs & SOPs by 31st Oct 24.

  - Dependency/Decisions:

    - Need to ascertain with HR if there are any changes in policies within the Integrated Org

    - Need to ascertain with HR what process to be followed for UK employees moving on secondment to AI prior to activation on 28th Oct 12 am.

    - Testing in PeopleStrong is dependent on AI SF data migration testing – strategy is to ensure SF data migration testing is done well before PS testing to allow room for mitigating risks associated with any anomalies found.

  - Assumptions:

    - Revised policies will be shared by 30th Apr 24.

- Downstream 3rd Party Integration Strategy:

  - Since there are integrations existing already in AI PS between PS & other HR tools (SF), we will do a synchronization between PS & integrated system (3rd party) between 24th Oct 24 & 30th Oct 24.

  - 3rd Party Integration Milestone Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | Identify 3rd Party integrations with AI PS | Done | AI |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Identify common integration points & potential conflicts to create mitigation plan | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Map out data migration timelines within PS alongside SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Finalization on synchronized data migration roadmap plan between PS & SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Plan testing activities between PS & SF to align with integration steps | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Validate integrations post data migration to ensure seamless operations | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Coordinate deployment activities & timelines between PS & SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Full UK employees’ data migration from UK SF to AI SF | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Testing of data flowing correctly into AI PS | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Sanity testing of data flowing into 3rd party integrated systems | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | Post data migration support to be provided by HR Tech team | To Do | AI + UK |  | ​ | ​ | ​ | ​ | ​ | ​ | ​ |

- Contract Rationalization & Consolidation Strategy:

  - ​We will revisit AI’s PS license contract for renegotiation on commercial terms basis increased volumes.

  - We will procure additional PS licenses for UK employees.

  - Assumption:

    - Concur license & contract of UK employees will be terminated & contracts within PS AI to be extended for UK employees.

  - We will continue with PS team as AMS partner for UK and AI –

    - Option 1 is to continue with current AI PS AMS partner & extend the contract for UK employees.

    - Option 2 is to move to another SF AMS partner & negotiate contract for the Integrated Org

    - Recommended Option: Option 1

    - Rationale: Decision is basis the satisfactory historical performance record of current AMS partner with AI; hence moving to another partner for integrated Org would not make sense

- System Sunset Strategy:

  - We will migrate all UK employee's data from UK Concur Instance to AI PS Instance by 30th Sep 24​

  - We will review scope of historical data to be migrated –

    - Option 1: Migrate entire historical data of UK employees for entire past duration.

    - Option 2: Migrate specific employee historical data for a certain duration in past​.

  - We will review the timeline till which UK Concur instance needs to be kept active post 28th Oct 24, 12 am & determine the sunset timeline accordingly by 30th Apr 24.

- Detailed Roadmap Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | SAP & PeopleStrong (OEM) Kick Off Discussion​ | Assessment and Planning Track​ | In Progress​ | AI+SAP+PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Finalize decision on continuing with PS or Concur as BRE tool​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Understand HR processes, policies & requirements of integrated Org​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Contract review to identify scope of renegotiation​ | Contract Rationalization Track​ | To Do​ | AI + PS/SAP​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Gap Analysis between UK SF & AI existing PS instances and harmonized Org's requirement​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Overall Integration & Data Migration Strategy Option Finalization with PS & SAP team (OEM) Buy-In​ | Assessment and Planning Track​ | To Do​ | AI+SAP+PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Review data governance policies including correct access control for integrated Org​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Receiving of Harmonized Org Structure & Policies from HR​ | Reconfiguration Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Identify the scope of data to be migrated (learning history, personal details, employment details (designations, functions), course material, competencies gained, etc.)​​ | Reconfiguration Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Finalize data mapping and transformation requirements between the existing data structures and BRE data models​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | Reconfigure AI instance settings, workflows, and security based on the harmonized structure and policies for BRE modules​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 12​ | FUT & SIT to validate configured BRE changes​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 13​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 14​ | UAT to validate the configurations & workflows from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 15​ | FUT & SIT to validate data migration​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 16​ | UAT to validate the data migration from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 17​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 18​ | Configuration movement in Production​ | Production Deployment Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 19​ | SF Data Migration Completion​ | Production Deployment Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 20​ | Full UK Employee Data Migration in BRE Tool​ | Data Migration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 21​ | Sanity testing for configurations & workflows​ | Production Deployment Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 22​ | Sanity Testing for full UK employee data migration​ | Data Migration Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 23​ | User training, train the trainer and new user manual/SOP creation​ | Post Deployment activities Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 24​ | Conduct training sessions to familiarize users with the re-implemented BRE system​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 25​ | UK Employees to be given BRE access on the date of Go-Live​​ | Post Deployment activities Track​ | To Do​ | AI + SAP/PS​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 26 | Set up monitoring process post deployment & gather feedback from end user​ | Post Deployment activities Track​ | To Do​ | AI​ |  |  |  |  |  |  |  |
| 27 | Archiving data and shutting down the UK tool​ | Sunset UK Instance Track​ | To Do​ | AI + UK​ |  |  |  |  |  |  |  |

9. System 6. Rewards & Recognition – Advantage Club Integration Strategy

- System Strategy:

  - We have evaluated following two options with respect to end state system strategy for Advantage Club system in the Integrated Org:

    - Option 1 (R&R for secondment UK employees through existing UK Staff system and in Advantage Club post 27th Oct EOD):

      - R&R for UK employees on secondment with AI prior to 27th Oct EOD to be done via UK tool

      - Post 27th Oct EOD, UK employees to be onboarded on to Advantage Club

      - R&R for UK employees to be done via AI Advantage Club instance post integration on 27th Oct EOD.

      - Pros: (1) R&R via UK tool for UK employees on secondment prior to 27th Oct EOD will ensure compliance to merger guidelines

      - Cons: (1) Employee experience related to R&R would be different for AI & secondment UK employees prior to 27th Oct EOD

  - Basis the above option, we are having discussions with the Advantage Club team on the merits & demerits of the above options.

  - Detailed System Strategy for Staff Travel implementation in Advantage Club within the Integrated Org will be finalized by 24th Apr 24​.

  - We have begun discussions with HR & expect harmonized compensation structure, policies & processes to be shared by HR by 30th Apr 24​.

  - We will do a comparison of current policies & workflows against the finalized policies to be able to identify where all reconfigurations will be required based on harmonized policies & processes (Policies Link).

  - We will also list down available integrations with Advantage Club in AI system (SF) & required integrations within the Integrated Org.

  - Once the comparison is done & exact workflows and integrations are identified, AI Advantage Club instance will be reconfigured in Test instance by 31st July 24​.

  - We will do thorough testing (FUT, SIT & UAT) of integrated Advantage Club instance to validate reconfigurations & workflows basis UK & AI integrated Staff Travel policies by 25th Aug 24.

  - We will do Production movement of reconfigured AI Advantage Club & perform sanity tests on Production by 15th Sep 24.

  - We will do full data migration (detailed covered in below section) in Advantage Club by 22nd Oct 24.

  - User training, train the trainer and new user manual/SOP creation to be done by 31st Oct 24 to ensure adoption to the reconfigured system.

- Data Migration Strategy:

  - We have identified following data points specific to Advantage Club system which we will need to migrate from UK tool to AI Advantage Club instance to ensure there is no break in the experience of UK employees migrating to AI:

    - Basic & Personal Information

    - Job Information

  - We will export all data as per above data elements from UK tool instance.

  - We will cleanse data & rearrange the data as per AI Advantage Club upload templates by 16th Aug 24.

  - We will do FUT, SIT testing to ensure that the data is correctly migrated from UK tool to AI Advantage Club & any anomalies can be corrected prior to UAT by end users.

  - We will do full UK employees' data migration by 24th Oct 24 (post SF data migration on 22nd Oct) prior to activation on the AI Advantage Club system ​on 28th Oct 24, 12 am.

  - UK employees will be activated on AI Advantage Club one-shot at 12 am on 28th Oct 24.

  - In order to ensure the end user adoption is high, strategy is to create User training docs, train the trainer docs & SOPs by 31st Oct 24.

  - Dependency/Decisions:

    - Need to ascertain with HR if there are any changes in policies within the Integrated Org

    - Need to ascertain with HR what process to be followed for UK employees moving on secondment to AI prior to activation on 28th Oct 12 am.

    - Testing in Advantage Club is dependent on AI SF data migration testing – strategy is to ensure SF data migration testing is done well before PS testing to allow room for mitigating risks associated with any anomalies found.

  - Assumptions:

    - Revised policies will be shared by 30th Apr 24.

- Downstream 3rd Party Integration Strategy:

  - No specific integrations exist which need to be taken care of as part of current scope.

- Contract Rationalization & Consolidation Strategy:

  - ​We will revisit AI’s Advantage Club license contract for renegotiation on commercial terms basis increased volumes.

  - We will procure additional Advantage Club licenses for UK employees.

  - We will continue with Advantage Club team as AMS partner for UK and AI –

    - Option 1 is to continue with current AMS partner & extend the contract for UK employees.

    - Option 2 is to move to another AMS partner & negotiate contract for the Integrated Org

    - Recommended Option: Option 1

    - Rationale: Decision is basis the satisfactory historical performance record of current AMS partner with AI; hence moving to another partner for integrated Org would not make sense

- System Sunset Strategy:

We will migrate all UK employee's data from UK tool Instance to AI Advantage Club Instance by 30th Sep 24​

  - We will review scope of historical data to be migrated –

    - Option 1: Migrate entire historical data of UK employees for entire past duration.

    - Option 2: Migrate specific employee historical data for a certain duration in past​.

  - We will review the timeline till which UK tool instance needs to be kept active post 28th Oct 24, 12 am & determine the sunset timeline accordingly by 30th Apr 24.

- Detailed Roadmap Plan:

| S.No.​ | Summary​ | Stage​ | Status​ | Owner​ | Apr​ | May​ | June​ | July​ | Aug ​ | Sep​ | Oct​ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1​ | Advantage Club (OEM) Kick Off Discussion​ | Assessment and Planning Track​ | In Progress​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 2​ | Understand HR processes, policies & requirements of integrated Org​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 3​ | Contract review to identify scope of renegotiation​ | Contract Rationalization Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 4​ | Gap Analysis between UK instance & AI existing Advantage Club instances and harmonized Org's requirement​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 5​ | Overall Integration & Data Migration Strategy Option Finalization with Advantage Club team (OEM) Buy-In​ | Assessment and Planning Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 6​ | Review data governance policies including correct access control for integrated Org​​ | Assessment and Planning Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 7​ | Receiving of Harmonized Org Structure & Policies from HR​ | Reconfiguration Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 8​ | Identify the scope of data to be migrated (pending passages as per policy, personal details, employment details, manager details, etc.)​​ | Reconfiguration Track​ | To Do​ | AI + UK​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 9​ | Finalize data mapping and transformation requirements between the existing data structures and Advantage Club data models​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 10​ | Reconfigure AI instance settings, workflows, and security based on the harmonized structure and policies for Advantage Club modules​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 11​ | FUT & SIT to validate configured Advantage Club changes​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 12​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 13​ | UAT to validate the configurations & workflows from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 14​ | FUT & SIT to validate data migration​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 15​ | UAT to validate the data migration from end-users' perspective​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 16​ | Create Deployment Plan & Roll-back plan in case of issues​ | Reconfiguration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 17​ | Configuration movement in Production​ | Production Deployment Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 18​ | SF Data Migration Completion​ | Production Deployment Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 19​ | Full UK Employee Data Migration in Advantage Club Tool​ | Data Migration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 20​ | Sanity testing for configurations & workflows​ | Production Deployment Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 21​ | Sanity Testing for full UK employee data migration​ | Data Migration Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 22​ | User training, train the trainer and new user manual/SOP creation​ | Post Deployment activities Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 23​ | Conduct training sessions to familiarize users with the re-implemented Advantage Club system​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 24​ | UK Employees to be given Advantage Club access on the date of Go-Live​​ | Post Deployment activities Track​ | To Do​ | AI + Adv Club​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 25​ | Set up monitoring process post deployment & gather feedback from end user​ | Post Deployment activities Track​ | To Do​ | AI​ | ​ | ​ | ​ | ​ | ​ | ​ | ​ |
| 26 | Archiving data and shutting down the UK tool​ | Sunset UK Instance Track​ | To Do​ | AI + UK​ |  |  |  |  |  |  |  |